RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO COMMUNITY COMMITTEE

Agenda Item No

meeting date: 	6 NOVEMBER 2007

title:	CAPITAL MONITORING 2007/08

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

- PURPOSE

  - To update members with progress on the Capital Programme for this committee for the current financial year.

- BACKGROUND

  - The Capital Programme for 2007/08 was approved in February 2007.  In the March cycle of committee meetings capital reports were considered which included capital evaluation statements giving full details of all new schemes for the forthcoming year.

- PROGRESS TO DATE

  - The table below shows a financial summary of the progress on the capital programme.

| Budget Analysis | Expenditure Analysis |
| --- | --- |
| Original | Slippage | Additional | Total | Total |
| Estimate |  | Approvals | Approved | Expenditure |
| 2007/08 |  |  | Budget | To Date |
| £ | £ | £ | £ | £ |
| 1,723,160 | 250,380 | 151,210 | 2,124,750 | 376,307 |

  - Annex 1 shows the full programme by scheme.

  - You will see from the above table additional approvals, since the original programme was approved, have been brought into the programme with a net total of £151,210.  Indeed there are a number of schemes where the original budget has proved to be incorrect. These include the following changes:

| Scheme | Cost/Saving |  |
| --- | --- | --- |
| Badger Well Water Sewer Collapse – to carry out necessary remedial works | £10.000 |  |
| Relocation of Sports Centre Gym to Longridge Civic Hall Net additional cost to the council (dependant on success of grant application) | Up to £31,600 |  |
| Rose Garden – extra costs as reported to committee | £22,100 |  |
| Refuse Collection/Recycling Vehicles – savings in current year | -£22,600 |  |
| but extra costs added to next year (2008/09) capital programme for wheeled bins/chips | £90,100 |  |
| Increase in cost of bin lift for current year | £4,300 |  |
| Pool Boiler Replacement – will cost more than originally planned but will be offset from savings on Pool Energy Efficiency Capital Scheme. |  |  |
| Chipping Toilets – increased costs of | £8,800 |  |
| Castle Keep Repairs shortfall of | £50,600 |  |
| consisting of additional expenditure of |  | £25,600 |
| and anticipated grant funding that did not materialise |  | £25,000 |
| Net Total of changes | 194,900 |  |

3.4	The Castle Lottery Scheme (CSLOT) has been brought into the capital programme at full cost of £3.2m.  Details are given on the evaluation sheet.

- CAPITAL EVALUATION STATEMENTS

  - As most members will be aware the individual officers responsible for schemes in the capital programme complete an evaluation sheet prior to the start of the scheme.  Statements are then updated to show progress/any changes and reported to committee ideally on a quarterly basis.

  - The statements are attached at Annex 2 (YELLOW) and have been updated by the individual officers to show ‘Progress to End of September 2007’.

5	CONCLUSION

  - Considerable changes have taken place already during the financial year regarding this committee’s capital programme.  It is important that monitoring continues to ensure the programme is achieved within the individual budgets.

- RECOMMENDED THAT COMMITTEE

  - Review the capital evaluation sheets to consider the progress made and any comments members may wish to make.

FINANCIAL SERVICES MANAGER

CM6-07/JP/AC

17 OCTOBER 2007

|  |  | Budget Analysis | Expenditure Analysis |
| --- | --- | --- | --- |
| Schemes | budget holder | Original | Slippage | Additional | Total | Total |
|  |  | Estimate |  | Approvals | Approved | Expenditure |
|  |  | 2007/08 |  |  | Budget | To Date |
|  |  | £ | £ | £ | £ | £ |
| Badger Well Water Culvert Collapse | je |  |  | 10,000 | 10,000 | 0 |
| Brungerley Park Sculpture Trial | ch |  |  | 14,620 | 14,620 | 3,874 |
| Provision of shelter in Woodland Cemetery | jr | 8,500 |  |  | 8,500 | 0 |
| Castle Lottery scheme | ch | 33,750 | 9,910 |  | 43,660 | 158,048 |
| Edisford Changing Rooms | rp | 65,000 |  |  | 65,000 | 0 |
| Relocate fitness room at LSC to Longridge Civic Hall | ch | 18,600 |  | 196,000 | 214,600 | 0 |
| Replace Boiler at Platform Gallery | rp | 11,000 |  |  | 11,000 | 8,633 |
| Gisburn Forest Park Cycling Trails | gj | 20,000 |  |  | 20,000 | 0 |
| Castle Keep Repairs - Phase 1 | ch |  | 48,480 |  | 48,480 | 62,467 |
| Provision of Fire Escape at Longridge Depot | rp | 6,300 | -1,510 |  | 4,790 | 1,457 |
| Grant Aid to Longridge Action Group re Civic Hall | ch |  | 10,000 | -10,000 | 0 | 0 |
| Longridge Skate Park Retention | ch |  |  | 3,000 | 3,000 | 380 |
| Longridge Sports Centre Reception | rp | 54,410 |  | -54,410 | 0 | 110 |
| Pool - Replace boiler and calorifier | rp | 96,300 |  |  | 96,300 | 2,600 |
| Refurbishment of Chipping Toilets | rp | 75,000 |  | 8,800 | 83,800 | 2,637 |
| Replace Slaidburn Toilets | rp |  | 2,500 |  | 2,500 | 2,234 |
| Funding towards reconstruction of Whalley Toilets | rp | 50,000 |  |  | 50,000 | 0 |
| Replace Suzuki Van - PJ02 NNA | gj | 10,000 |  |  | 10,000 | 9,297 |
| Improvements to children's play areas | gj | 50,000 |  |  | 50,000 | 1,045 |
| Energy Efficiency measures to Ribblesdale Pool | rp | 104,500 |  |  | 104,500 | 499 |
| Replace Steel Windows to building at Ribblesdale Pool | rp | 36,400 |  |  | 36,400 | 0 |
| Replace Refuse Collection Vehicle | gj |  | 180,000 | -4,200 | 175,800 | 0 |
| Recycling and Residual Waste Containers | pmcg | 408,500 |  |  | 408,500 | 0 |
| Refurbishment of Ribchester Public Conveniences | rp |  | 1,000 |  | 1,000 | 126 |
| Bin Lifts (x2) for existing Refuse Vehicles & ID system | gj | 30,900 |  | 4,300 | 35,200 | 0 |
| Rose Garden Castle Grounds | ch |  |  | 1,500 | 1,500 | 1,503 |
| Small Compressor Ingersoll Rand | gj | 5,100 |  |  | 5,100 | 0 |
| Replace P051 DHM Iveco Daily with roll on/roll off 6 tonne pick up | gj | 47,900 |  |  | 47,900 | 34,764 |
| Replace Landrover J438 JFV | gj | 15,000 |  |  | 15,000 | 14,643 |
| Vehicle Lifting Equipment | gj | 13,000 |  |  | 13,000 | 13,370 |
| Replace Hayter Triple Mower LT322 2WD | gj | 25,700 |  |  | 25,700 | 24,980 |
| Replace G516 OCK with landrover & trailer | gj | 18,500 |  |  | 18,500 | 18,448 |
| Replace R563 SFR John Deere Ride On Mower | gj | 14,900 |  |  | 14,900 | 15,193 |
| New Vehicle Three Stream Waste Collection | gj | 190,000 |  | -14,200 | 175,800 | 0 |
| Replace W697 WHP Dennis Refuse Collection Vehicle | gj | 180,000 |  | -4,200 | 175,800 | 0 |
| Longridge Sports Centre Replace carpet on synthetic pitch | rp | 133,900 |  |  | 133,900 | 0 |
| Total Community Committee |  | 1,723,160 | 250,380 | 151,210 | 2,124,750 | 376,307 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | BADWC |
| Name of Scheme | Badger Well Water Culvert Collapse |
| Officer Responsible | John Edwards |
| Description of Scheme | To carry out necessary remedial works at Badger Well Water, Sabden due to Culvert Collapse. |
| Benefits of Scheme | To protect and enhance the environmental quality of our area |
| Project Timetable | Start Date |  |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | An investigation has been carried out to establish land ownership as the landowner is responsible for the repair under land drainage legislation. However a land registry search has returned information that the land in the vicinity of the culvert collapse is unregistered. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose |  |
| What are the revenue implications of the scheme? |  |

|  |  |  |  |  |  | Cost Centre | BADWC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £10,000 |  |
| Summary | Expected Total Cost of Scheme: | £10,000 |  |
|  | Approved by Committee: | Policy & Finance |
|  | Date: |  |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 10,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 10,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End September 2007 | As reported to community committee. Property flooding has occurred in Sabden. This scheme is necessary to carry out identified works and reduce the risk of further flooding from Badger Well Water. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | BPSCT |
| Name of Scheme | REPLACEMENT OF BRUNGERLEY SCULPTURE TRAIL |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | Replace public art pieces in Brungerley Park |
| Benefits of Scheme | Improve environment of park |
| Project Timetable | Start Date | April 2003 |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
|  |  | Develop annual projects to replace one sculpture each year for the duration of the project |
| Indication of any problems | None, although each piece will rely on a partnership between community groups and artists |
| Grants Rec'd Brungerly Park Sculpture Trail Grant from Market Towns Initiative 12,000 LCC - Brungerly Park Sculpture Trail Grant 4,500 16,500 |
| Financial | Original Budget for Current Year: | £5,400 |  |
| Summary | Slippage from 2005/06 | £15,300 |  |
|  | Total budget for current year: | £14,620 |  |
|  | Expected Total Cost of Scheme: | £37,320 |  |
|  | Approved by Committee: | Council |
|  | Date: | 4 March 2003 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  | Actual Expenditure 2003/04 £ | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  | 110 | 22,586 | 14,620 | 37,316 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | TOTAL |  | 110 | 22,586 | 14,620 | 37,316 |
|  |  |  |  |  | Cost Centre | BPSCT |
| End August 2003 | Potential to expand trail. External funding is being explored before project is started. Still able to implement original timetable. |
| End Dec 2003 | Work still being carried out on project details. |
| End June 2004 | Waiting to see if our investment can be matched through money within the Market Towns Initiative to provide an enhanced scheme. |
| End Nov 2004 | As above, however need to set a deadline with Clitheroe the Future to determine whether an enhanced scheme is possible otherwise Ribble Valley to run its own scheme early next year. Due to this suggest money moved to 2005/06. |
| End June 2005 | In final stages of securing match funding. Will shortly be commencing scheme. Artist to start work. |
| End Sept 2005 | Awaiting to confirm funding via Clitheroe the Future. Sent out initial expressions of interest for commissions for local artist to start the work. |
| End Dec 2005 | Work to start January 2006. |
| End March 2006 | Problems in delay in securing matched funding via Clitheroe The Future. Just heard that we have £12,000 and so are able to start someone. Artists have been commissioned but this will mean that the bulk of the expenditure will be in 2006/07. |
| End Sept 2006 | Sculptures being made for 2006-07 expenditure for installation from Dec – March. |
| End Dec 2006 | Plan to install sculptures for end March |
| End September 2007 | Four new sculptures installed and one to be installed in October 07 to complete Phase 1. Match funding for Phase 2 from LCC Arts Unit and Wildlife Trust. Brief for artists now released and artists selection by end of October. Installation from Nov – March 08 for 2007/08 expenditure. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CCSHE |
| Name of Scheme | PROVISION OF SHELTER IN WOODLAND CEMETERY |
| Officer Responsible | JAMES RUSSELL |
| Description of Scheme | Shelter for woodland burials made in traditional style |
| Benefits of Scheme | Focal point in woodland, providing shelter for visitors and bereaved |
| Project Timetable | Start Date | In progress |
|  | Completion Date | February 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None foreseeable other than weather conditions and funerals affecting work pattern |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | No, will need outside contractor |
| What are the revenue implications of the scheme? | Improved service which will promote woodland burial scheme |

|  |  |  |  |  |  | Cost Centre | CCSHE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £8,500 |  |
| Summary | Expected Total Cost of Scheme: | £8,500 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 8,500 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 8,500 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Regular inspections during and on completion of construction |
| End September 2007 | Agreed design and location. Obtaining estimates from contractors. To implement as soon as quotation accepted. Work to be undertaken during winter/early in new year subject to weather |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CSLOT |
| Name of Scheme | CASTLE LOTTERY SCHEME |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | Redevelopment of Castle Museum and associated buildings into all-weather visitor attraction |
| Benefits of Scheme | Future sustainability of Museum Sound Archive and Parks Buildings |
| Project Timetable | Start Date | September 2007 |
|  | Completion Date | Spring 2009 |
|  | Any Other Key Dates | Description of Work |
|  | 8th March | - HLF Panel Date |
| Indication of any problems which may ultimately affect either the project timetable or final costs | A negative decision from HLF |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | No, external Project Managers have been appointed |
| What are the revenue implications of the scheme? | To be confirmed through negotiation with county museum service |

|  |  |  |  |  |  | Cost Centre | CSLOT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £3,223,820 |  |
| Summary | Expected Total Cost of Scheme: | £3,240,320 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Construction Works |  |  | 2,337,107 |
|  | Exhibition Fit-Out |  |  |  | 379,500 |
|  | Other Fit-Out/RVBC Supply Items |  |  | 110,651 |
|  | Professional Fees – Turner & Townsend |  |  | 396,561 |
|  | Promotional Activities |  |  | 16,500 |
|  | Other |  |  |  |  | 0 |
|  | TOTAL |  |  |  | 900,000 | 3,240,319 |
| Scheme Funding |
| Heritage Lottery Fund 1,835,260 Ribble Valley existing Capital Programme 176,160 Clitheroe The Future NWDA 250,000 SITA 135,000 Private Sector Sponsorship 100,000 Friends of Clitheroe Castle 16,245 Clitheroe Town Council 5,000 2,517,665 Cost of Scheme from above 3,240,319 Shortfall 722,654 Funding Applied For Lancashire Economic Partnership 770,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End September 2007 | Main contract let and due for completion November 2008. Scheme completion estimated Spring 2009. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | EDCHR |
| Name of Scheme | EDISFORD CHANGING ROOMS |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Improvements to changing rooms including removal of asbestos, tank fed hot water and provision of new showers. |
| Benefits of Scheme | Improved facilities for customers |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Discussions still ongoing with Roefield re: joint scheme, start on site currently on hold |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | EDCHR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £65,000 |  |
| Summary | Expected Total Cost of Scheme: | £65,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 65,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 65,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Asbestos survey done, price for removal of same being sought. Price for showers obtained, preparatory design work commenced but scheme on hold pending conclusion of discussions with Roefield re: joint scheme. |
| End September 2007 | Joint scheme shelved. Asbestos removal to be carried out as part of refurbishment. Design continuity based upon Match funding from football foundation Existing development refurbishment based on current budget |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | FITRM |
| Name of Scheme | RELOCATE FITNESS ROOM AT LSC TO LONGRIDGE CIVIC HALL |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | Construction of permanent gym facility at Longridge Civic Hall |
| Benefits of Scheme | To provide better access to facilities and improve sustainability of Civic Hall |
| Project Timetable | Start Date | Dec 2007 |
|  | Completion Date | May 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | The possibility of a permanent replacement over the next 12 months is being explored as this will generate better value for money. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Being worked up as part of service planning process |

|  |  |  |  |  |  | Cost Centre | FITRM |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Original Approved Budget for Current Year: | £18,600 |  |
|  | Additional Approvals | £196,000 |  |
| Summary | Expected Total Cost of Scheme: | £214,600 |  |
|  | Approved by Committee: | Full Council & Spec P&F |
|  | Date: | 6 March 2007 & 29 Aug 07 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 214,600 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 214,600 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End September 2007 | Joint scheme for construction of childrens centre and gym agreed by Policy and Finance committee. Funding as follows: (Total Cost £214,600) Current capital budget £18,600 Civic Hall Grant £100,000 Transferred from LSC reception capital budget £54,400 PCT Grant £10,000 Sport England £20,000 (to be confirmed) LSP £11,600 (to be confirmed) £214,600 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | GALBO |
| Name of Scheme | REPLACE BOILER AT PLATFORM GALLERY |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Replacement boiler at Gallery |
| Benefits of Scheme | Reduction in breakdowns and more efficient heating system |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Reduced running costs |

|  |  |  |  |  |  | Cost Centre | GALBO |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £11,000 |  |
| Summary | Expected Total Cost of Scheme: | £11,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 11,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 11,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Prices to be obtained be end of May 2007 work to be undertaken during summer months. |
| End September 2007 | Boiler replacement complete. CCTV installed within scheme as identified in service plan. Remainder of budget utilised to carry out fire protection work in cellar. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | GFCYC |
| Name of Scheme | GISBURN FOREST PARK CYCLING TRAILS |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Financial support to major improvement scheme |
| Benefits of Scheme | Improved facilities for cyclists and tourism generation |
| Project Timetable | Start Date | April 2007 |
|  | Completion Date | January 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Development of agreed schemes and approval from other partners and funding streams |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | GFCYC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £20,000 |  |
| Summary | Expected Total Cost of Scheme: | £20,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 20,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 20,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Discussions ongoing with other funding partners |
| End September 2007 | Match funding is currently being secured and commencement of the scheme is expected March 2008. The total amount in the budget will be spent in the 2008/09 financial year alongside a further £160,000 from other funding. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | KEEPR |
| Name of Scheme | CASTLE KEEP IMPROVEMENTS – PHASE 1 |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | Health and Safety improvements, permanent flood lighting and refurbishment of garden areas and signage |
| Benefits of Scheme | Improvements to keep |
| Project Timetable | Start Date | January 07 |
|  | Completion Date | March 07 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Securing all external funding |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose |  |
| What are the revenue implications of the scheme? | None |
| Funding | Phase 2 brought into 5 year Capital Programme - £110,000 in 2008/09 as a new bid |
|  | £ Total cost of Phase 1 = 79,400 To be funded from: Lancashire Environmental Fund -25,000 Clitheroe Rotary Club -1,800 Regional Park Grant -39,400 From RVBC 13,200 |
|  | (To be met from Castle Lottery scheme monies in 5 year capital prog) i.e. 2007/08 allocation reduced by £13,200 |

|  |  |  |  |  |  | Cost Centre | KEEPR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £48,480 |
| Summary | Expected Total Cost of Scheme: | £105,000 |
|  | Approved by Committee: |  |
|  | Date: |  |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 30,924 | 74,050 | 104,974 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  | 30,924 | 74,050 | 104,974 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End Dec 2006 | Started on site early Jan 07 with Phase 1 Scheme Grant application made to Regional Park (Approved) and also made to LEF. |
| End September 2007 | Work complete with exception of decoration of railings. Extra work (£2,000) was required for Health and Safety measures to the railings. £25,000 funding from Lancashire Environmental Fund identified at start of project will not now be forthcoming. Original budget was for £79,400 and this was based on received £25,000 funding from LEF. Total cost identified now as £105,000 which results in an effective shortfall on scheme of £50,600. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | LFIRD |
| Name of Scheme | PROVISION OF FIRE ESCAPE LONGRIDGE DEPOT |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | The need for the provision of a first floor fire escape has been identified as a priority within the fire risk assessment. This will provide alternative means of escape from first floor work and storage areas. Within the scheme would also be the demolition of s single storey asbestos and brick store. |
| Benefits of Scheme | Health and safety and comply with fire precautions workplace regulation |
| Project Timetable | Start Date | Scheme moved to 2007/08 |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Anticipated to be within scheme budget |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Minor addition to electricity bills for extra lighting to stairs |

|  |  |  |  |  |  | Cost Centre | LFIRD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £6,300 |  |
| Summary | Expected Total Cost of Scheme: | £6,300 |  |
|  | Approved by Committee: | Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: | 755 |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 5,900 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  | 400 |
|  | TOTAL |  |  |  |  | 6,300 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | Scheme design to commence April 2006. Demolition of existing store March 2006. |
| End Sept 2006 | Scheme delayed due to need for asbestos removal. Estimates for fire escape requested. Anticipated commencement Feb 07. |
| End Dec 2006 | Quotes currently being sought for asbestos removal and demolition. Work anticipated to commence February 2007 |
| End March 2007 | Scheme moved to 2007/08 Capital Programme. Asbestos removal and demolition carried out. Quote for fire escape obtained, sent off confirmation of acceptance of quote start on site April 2007 |
| End September 2007 | Fire Escape complete. Exit door on site October 07. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | LOCHG |
| Name of Scheme | GRANT AID TO LONGRIDGE ACTION GROUP FOR CIVIC HALL |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | Improvements to reception/entrance |
| Benefits of Scheme | Improving access and better use of space |
| Project Timetable | Start Date | May 2005 |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Final costs will not change but timetable is reliant on Longridge Action Group signing their lease |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | LOCHG |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2006/07: | £10,000 |  |
| Summary | Budget Transferred to Fitness Room Relocation Scheme: | -£10,000 |  |
|  | Expected Total Cost of Scheme: | 0 |  |
|  | Approved by Committee: | Council |
|  | Date: | 2 March 2005 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  | 0 | 0 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  | 0 | 0 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| June 2005 | Awaiting receipt of proposal from Longridge Action Group. |
| End Sept 2005 | Still awaiting receipt of proposal from Longridge Action Group. |
| End Dec 2005 | Still awaiting receipt of proposal from Longridge Action Group. |
| End Sept 2006 | Designs for new reception being produced |
| End Dec 2006 | Designs still underway for new reception. |
| End September 2007 | Will be used to part fund the re-location of the sports centre gym to the civic hall |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | LSREC |
| Name of Scheme | LONGRIDGE SPORTS CENTRE RECEPTION |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Relocation of fitness suite from first floor to ground floor incorporating bar area |
| Benefits of Scheme | To comply with DDA Act and also enhance existing facilities |
| Project Timetable | Start Date | Dependant on negotiations with LCC |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
|  |  | Fitness suite relocated and extended to ground floor to comply with DDA |
| Indication of any problems which may ultimately affect either the project timetable or final costs | See notes over |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Ongoing maintenance |

|  |  |  |  |  |  | Cost Centre | LSREC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £54,410 |  |
|  | Budget Transferred to Gym Relocation at Civic Hall | -£54,410 |  |
| Summary | Expected Total Cost of Scheme: | £130,951 |  |
|  | Approved by Committee: | Council |
|  | Date: | 2 March 2005 |
|  | Minute Ref: | 762 |
| Expenditure Analysis |  |  | Actual Expenditure 2004/05 £ | Actual Expenditure 2005/06 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  | 128,495 | 2,456 | 0 | 130,951 |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  | 128,495 | 2,456 | 0 | 130,951 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2004 | Scheme is 75% complete. Toilet and changing room work to commence in August. New fitness suite to be opened shortly. |
| End Aug 2004 | Scheme to fitness suite complete. Work to toilet and changing rooms to commence October. Awaiting completion of public conveniences prior to commencement of this scheme. |
| End Nov 2004 | Works complete to function room. Public conveniences work to commence in January 2005. |
| End June 2005 | Scheme is on hold at the moment. Awaiting outcome of decision on the future arrangements at the sports centre. |
| End Sept 2005 | No further progress made since the end of June. |
| End Dec 2005 | No further progress made since the end of June. |
| End March 2006 | Scheme on hold due to negotiation with Lancashire County Council. Some expenditure due March 2006 in relocation of fitness suite to Longridge Civic Hall, anticipated cost £12,500 |
| End Sept 2006 | Scheme on hold due to negotiations with LCC. Some expenditure anticipated due to relocation of fitness suite to Longridge Civic Hall anticipated cost £18,500. Decision due from Committee Nov 06 if scheme is to proceed. |
| End Dec 2006 | Scheme as above on hold, no decision received from Committee, to date. |
| End March 2007 | Scheme budget moved to 2007/08. Scheme as above on hold, no decision received from Committee to date. |
| End Sept 2007 | Budget moved to Relocation of Gym to Longridge Civic Hall Scheme. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PBOIL |
| Name of Scheme | POOL – REPLACE BOILER AND CALORIFIER |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Replacement of oil boiler for gas boiler |
| Benefits of Scheme | Energy efficiency, reduced fuel usage |
| Project Timetable | Start Date | Design stage to commence March 2006 |
|  | Completion Date | Scheme currently on hold |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | See notes overleaf |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Decrease in fuel usage and therefore cost |

|  |  |  |  |  |  | Cost Centre | PBOIL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £96,300 |  |
| Summary | Expected Total Cost of Scheme: | £130,000 |  |
|  | Approved by Committee: | Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: | 755 |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 108,725 |
|  | Retention (show separately) |  |  |  | 2,275 |
|  | Building Regulations Fee |  |  |  | 352 |
|  | External Fees |  |  |  |  | 11,100 |
|  | Internal Salaries |  |  |  |  | 7,500 |
|  | TOTAL |  |  |  |  | 129,952 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | The scheme has previously been held back awaiting finalisation of Edisford changing room scheme and of associated consequences. However, the decision has now been taken to enter a joint scheme for the changing rooms with Roefield and therefore the boiler will be stand alone supplying the pool only. Consultants will be employed early in the financial year to carry out design of scheme and provide an accurate estimate of costs. |
| End Sept 2006 | Scheme back on hold following consultants appraisal of whole site management arrangements. Report to committee November 2006 re: trust recommendations to include boiler situation. |
| End Dec 2006 | Scheme on hold no decision received from Committee |
| End March 2007 | Scheme budget moved to 2007/08. Progress as above. |
| End September 2007 | Consultants preparing specification of work for boiler replacement. Scheme will overspend. Intention to combine this scheme with Energy Efficiency scheme (POENE). |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PCCHI |
| Name of Scheme | REFURBISHMENT OF CHIPPING TOILETS |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Refurbishment of toilets in June with similar schemes recently undertaken |
| Benefits of Scheme | Improvement of facilities for customers. DDA compliance |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Scheme anticipated to overspend due to increase in materials costs since original tender |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | PCCHI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £75,000 |  |
| Summary | Expected Total Cost of Scheme: | £83,800 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 72,440 |
|  | Retention (show separately) |  |  |  | 1,860 |
|  | Other Costs - Electrical |  |  |  | 2,000 |
|  | External Fees |  |  |  |  | 4,500 |
|  | Internal Salaries |  |  |  |  | 3,000 |
|  | TOTAL |  |  |  |  | 83,800 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Scheme initially drawn up 4 years ago requires slight amendments before going out to tender. Lease needs finalising Graham Jagger leading on this no indication of any problems |
| End September 2007 | Work commenced September 2007. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PCRPE |
| Name of Scheme | PUBLIC CONVENIENCES – SLAIDBURN |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Demolition of existing public conveniences and rebuild new due to ongoing problem with user capacity |
| Benefits of Scheme | Larger facility to cater for large demand |
| Project Timetable | Start Date | October 2005 |
|  | Completion Date | August 2006 |
|  | Any Other Key Dates | Description of Work |
|  | Spring 2006 | Building control application |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Originally this scheme was for Dunsop Bridge but due to problems obtaining permission from the Duchy of Lancaster the scheme was “swapped” with Slaidburn public conveniences due in 2007/08. Scheme altered to reconstruct Slaidburn conveniences. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Increased cleaning cost and materials and potential higher rateable value. However, this will be a new facility and therefore should be cheaper to maintain. |

|  |  |  |  |  |  | Cost Centre | PCRPE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Budget for Current Year: | £2,500 |  |
|  | Original Total Budget: | £125,040 |  |
| Summary | Expected Total Cost of Scheme: | £127,499 |  |
|  | Approved by Committee: | Council |
|  | Date: | 1 March 2005 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  | Actual Expenditure 2005/06 £ | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  | 13,703 | 104,425 |  | 118,128 |
|  | Retention (show separately) |  |  | 2,500 | 2,500 |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  | 2,603 | 4,268 |  | 6,871 |
|  | TOTAL |  | 16,306 | 108,693 | 2,500 | 127,499 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| June 2005 | Specification in production. Potential delay on start date due to outstanding permission from landowner. |
| End Sept 2005 | Specification in production. No approval to date from landowner. Separate report will be submitted to committee requesting commencement with Slaidburn scheme. |
| End Dec 2005 | Specification in progress for Slaidburn conveniences. Realistically no expenditure on construction work will take place in 2005/06. |
| End March 2006 | Contracts have now been tendered for. Tenders have been returned. Contract in process of being let. Work should commence on site by end of March. |
| End Sept 2006 | Work complete July 06 possible anticipated expenditure possible underspend by approx £500 |
| End Dec 2006 | Scheme complete. Retention outstanding £2,533.85 |
| End September 2007 | Scheme complete. Retention issued. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PCWHA |
| Name of Scheme | FUNDING TOWARDS RECONSTRUCTION OF WHALLEY TOILETS |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Rebuilding of Whalley toilets in conjunction with Whalley Parish Council |
| Benefits of Scheme | Improvement of facilities for customers DDA compliance |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | No indication of any issues but scheme is being undertaken by Parish Council so scheme not under direct control of Local Authority Anticipated scheme will be delayed until 2008/09 |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | PCWHA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £50,000 |  |
| Summary | Expected Total Cost of Scheme: | £50,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 50,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 50,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Initial plans drawn up by architects acting for Parish Council, requirements of RVBC have been incorporated into design |
| End September 2007 | Architect producing tender documents on behalf of Whalley Parish Council |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PESSU |
| Name of Scheme | REPLACE SUZUKI CAN PJ02 NNA |
| Officer Responsible | JAMES RUSSELL |
| Description of Scheme | Replace Suzuki 1.3 Carry (PJ02 NNA) with Fiat Diablo 1.3D white panel van |
| Benefits of Scheme | Assist in making peoples lives safer and healthier – reduce emissions, improved economy and improved safety for operative |
| Project Timetable | Start Date | April 2007 |
|  | Completion Date | Sept 2007 |
|  | Any Other Key Dates | Description of Work |
|  | April 2007 | Purchase vehicle April 2007. Modify internal layout partitions September 2007. |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Needed to provide additional electric extract fan to rear compartment |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Reduced fuel usage and vehicle maintenance |

|  |  |  |  |  |  | Cost Centre | PESSU |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £10,000 |  |
| Summary | Expected Total Cost of Scheme: | £10,107 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  | 10,107 |
|  | Cost of Work |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 10,107 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End September 2007 | Vehicle purchased and modified as required. Fitted partitions, wash basin and extractor fans. Awaiting final invoice for extractor. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PLAYH |
| Name of Scheme | IMPROVEMENTS TO CHILDREN’S PLAY AREAS |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replacement of worn out equipment and general improvements |
| Benefits of Scheme | Quality play areas for children |
| Project Timetable | Start Date | April 2007 |
|  | Completion Date | March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | PLAYH |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £50,000 |  |
| Summary | Expected Total Cost of Scheme: | £50,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 50,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 50,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | With increase in budget reactive maintenance to children’s play areas can now begin again as well as continuation with replacement and improvement programme |
| End September 2007 | £15k set aside for maintenance due to no revenue budget for such work and £35k for new/replacement equipment. Agreed scheme with Whalley Play Area Group regarding Proctors Field play area for which £5k of capital budget will be used. £17.5k spent on safety surfacing at Highmoor Park Clitheroe. Quote awaited for all necessary maintenance work following insurance company setting out defects on all play areas. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | POENE |
| Name of Scheme | ENERGY EFFICIENCY MEASURES TO RIBBLESDALE POOL |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Numerous measure to be undertaken at Ribblesdale Pool to improve energy efficiency |
| Benefits of Scheme | Improved energy efficiency, lower carbon footprint |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Feasibility of wind turbine |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Reduced running costs |

|  |  |  |  |  |  | Cost Centre | POENE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £104,500 |  |
| Summary | Expected Total Cost of Scheme: | £104,500 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 104,500 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 104,500 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Limited progress due to sickness absence of Principle Building Surveyor |
| End September 2007 | Planning permission obtained for wind turbine. However feasibility study being carried out on average wind speed for site. Currently indicating that wind turbine is not feasible. Due to shortfall of boiler replacement scheme (PBOIL) intention is to utilise this scheme to supplement boiler replacement. Funding currently being sought for contribution towards solar hot water panels. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | POSTW |
| Name of Scheme | REPLACE STEEL WINDOWS TO BUILDING AT RIBBLESDALE POOL |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Replace old and inefficient steel framed windows at Ribblesdale Pool |
| Benefits of Scheme | Improve look of building and contribute to lower maintenance better energy efficiency |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | POSTW |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £36,400 |  |
| Summary | Expected Total Cost of Scheme: | £36,400 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 36,400 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 36,400 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Quotes to be obtained by end of May 2007 |
| End September 2007 | Specification clarified. Quotes to be received by 19 October 2007. Work to be carried out during boiler replacement closedown. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RCOLT |
| Name of Scheme | REPLACE N313 SWK REFUSE COLLECTION VEHICLE |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | To replace a vehicle on expiry of its lease |
| Benefits of Scheme | To have a vehicle fleet fit for purpose |
| Project Timetable | Start Date | 1 April 2006 |
|  | Completion Date | 29 October 2006 |
|  | Any Other Key Dates | Description of Work |
|  |  | Lease ends 29 October 2006 |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Manufacture and delivery period depending on type and style of vehicle chosen |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Costs included our existing budgets |

|  |  |  |  |  |  | Cost Centre | RCOLT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £180,000 |  |
|  | Less saving : | -£4,200 |  |
| Summary | Expected Total Cost of Scheme: | £175,800 |  |
|  | Approved by Committee: | Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: | 755 |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Vehicle |  |  |  |  | 175,800 |
|  | Retention (show separately) |  |  |  | 0 |
|  | Other Costs |  |  |  |  | 0 |
|  | External Fees |  |  |  |  | 0 |
|  | Internal Salaries |  |  |  |  | 0 |
|  | TOTAL |  |  |  |  | 175,800 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | A decision has yet to be taken on the type and style of vehicle(s) to be purchased. The work being undertaken in respect of re-designing the collection service will influence the decision on the vehicle(s) bought. |
| End Sept 2006 | The delay in purchasing a new refuse collection vehicle is because decisions have yet to be made about how and when to extend the three-stream refuse collection and recycling service. The type of vehicle will depend on the style of service finally adopted following the evaluation of the trial operation. N313 SWK is to be purchased from lease company to be used as a spare vehicle. |
| End September 2007 | Replacement vehicle ordered following tendering exercise using YPO framework contract. Delivery due February 2008. Cost for all 3 vehicles in programme expected to be under budget by £4,200 as reported to community committee |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | REBIN |
| Name of Scheme | RESIDUAL WASTE BINS – THREE STREAM WASTE COLLECTION |
| Officer Responsible | PETER McGEORGE |
| Description of Scheme | The provision of 140 litre wheeled bins for three stream collection to be introduced borough wide in 2 phases 2007/08 and 2008/09 |
| Benefits of Scheme | The provision of wheeled bins will complete investment for three stream collection borough wide and improve recycling performance |
| Project Timetable | Start Date | Phase 1 completed March 2006 Phase 2 should be completed by Sept 07 Phase 3 should be completed in 2008 |
|  | Completion Date | 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Public participation. Change to cost sharing arrangement. Downturn in market value/price. Production schedules for both vehicles and wheeled bins |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose What are the revenue implications of the scheme? | For Phase 2 will need an additional split bodied vehicle (incl. in Capital Programme £190,000) For Phase 3 will need extra crew (driver + 2 operatives) Recycling credits Phase 2 1,352 x £42.87 = £57,960.24 Phase 3 2,704 x £44.16 = £119,408.64 |

|  |  |  |  |  |  | Cost Centre | REBIN |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved Budget for Current Year: | £408,500 |  |
| Financial | Expected Total Cost of Scheme: | £815,100 |  |
| Summary | Approved by Committee: | Policy & Finance |
|  | Date: | 24 January 2006 |
|  | Minute Ref: |  |
| Expenditure Analysis |  | Actual Expenditure 2005/06 £ | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |
|  | Other Costs | 80,500 | 0 | 408,500 | 326,100 | 815,100 |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL | 80,500 | 0 | 408,500 | 326,100 | 815,100 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | Bins due to be delivered to households this week. |
| End Sept 2006 | Expenditure completed in 2005/06 with purchase of wheeled bins and introduction of new three-stream collection system to target round. Target round still being evaluated. Delay in development of Waste Transfer facility has affected programme for expansion of wheeled bin delivery. It is now proposed to commence expansion Mid 2007 therefore 2006/07 Budget needs to be included in 2007/08 expenditure. |
| End March 2007 | In January 2007 Community Committee decided to extend the three-stream collection borough wide in two phases. (Phase 2 and 3). Phase 2 to commence as soon as possible and Phase 3 in 2008 we are currently preparing tenders for bins and vehicles. |
| End September 2007 | Community Committee opted to include chips in wheeled bins. Full assessment of properties identified over 97% suitable for wheeled bins. Bins ordered for Phase 2 and 3. Delivery Phase 2 – 1 October 2007 and retrofitting existing bins in November 2007. Total cost £90,100 over budget as reported to September Community Committee. Cost £734,595, Budget £644,500. An extra £90,100 has been added to the 5year Capital Programme in 2008/09. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RIBCA |
| Name of Scheme | REFURBISHMENT OF RIBCHESTER PUBLIC CONVENIENCES |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Full refurbishment to include re-roofing of existing public conveniences at Ribchester |
| Benefits of Scheme | Provision of anti-vandal fittings |
| Project Timetable | Start Date | October 2006 |
|  | Completion Date | January 2006 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | As existing |

|  |  |  |  |  |  | Cost Centre | RIBCA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £37,200 |  |
| Summary | Expected Total Cost of Scheme: | £38,400 |  |
|  | Approved by Committee: | Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: | 755 |
| Expenditure Analysis |  |  |  | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 33,405 | 0 | 33,405 |
|  | Retention (show separately) |  |  | 2,303 | 2,303 |
|  | Other Costs |  |  | 697 | 1,250 | 1,947 |
|  | External Fees |  |  |  |  | 0 |
|  | Internal Salaries |  |  | 605 | 125 | 730 |
|  | TOTAL |  |  | 34,707 | 3,678 | 38,385 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | Design stage to commence May 2006. |
| End Sept 2006 | Scheme tenders received September 2006 work to commence Mid October/early November – completion January 2007 |
| End Dec 2006 | Work on site completion due 19 January 2007, scheme appears to be on budget at present time no savings anticipated. |
| End September 2007 | Scheme complete. Retention due January 2008. Scheme overspend - extra works required to pedestrian bollards. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RLIFT |
| Name of Scheme | BIN LIFTS FOR TWO EXISTING VEHICLES |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | To purchase fit bin lifts for wheelie bin collection |
| Benefits of Scheme | To support the introduction of three stream refuse collection |
| Project Timetable | Start Date | April 2006 |
|  | Completion Date | October 2006 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | The decision on when to extend the introduction of wheelie bins to other parts of the borough will influence when the bin lifts are purchased |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | The addition of bin lifts to refuse collection vehicles increases fuel consumption and reduces the carrying capacity of the vehicle, which has an effect on running costs |

|  |  |  |  |  |  | Cost Centre | RLIFT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £30,900 |  |
|  | Additonal Approval: | £4,300 |  |
| Summary | Expected Total Cost of Scheme: | £35,200 |  |
|  | Approved by Committee: | Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: | 755 |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 35,200 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 35,200 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Decision on the extension of Three Stream Waste Collection was not made until January 2007 which has delayed the purchase of new bin lifts. Carry forward to 2007/08 Capital Programme and incorporate in purchase of new/replacement refuse collection vehicles. |
| End September 2007 | Only one bin can be provided with the money available. Order placed for fitting with work to be completed in early November 2007. Cost increased by £4,300 – reported to community committee in Sept 07 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | ROSEG |
| Name of Scheme | ROSE GARDEN CASTLE GROUNDS |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | To refurbish the old rose garden in the Castle Grounds. |
| Benefits of Scheme | Aesthetics and environmental improvements in Castle area. |
| Project Timetable | Start Date | Autumn 05 |
|  | Completion Date | March 07 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? |  |
| Funding | Total cost of scheme (over 2 years) 92,000 To be funded: LCC Grant -31,000 Market Towns Initiative Grant -28,000 Art Development Revenue Budget -5,000 Balance to be identified 28,000 |

|  |  |  |  |  |  | Cost Centre | ROSEG |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £0 |  |
| Summary | Expected Total Cost of Scheme: | £86,185 |  |
|  | Approved by Committee: |  |
|  | Date: |  |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  | Actual Expenditure 2005/06 £ | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Cost £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  | 32,692 | 46,426 | 1,503 | 80,621 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  | 3,188 | 2,376 |  | 5,564 |
|  | TOTAL |  | 35,880 | 48,802 | 1,503 | 86,185 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End Sept 06 | Scheme complete apart from installation of Public Art pieces |
| End Dec 06 | Scheme complete except awaiting installation of one public art piece. Final payments be made before end of financial year. |
| End September 2007 | Scheme complete. Actual total expenditure £86,185. Total funding actually received £64,080 Shortfall £22,105 as reported to committee in Sept 07 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWCOM |
| Name of Scheme | SMALL COMPRESSOR INGERSOLL RAND |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replacement of old equipment |
| Benefits of Scheme | Improved reliability, less breakdowns |
| Project Timetable | Start Date | May 2007 |
|  | Completion Date | October 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | RWCOM |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £5,100 |  |
| Summary | Expected Total Cost of Scheme: | £5,100 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 5,100 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 5,100 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Lease ran out in December 2004 and was subsequently purchased. A replacement will be sourced later this year. |
| End September 2007 | Order placed for purchase and installation. Work to be completed by early Novemenber 07. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWDHM |
| Name of Scheme | REPLACE PO51 DHM IVECO DAILY WITH ROLL ON ROLL OFF 6 TONNE PICK UP |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replace with vehicle better suited to needs |
| Benefits of Scheme | Greater flexibility of use than existing vehicle |
| Project Timetable | Start Date |  |
|  | Completion Date | May 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Delivery from supplier |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | RWDHM |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £47,900 |  |
| Summary | Expected Total Cost of Scheme: | £47,900 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Actual Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 34,764 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 34,764 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | At tender stage |
| End September 2007 | Vehicle replaced and now in use. Complete |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWJFV |
| Name of Scheme | REPLACE LANDROVER J438 JFV |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replace old vehicle |
| Benefits of Scheme | Improved efficiency and flexibility of use |
| Project Timetable | Start Date |  |
|  | Completion Date | April 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Delivery from supplier |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | RWJFV |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £15,000 |  |
| Summary | Expected Total Cost of Scheme: | £15,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Actual Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 14,643 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 14,643 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Tenders received and order placed for delivery early April – Ford Ranger 4x4 |
| End September 2007 | Vehicle replaced with Ford Ranger Super Cap 4x4 and in use. Complete. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWLIF |
| Name of Scheme | VEHICLE LIFTING EQUIPMENT |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Purchase of equipment to lift refuse collection vehicles |
| Benefits of Scheme | In order to be able to lift RCV’s in workshop and therefore no need to outsource work |
| Project Timetable | Start Date | May 2007 |
|  | Completion Date | November 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | No |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | RWLIF |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £13,000 |  |
| Summary | Expected Total Cost of Scheme: | £13,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Actual Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 13,370 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 13,370 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Existing equipment in workshop is unable to lift the larger RCV’s off the ground so new lifting equipment is required. |
| End September 2007 | Equipment purchased , old lift removed, new one in use. Complete. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWLWD |
| Name of Scheme | REPLACE HAYTER TRIPLE MOWER LT322 2WD |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | REPLACEMENT OF OLD EQUIPMENT |
| Benefits of Scheme | IMPROVED STANDARDS AND EFFICIENCY |
| Project Timetable | Start Date |  |
|  | Completion Date | 2 April 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Delivery period from supplier |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | RWLWD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £25,700 |  |
| Summary | Expected Total Cost of Scheme: | £25,700 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Actual Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 24,980 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 24,980 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Tenders received and order placed for delivery during week commencing 2 April 2007 |
| End September 2007 | Replaced with Hayter LT324 Triple mover and in use. Complete. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWOCK |
| Name of Scheme | REPLACE G516 OCK WITH LANDROVER AND TRAILER |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replacement of old equipment |
| Benefits of Scheme | Improved standards and efficiency |
| Project Timetable | Start Date |  |
|  | Completion Date | 2 April 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Delivery period from supplier |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | RWOCK |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £18,500 |  |
| Summary | Expected Total Cost of Scheme: | £18,500 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Actual Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 18,448 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 18,448 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Tenders received and order placed for delivery during week commencing 2 April 2007 – Ford Ranger 4x4 - complete |
| End September 2007 | Complete. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWSFR |
| Name of Scheme | REPLACE R563 SFR JOHN DEERE RIDE ON MOWER |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replacement of old equipment |
| Benefits of Scheme | Improved standards and efficiency |
| Project Timetable | Start Date |  |
|  | Completion Date | 2 April 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Delivery period from supplier |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | RWSFR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £14,900 |  |
| Summary | Expected Total Cost of Scheme: | £14,900 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Actual Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 15,193 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 15,193 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Tenders received and order placed for delivery during week commencing 2 April 2007 - complete |
| September 2007 | Complete. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWTSW |
| Name of Scheme | NEW VEHICLE THREE STREAM WASTE COLLECTION |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Purchase of new vehicle for extension of Three Stream Waste Collection |
| Benefits of Scheme |  |
| Project Timetable | Start Date | April 2007 |
|  | Completion Date | November 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Minimum 26 week delivery period. RVBC Contract Procedure means tendering timescale is significant and will affect introduction of new service. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Additional revenue costs included in budget |

|  |  |  |  |  |  | Cost Centre | RWTSW |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £190,000 |  |
|  | Less reported to committee: | -£14,200 |  |
| Summary | Expected Total Cost of Scheme: | £175,800 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 175,800 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 175,800 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | An extra collection round is required so as to introduce the new Three Stream Collection and recycling service. Contract Procedure rules and delivery period will determine when new service can be brought in which is likely to be October/November 2007 |
| End September 2007 | New split bodied refuse collection and recycling vehicle ordered through YPO framework contract and due for delivery early February 2008. Expected cost £175,800 as reported to community committee Sept 07. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWWHP |
| Name of Scheme | REPLACE W697 WHP DENNIC REFUSE COLLECTION VEHICLE |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replace old vehicle |
| Benefits of Scheme | To support Three Stream Waste Collection and recycling service |
| Project Timetable | Start Date | April 2007 |
|  | Completion Date | November 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Min 26 week delivery period from placing order Contract Procedure is lengthy process |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Included in 2007/08 Revenue Budget |

|  |  |  |  |  |  | Cost Centre | RWWHP |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £180,000 |  |
|  | Less saving : | -£4,200 |  |
| Summary | Expected Total Cost of Scheme: | £175,800 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 175,800 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 175,800 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Decision yet to be taken on precise type of vehicle to be purchased to support Three Stream refuse collection and recycling service |
| End September 2007 | New split bodied refuse collection and recycling vehicle ordered through YPO framework contract and due for delivery early February 2008. Expected cost £175,800 as reported to community committee Sept 07. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | SYNCA |
| Name of Scheme | LONGRIDGE SPORTS CENTRE – REPLACE CARPET ON SYNTHETIC PITCH |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Contribution to Lancashire County Council (joint use) to replacement of defective playing surface |
| Benefits of Scheme | Health and safety |
| Project Timetable | Start Date | Summer 2006 (grant dependable LCC) Summer 2007 if no grant |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Scheme is joint use and 50% : 50% funded between school and RVBC. May be delayed until summer 2007 if grant from LCC not available to school. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes. LCC will manage scheme. |
| What are the revenue implications of the scheme? | Future maintenance as pitch wears as existing. |

|  |  |  |  |  |  | Cost Centre | SYNCA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £133,900 |  |
| Summary | Expected Total Cost of Scheme: | £133,900 |  |
|  | Approved by Committee: | Council |
|  | Date: | 28 February 2007 |
|  | Minute Ref: | 755 |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 133,900 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 133,900 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | See problems. |
| End Sept 2006 | As previous awaiting LCC commitment to scheme – expenditure unlikely 07 |
| End Dec 2006 | As end September 2006 |
| End March 2007 | Progress as above scheme budget moved to 2007/08 |
| End September 2007 | As above |

# Text boxes

INFORMATION

Community Committee Capital Programme 2007/08

### ANNEX 1

### ANNEX 2