RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO HOUSING COMMITTEE

Agenda Item No

meeting date: 	3 DECEMBER 2007

title:	CAPITAL MONITORING 2007/08

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

- PURPOSE

  - To update members with progress on the Capital Programme for this committee for the current financial year.

- BACKGROUND

  - The Capital Programme for 2007/08 was approved in February 2007.  In the March cycle of committee meetings capital reports were considered which included capital evaluation statements giving full details of all new schemes for the forthcoming year.

- PROGRESS TO DATE

  - The table below shows a financial summary of the progress on the capital programme.

| Budget Analysis | Expenditure Analysis |
| --- | --- |
| Original | Slippage | Additional | Total | Total |
| Estimate |  | Approvals | Approved | Expenditure |
| 2007/08 |  |  | Budget | To Date |
| £ | £ | £ | £ | £ |
| 1,201,800 | -28,200 | 0 | 1,173,600 | 448,752 |

  - Annex 1 shows the full programme by scheme.

- CAPITAL EVALUATION STATEMENTS

  - As most members will be aware, the individual officers responsible for schemes in the capital programme complete an evaluation sheet prior to the start of the scheme.  Statements are then updated to show progress/any changes and reported to committee ideally on a quarterly basis.

  - The statements are attached at Annex 2 (YELLOW) and have been updated by the individual officers to show ‘Progress to End of September 2007’.

5	CONCLUSION

  - The main repairs and improvements contract is currently on schedule to complete prior to the end of March 2008 in time for the proposed stock transfer.

  - As stated on the attached evaluation sheets, the disabled facilities grant and landlord/tenant grant schemes are already fully committed with applications being received for the 2008/09 financial year.

  - The Equity Release Loan scheme however, whilst receiving a lot of interest, is lengthy and complex to apply for and is therefore experiencing a slow take up.  It is not expected this budget will be spent before the end of the financial year.

- RECOMMENDED THAT COMMITTEE

  - Review the capital evaluation sheets to consider the progress made and any comments members may wish to make.

FINANCIAL SERVICES MANAGER

H11-07/JP/AC

23 NOVEMBER 2007

|  |  | Budget Analysis | Expenditure Analysis |
| --- | --- | --- | --- |
| Schemes | budget holder | Original | Slippage | Additional | Total | Total |
|  |  | Estimate |  | Approvals | Approved | Expenditure |
|  |  | 2007/08 |  |  | Budget | To Date |
|  |  | £ | £ | £ | £ | £ |
| Housing Committee |  |  |  |  |  |  |
| Housing General Fund Schemes |  |  |  |  |  |  |
| Improvements to Longridge Homeless Facility | cg |  | 10,700 |  | 10,700 | 10,000 |
| Improvement Grants: |  |  |  |  |  |  |
| Landlord/Tenant Grants | cg | 100,000 | 13,100 |  | 113,100 | 37,806 |
| Equity Release Loans | cg | 138,000 |  |  | 138,000 | 3,741 |
| Disabled Facilities Grants | cg | 120,000 |  |  | 120,000 | 25,965 |
| Total Housing General Fund |  | 358,000 | 23,800 | 0 | 381,800 | 77,512 |
| Housing Revenue Schemes |  |  |  |  |  |  |
| Council House Improvements 2007/08 | rp | 843,800 | -52,000 |  | 791,800 | 371,240 |
| Total Housing Revenue Schemes |  | 843,800 | -52,000 | 0 | 791,800 | 371,240 |
| Total Housing Committee |  | 1,201,800 | -28,200 | 0 | 1,173,600 | 448,752 |

##### ANNEX 2

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | LHOME |
| Name of Scheme | IMPROVEMENTS/REVIEW OF LONGRIDGE HOMELESS FACILITY |
| Officer Responsible | CHRISTINE GRIMSHAW |
| Description of Scheme | Refurbishment of hostel to provide energy efficient heating system and insulation |
| Benefits of Scheme | Energy efficient system |
| Project Timetable | Start Date | Not yet determined |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None currently |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | In addition to the £50,000 in the general fund capital programme there will also be a contribution from the HRA as three of the flats are used for general let. |

|  |  |  |  |  |  | Cost Centre | LHOME |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Summary | Approved Budget for Current Year: | £10,700 |  |
|  | Expected Total Cost of Scheme: | £20,014 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 9,314 | 10,700 | 20,014 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  | 9,314 | 10,700 | 20,014 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | Before a decision is taken to spend this money an option appraisal will be undertaken to see whether Beacon Villas is the most appropriate accommodation for a homeless service. This option appraisal will consider the open market value that can be obtained for Beacon Villas, alternative locations for the homeless unit and the timescales involved in relocation. A report will be taken to housing Committee in May/June 2006. |
| End Sept 2006 | In year bid made to the Housing Corporation in partnership with Adactus HA. If successful will result in substantial capital receipt to authority together with refurbishment of the building. Flats will continue to be rented at social rent levels and Ribble Valley will lease back required no of units for homeless service. Update meeting with Housing Association arrange for 10/10/06. |
| End Dec 2006 | Sale anticipated to be finalised by end of February 2007. Part of the budget will be utilised to set up a new homeless facility in Longridge. Savings on this scheme will be used to support the improvements grant budgets. |
| End September 2007 | Property sold Feb 2007 to Adactus Housing Association. Conversion underway from 7 bedsits and flats to 2 x 1 bed; 2 x 2 bed; & 1 x 3 bed unit due for completion November 2007. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | LANGR |
| Name of Scheme | LANDLORD/TENANTS GRANTS |
| Officer Responsible | CHRISTINE GRIMSHAW |
| Description of Scheme | Payments of up to 50% of the cost of works to landlords to bring properties back into use. |
| Benefits of Scheme | Reduces empty properties, makes best use of housing stock, nomination arrangements reduced rents. |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | LANGR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £100,000 |  |
| Summary | Expected Total Cost of Scheme: | £100,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 100,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 100,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Sufficient applications at the current time to spend the budget. |
| End September 2007 | Applications approved to budget limit for completion by March 2008. Applicants already on waiting list for 2008/09 no problems anticipated with spend. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | EQUIT |
| Name of Scheme | EQUITY RELEASE LOANS |
| Officer Responsible | CHRISTINE GRIMSHAW |
| Description of Scheme | Housing Committee agreed to switch from grants to loans in respect of minor works and renovation grants. |
| Benefits of Scheme | Scheme brings properties in the Private Sector up to Decent Homes Standard. Equity loans are repayable so recycling of monies. |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | As this scheme is a new venture for the council unsure as to take up however, early indications are that there is interest in the product. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes. Joint arrangement between identified Ribble Valley officers and Regenda group who offer product. |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | EQUIT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £138,000 |  |
| Summary | Expected Total Cost of Scheme: | £138,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 138,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 138,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | No concerns at present scheme will be ready to run from 1 April 2007 |
| End September 2007 | Minimal expenditure to date, equity release product attracting a lot of interest but lengthy and complex procedure to achieve approval. Anticipated approvals to budget limit by March 2008 but unlikely to spend allocation. Permission granted at Housing Committee in September 2007 to use budget flexibly to assist commitments in respect of Disabled Facilities Grants. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | DISCP |
| Name of Scheme | DISABLED FACILITIES GRANTS |
| Officer Responsible | CHRISTINE GRIMSHAW |
| Description of Scheme | Grants to enable clients to remain in their own homes following adaptation |
| Benefits of Scheme | Reduced requirement for residential places improved quality of life for clients |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Potential difficulty with insufficient budget, enough current recommendations to spend budget request made to GONW for additional funding |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | DISCP |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £120,000 |  |
| Summary | Expected Total Cost of Scheme: | £120,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 120,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 120,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Scheme will commence on time no difficulties anticipated with delivery see comments re: budget on front sheet |
| End September 2007 | Request for additional funding denied. Budget currently over committed and waiting list already lengthy with six months of financial year remaining. Permission granted to use potential underspend on equity release scheme. Request for increased funding made for 2008/09. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | IMPCN |
| Name of Scheme | COUNCIL HOUSE IMPROVMENTS 2007/08 |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Planned works to Council Houses |
| Benefits of Scheme | Enables us to work towards meeting the Decent Homes Standard |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Delay in start on site due to requirement of Accounts and Audit Committee for works to be tendered. Also extended sick leave of Principle Building Surveyor will have impact |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | IMPCN |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £843,500 |  |
|  | Less slippage from previous year: | -£52,000 |  |
| Summary | Expected Total Cost of Scheme: | £791,800 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 731,015 |
|  | Retention (show separately) |  |  |  | 13,500 |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  | 12,285 |
|  | Internal Salaries |  |  |  |  | 35,000 |
|  | TOTAL |  |  |  |  | 791,800 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | A limited amount of work has been undertaken so far in preparation of this scheme. Will need to be made high priority as due to potential transfer of stock to a Registered Social Landlord by 31 March 2008 essential work programme is completed within financial year. Also essential that work undertaken concentrates on Decent Home Standard issues in case tenants vote against transfer |
| End September 2007 | External redecoration near completion. Kitchen contracts on site. Currently on programme for completion date. |

# Text boxes

INFORMATION