PROGRAMME OF KEY TASKS FOR 3 STREAM WASTE COLLECTION SERVICE

| DATE | DAY | ACTION |
| --- | --- | --- |
| 30 JUNE | MONDAY | Start of collections on Phase II. |
| 20 JUNE | FRIDAY | Last day for delivery of wheeled bins and information leaflets to properties on Phase II |
| 9 JUNE | MONDAY | Finalise press release for CA&T on 19/26 May, Longridge News on 20/27 May, Lancashire Telegraph week commencing 26 May. |
| 27 MAY | TUESDAY | Delivery of wheeled bins to properties on Phase II to start today (including leaflets) – allows 4 weeks delivery period. |
| 23 MAY | FRIDAY | Last day by which letters to properties on Phase II are to be received by residents advising of new arrangements and delivery of bins. Last day by which new information leaflets are to be supplied to RVBC from printers ready to be handed to Titan. |
| 6 MAY | TUESDAY | Start distribution of letters to properties in Phase II advising of new arrangements and delivery of wheeled bins – allows 3 week delivery period. |
| 2 MAY | FRIDAY | Last day by which Titan require full address list for Chipping and delivery of wheeled bins. |
| 1 MAY | THURSDAY | Final amendments to leaflets and calendars and send to printer for production. |
| 30 APRIL | WEDNESDAY | Return of second proofs from printer re leaflets and calendars. |
| 21 APRIL | MONDAY | Last date for letter data to PMM. |
| 18 APRIL | FRIDAY | Return of first proofs for leaflets and calendars from printers. |
| 15 APRIL | TUESDAY | Start sorting data for plans for collection points. Start production of delivery point plans and letters. Last day for numbers of bins to Titan. |
| 14 APRIL | MONDAY | Results from Entec. |
| 11 APRIL | FRIDAY | Send details to printer re leaflets and calendars. |
| 7 APRIL | MONDAY | Data to Entec for re-evaluation. Start draft of letters (Consult with Councillors). |
| 4 APRIL | FRIDAY | Final results of Councillor consultation to feed into database. |
| DATE | DAY | ACTION |
| 28 MARCH | FRIDAY | End of period of consultation with Councillors re Phase II. |
| 24 MARCH | MONDAY | GMJ on leave all week. |
| 14 MARCH | FRIDAY | Confirm delivery dates with Titan. |
| 11 MARCH | TUESDAY | Meeting of Community Committee – progress report. |
| 10 MARCH | MONDAY | PMcG on leave all week. |
| 5 MARCH | WEDNESDAY | Meeting of Leader, Chairman of Community Committee, Chief Executive, Director of Community Services and Street Scene Manager to discuss problem sites that remain unresolved from Phase I. |
| 3 MARCH | MONDAY | Start of Councillor consultation period regarding proposals for Phase II. Completion of Phase I issues analysis ready for report to Community Committee. |
| 25 FEBRUARY | MONDAY | BK starts 2 weeks leave. |
| 18 FEBRUARY | MONDAY | Start of collection point re-evaluation process for Phase II including map analysis and site visits. PMcG on leave all week. |
| 28 JANUARY | MONDAY | Start review of Phase I issues and preparation of detailed list of locations where interim collection arrangements continue to be provided. |
| 15 JANUARY | TUESDAY | Meeting of Community Committee – decisions taken regarding criteria for larger bins for residual waste and to continue to provide interim arrangements to some properties in rural areas of Phase I. |