RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO POLICY AND FINANCE COMMITTEE

Agenda Item No

meeting date: 	21 NOVEMBER 2006

title:	TIMETABLE FOR BUDGET SETTING

submitted by: 	FINANCIAL SERVICES MANAGER

principal author: 	JANE PEARSON

1	PURPOSE

1.1	To agreed the attached timetable.

2	BACKGROUND

2.1	Part of our Corporate Governance arrangements is to set out clearly to both officers and members the Council’s budget timetable.

3	BUDGET TIMETABLE

3.1	Attached at Annex 1 is a comprehensive timetable covering the main elements of the Council’s budget setting progress together with key dates and responsibilities.

The timetable has been circulated to Service Managers and the Corporate Management Team.

4	RECOMMENDED THAT COMMITTEE

  - Approve the budget timetable.

FINANCIAL SERVICES MANAGER

PF46-06/JP/AC

|  | Budget Timetable 2007/08 |  |  |
| --- | --- | --- | --- |
|  | Task | Who? | When? |
| 1 | Consideration of Draft Medium Term Financial Strategy | Policy & Finance Committee/BWG | 26-Sep-06 |
| 2 | Send out % time allocation sheets to service managers for purpose of calculating departmental recharges | Accountants | 09-Oct-06 |
| 3 | Send out new Capital Scheme Pro Formas for completion by Service Managers | Financial Services Manager | 19-Oct-06 |
| 4 | Completion of Recharge time allocation sheets | Service Managers/individual members of staff | 23-Oct-06 |
| 5 | Calculation of Taxbase for council tax setting purposes for 2007/08 | FSM/ Revenues Manager | 31-Oct-06 |
| 6 | Send out Precept Letters to Parish Councils | Accounting Technician | 03-Nov-06 |
| 7 | Finalise Revised Capital Programme for 2006/07 | FSM/Capital Working Group | mid November 2006 |
| 8 | Calculate Capital Charges | Accountant - TH | mid November 2006 |
| 9 | Provision of Budget information for Service Plans | Accountants | Oct/Nov 2006 |
| 10 | Identification of Growth Items/Gershon Efficiency Savings | Service Managers | Nov-06 |
| 11 | Review of Fees and Charges | Service Managers/Accountants | Nov-06 |
| 12 | Agreement of Service Plans | Committees | Nov-06 |
| 13 | Final Calculations of Recharges | Accountants | 30-Nov-06 |
| 14 | Announcement of Provisional Settlement information from DCLG | DCLG | mid to late November 2006 |
| 15 | Assess Implications of Settlement for RVBC | DOR/FSM |  |
| 16 | DOR to agree taxbase with Chairman & Shadow Chairman of Policy and Finance Committee | DOR | early Dec 2006 |
| 17 | Notification of Supported Borrowing Allocation | DCLG | Dec-06 |
| 18 | CMT to meet to discuss Service Plans with Service Managers | CMT | Dec-06 |
| 19 | Inform Members of Implications for RVBC of Settlement | DOR/FSM | early December 2006 |
| 20 | CMT to consider latest budgetary position | CMT | 13-Dec-06 |
| 21 | BWG to meet to consider latest indications of 2007/08 budget | BWG | mid December |
| 22 | Calculate Collection Fund Surplus/Deficit and apportion between Precepting Authorities | FSM | mid December |
| 23 | Finalisation of Draft Budget Reports | Accountants | 21-Dec-06 |
| 24 | Deadline for receipt of parish precept letters | Accounting Technician | 02-Jan-07 |
| 25 | Notify Lancashire County Council, Police and Fire Authorities of Collection Fund Surplus/Deficit and Taxbase | FSM | mid January 2007 |
| 26 | Consideration of Budget Reports by Committees | Service Committees | 16 January 2006 to 30 January 2006 |
| 27 | Meetings of Budget Working Group to consider budgetary recommendations to give Special Policy & Finance Cttee | BWG | mid to late January 2007 |
| 28 | Settlement Debate in Parliament |  | late January, early February 2007 |
| 29 | Meeting of Special Policy and Finance Committee to approve budget and recommend Council Tax to Full Council | DOR/FSM | 13-Feb-07 |
| 30 | Provision of Financial Information for Council Tax Leaflet | FSM to Revenues Manager | mid February 2007 |
| 31 | Set up meeting with Industrialists to consider budget | PA to Director of Resources | Feb-07 |
| 32 | Receipt of Precept Letters from Major Precepting Authorities | FSM | 01-Mar-07 |
| 33 | Full Council to agree Budget, set Housing Rents and set Council Tax | Members | 06-Mar-07 |
| 34 | DOR, FSM, CMT to inform Service Mangers of agreed Budget |  | 07-Mar-07 |
| 35 | Entering of Approved Budget onto Financials system | Accountants | Feb/March 07 |
| 36 | Production of Budget Book | FSM | mid March 2007 |

# Text boxes

DECISION