RIBBLE VALLEY BOROUGH COUNCIL

INFORMATION

REPORT TO POLICY AND FINANCE COMMITTEE

Agenda Item No 14

meeting date: 	20 NOVEMBER 2007

title:	CAPITAL MONITORING 2007/08

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

- PURPOSE

  - To update members with progress on the Capital Programme for this committee for the current financial year.

- BACKGROUND

  - The Capital Programme for 2007/08 was approved in February 2007.  In the March cycle of committee meetings capital reports were considered which included capital evaluation statements giving full details of all new schemes for the forthcoming year.

- PROGRESS TO DATE

  - The table below shows a financial summary of the progress on the capital programme.

| # Budget Analysis |  |  |  | Expenditure Analysis |
| --- | --- | --- | --- | --- |
| Original | Slippage | Additional | Total | Total |
| Estimate |  | Approvals | Approved | Expenditure |
| 2007/08 |  |  | Budget | To Date |
| £ | £ | £ | £ | £ |
| 87,800 | 112,320 | 795,000 | 995,120 | 36,116 |

  - Annex 1 shows the full programme by scheme.

  - You will see from the above table additional approvals of £795,000 have been brought in since the original programme was approved.  These are in respect of the following:

- Loan agreed to Ribble Valley Sports Association for the improvements at Roefield Leisure Centre £645,000.

- Loan agreed to Trinity to support the purchase of St Mary’s Art Centre £150,000.

- CAPITAL EVALUATION STATEMENTS

  - As most members will be aware the individual officers responsible for schemes in the capital programme complete an evaluation sheet prior to the start of the scheme.  Statements are then updated to show progress/any changes and reported to committee ideally on a quarterly basis.

  - The statements are attached at Annex 2 (YELLOW) and have been updated by the individual officers to show ‘Progress to End of September 2007’.

5	CONCLUSION

  - The majority of schemes in the current capital programme for this committee have been carried forward as slippage from previous years.  After reviewing the comments provided on the evaluation statements by the responsible officers it appears most of these schemes are on target for completion before the end of the financial year which is good news.

  - As far as the Roefield loan is concerned, the Sports Association have accepted the council’s loan offer including the conditions attached.  They are currently pursuing the funding from the other parties concerned.

- RECOMMENDED THAT COMMITTEE

  - Review the capital evaluation sheets to consider the progress made and any comments members may wish to make.

FINANCIAL SERVICES MANAGER

PF42-07/JP/AC

12 NOVEMBER 2007

| Policy and Finance Committee Capital Programme 2007/08 |  | Budget Analysis |  |  |  | Expenditure Analysis ### ANNEX 1 |
| --- | --- | --- | --- | --- | --- | --- |
| Schemes | budget holder | Original | Slippage | Additional | Total | Total |
|  |  | Estimate |  | Approvals | Approved | Expenditure |
|  |  | 2007/08 |  |  | Budget | To Date |
|  |  | £ | £ | £ | £ | £ |
| Civic Suite - DDA & Impts to stored water system | rp |  | 25,950 |  | 25,950 | 10,500 |
| Computer Server Room Improvements | ph |  | 11,940 |  | 11,940 | 8,615 |
| eEnabling Members | msm |  | 3,200 |  | 3,200 | 0 |
| E Government Initiative | ml |  | 53,230 |  | 53,230 | 4,712 |
| Fire safety improvements to council office ceilings | rp | 21,600 |  |  | 21,600 | 4,711 |
| Replace Risograph Printer | msm | 6,200 |  |  | 6,200 | 0 |
| Roefield Loan | ms |  |  | 645,000 | 645,000 | 0 |
| Replace Telephone system | msm |  | 8,000 |  | 8,000 | 6,860 |
| Grant & Loan to Trinity | ms | 60,000 |  | 150,000 | 210,000 | 0 |
| Upgrade of Financial Ledger System | jp |  | 10,000 |  | 10,000 | 718 |
| Total Policy & Finance Committee |  | 87,800 | 112,320 | 795,000 | 995,120 | 36,116 |

ANNEX 2

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CIVHS |
| Name of Scheme | DDA AND HEALTH AND SAFETY WORKS TO CIVIC SUITE |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | To install lift to allow access to first floor meeting rooms. Refurbish works to comply with DDA and remove Legionnaires risk from existing stored water system. Civic Suite – Lift The lift is necessary as no disabled access is available to the meeting rooms on the first floor or the public gallery. - Installing monitors within reception that transmit live pictures and sound from the council chamber have catered for access to the gallery. - The meeting rooms are however inaccessible for disabled people with walking difficulties attending meetings. This can include members of staff, members of the public, external auditors and members of the Council. - Regarding members of the Council the DDA has been amended in that members are now included within the Act and as such councils cannot discriminate against this group. ## Civic Suite – WCs - The WCs are included for inclusion as it was deemed that they are not really up to a sufficient standard (unlike offices) for the building they are held in. - The main issue however is that the WCs are served from a large water heater that stores hot water. This is defective at the moment and as such is potentially a Legionella bacteria source. The aim is to remove the heater and incorporate instantaneous water heaters therefore eliminating the Legionella risk. - During refurbishment water saving taps would be installed and an anti-slip floor covering. - The whole refurbishment would improve health and safety regarding the WCs. - The disabled WC does not comply with current best practice, building regulations and DDA regarding the equipment within it. |  |  |  |
| Benefits of Scheme | Health and safety improvements and compliance with current legislation |  |  |  |
| Project Timetable | Start Date | July 2006 |  |  |
|  | Completion Date | September 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None at this stage |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | £600 annual maintenance repairs to lift |  |  |  |

|  |  |  |  |  |  | Cost Centre | CIVHS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £25,950 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £45,005 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  | 17,342 | 25,950 | 43,292 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  | 1,713 |  | 1,713 |
|  | TOTAL |  |  |  | 19,055 | 25,950 | 45,005 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Design work to lift to be commenced/revisited. |  |  |  |  |  |
| End Sept 2006 |  | WC work complete beginning October 2006 lift prices received September 2006 final approval on design October 2006. Work to commence January 2007 completion January 2007. |  |  |  |  |  |
| End Dec 2006 |  | Retention and final account outstanding for toilet work. Lift decision still being considered. Plan to commence before end of financial year. |  |  |  |  |  |
| End September 2007 |  | Lift installation planned for January 2008. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CROOM |
| Name of Scheme | IMPROVEMENTS TO COMPUTER SERVER ROOM |  |  |  |
| Officer Responsible | PETER HOTHERSALL |  |  |  |
| Description of Scheme | Following review of IT service by external auditors a number of recommendations were made regarding the current server room. In addition our insurance company have requested similar improvements to ensure fire prevention methods are in place. |  |  |  |
| Benefits of Scheme | Will enhance and improve the efficiency and quality of services by optimising the application of information technology and continuing to invest in cost effective business solutions. |  |  |  |
| Project Timetable | Start Date | June 2006 |  |  |
|  | Completion Date | July 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | External contractors are doing the work |  |  |  |
| What are the revenue implications of the scheme? | £200 per annum service and maintenance of air conditioning unit. £200 per annum fire extinguishing system |  |  |  |

|  |  |  |  |  |  | Cost Centre | CROOM |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £11,940 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £15,200 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Expenditure £ |
|  | Fire Structural Precautionary Work |  |  |  |  |  |  |
|  | Fire Extinguishing System |  |  |  |  |  |  |
|  | Room Integrity Check |  |  |  |  |  |  |
|  | Air Sampling System |  |  |  | 3,257 | 11,940 | 15,197 |
|  | Ceiling Made Airtight |  |  |  |  |  |  |
|  | Secondary Air Conditioning Unit |  |  |  |  |  |  |
|  | TOTAL |  |  |  | 3,257 | 11,940 | 15,197 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | End of June completion |  |  |  |  |  |
| End Sept 2006 |  | The fire structural precautionary work completed. Room integrity check scheduled for December. |  |  |  |  |  |
| End Dec 2006 |  | Remainder of work scheduled for Feb 2007, to be completed by end of Feb 2007. |  |  |  |  |  |
| End September 2007 |  | Final ceiling work to be undertaken when main computer office ceiling is renewed, planned for January 2008. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | EENAB |
| Name of Scheme | E-ENABLING MEMBERS |  |  |  |
| Officer Responsible | MICHELLE SMITH/PETER HOTHERSALL |  |  |  |
| Description of Scheme | Provision of PC access/laptops |  |  |  |
| Benefits of Scheme | Enable email services for member information, eg minutes, agendas, circulars, and improve electronic communication between members and officers |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | April 2009 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Availability of in-house IT technical support, willingness of members to engage with new technology |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Probably within democratic services but issues regarding IT support. Discussions currently taking place between Michelle Smith, Peter Hothersall and Councillor Sherras to review issues. |  |  |  |
| What are the revenue implications of the scheme? |  |  |  |  |

|  |  |  |  |  |  | Cost Centre | EENAB |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £3,200 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £5,000 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  | 1,796 | 3,200 | 4,996 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  | 1,796 | 3,200 | 4,996 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Initial report on proposed method of implementation to policy and Finance Committee. |  |  |  |  |  |
| End Sept 2006 |  | - Have held 2 meetings of the e-enabling working group. - Carried out survey of IT equipment and usage amongst councillors. - Moved to electronic distribution of minutes and agendas where possible and reduce paper usage. - Explored options to improve email access for members and looking to purchase a Juniper Netscreen product at a cost of £2,659 (includes annual maintenance figure of £400) this will be confirmed when PH returns from holiday. |  |  |  |  |  |
| End Dec 2006 |  | Work commenced on developing Councillor’s portal to access committee papers on line. Brief presentation demonstrating portal and improvements to website, given at Full Council in November 2006. System currently under test after which full training/briefing session will be provided for members. Work ongoing to include appendices and attachments to electronic version of minutes and agendas. |  |  |  |  |  |
| End September 2007 |  | Member portal launched and training session for members has been delivered. Minutes and agendas now available on the website and intranet. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | EGIIV |
| Name of Scheme | E-GOVERNMENT INITIATIVE – IEG4 – PHASE 2 |  |  |  |
| Officer Responsible | MARSHAL SCOTT |  |  |  |
| Description of Scheme | To introduce electronic methods of service delivery |  |  |  |
| Benefits of Scheme | Improved access to services |  |  |  |
| Project Timetable | Start Date | April 2005 |  |  |
|  | Completion Date | March 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Shortage of staff resources. The number of computer projects to be implemented. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Will be difficult given the Government’s deadlines for priority outcomes |  |  |  |
| What are the revenue implications of the scheme? | Not yet quantified but the Government believes there will be long-term savings from this initiative |  |  |  |

|  |  |  |  |  |  | Cost Centre | EGIIV |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £53,230 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £60,003 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  | 6,773 | 53,230 | 60,003 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  | 6,773 | 53,230 | 60,003 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2005 |  | The £150,000 IEG4 grant money will be funding both the e-Government office and the East Lancashire e-Partnership (ELEP) initiatives. These initiatives consist of joint service delivery, e-Procurement, web interactions and joint e-Consultation. |  |  |  |  |  |
| End Sept 2005 |  | Continuing progress towards meeting the e-Government priority outcomes. Notified by ODPM funds need to be spent by 31 March 2006. |  |  |  |  |  |
| End Dec 2005 |  | Funds to be spent by 31 March 2006 to meet priority outcomes. Progress currently being reviewed. |  |  |  |  |  |
| End Dec 2006 |  | Evaluation of new projects currently underway. Electronic presentation improvements to Committee Room 1 costing £5,000 are underway. An E-forms package may be purchased at a cost of £7,500. May be some slippage into 2007/08. |  |  |  |  |  |
| End September 2007 |  | There is currently £40,000 remaining which is uncommitted. A review of outstanding egovernment projects will be undertaken. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | OFCEI |
| Name of Scheme | COUNCIL OFFICES – FIRE SAFETY IMPROVEMENTS TO CEILINGS |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Replacement of existing suspended ceilings |  |  |  |
| Benefits of Scheme | Improved fire and safety energy performance |  |  |  |
| Project Timetable | Start Date | July 2005 |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  |  | Strip our concealed grid ceiling and replace with exposed grid ceiling |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | OFCEI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Original Budget for year: |  |  |  |  | £21,600 |  |
|  | Slippage from 2006/07: |  |  |  |  | £ 7,000 |  |
|  | Total Budget for Year: |  |  |  |  | £28,600 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £93,230 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2005/06 £ | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  | 35,557 | 29,073 | 28,600 | 93,230 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  | 35,557 | 29,073 | 28,600 | 93,230 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2005 |  | Design works carried out. Delay due to programming on site. Works to start during holiday period to minimise disruption. Anticipate some of the budget may not be needed or may need to be moved to 2006/07, depending on progress. |  |  |  |  |  |
| End Sept 2005 |  | Work complete to several areas, including housing, level C, chief executive. Remaining ceiling due for replacing January 2006. |  |  |  |  |  |
| End Dec 2005 |  | As September 2005 |  |  |  |  |  |
| End March 2006 |  | Work to commence on staircases March 2006. Office area to Level C legal services planned for July 2006. |  |  |  |  |  |
| End Sept 2006 |  | Work delayed since July due to contractor commitments. Work planned October 2006 for Environmental Health Section followed by Legal Services. If funding allows then other items will be identified and work carried out. |  |  |  |  |  |
| End Dec 2006 |  | Work done to Environmental Health Section ceiling. Legal Section to commence February. Hope to carry out other work before end of March. Will be some slippage into 2007/08. |  |  |  |  |  |
| End March 2007 |  | Work undertaken to remainder of Level C over weekends of 3, 4 and 10, 11 March 2007. Final phase of work to Level B will be undertaken during 07/08 in June with Budget for 2007/08 |  |  |  |  |  |
| End September 2007 |  | Planned work during January 08 for level B finance office and remainder of level C. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | PRRIS |
| Name of Scheme | REPLACE RISOGRAPH PRINTER |  |  |  |
| Officer Responsible | MICHELLE SMITH |  |  |  |
| Description of Scheme | To replace the Risograph Printer in central printing department |  |  |  |
| Benefits of Scheme | Enables cost effective production of council papers and documents. High volume machines more cost effective than photocopiers. Machine currently produces one million copies per year. |  |  |  |
| Project Timetable | Start Date | April 2007 |  |  |
|  | Completion Date | April December 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | N/A |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | N/A |  |  |  |

|  |  |  |  |  |  | Cost Centre | PRRIS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £6,200 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £6,200 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 6 March 2007 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 6,200 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 6,200 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2007 |  | Currently seeking quotes for replacement from supplier |  |  |  |  |  |
| End September 2007 |  | Awaiting written quote from current supplier. May be a saving on this scheme. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RTELE |
| Name of Scheme | REPLACE TELEPHONE SYSTEM |  |  |  |
| Officer Responsible | MICHELLE SMITH |  |  |  |
| Description of Scheme | Replacement of existing system which currently has no capacity for future expansion |  |  |  |
| Benefits of Scheme | Improved telecom service for internal and external customers |  |  |  |
| Project Timetable | Start Date | March 2004 (tender) |  |  |
|  | Completion Date | Spring 2005 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  | 23 March 2004 | Final tender specification to Policy & Finance Committee then invitation to tender will be issued |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Possible IT issues when new system is selected although initial specification would prevent this |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose? | No. Have engaged consultancy services from Improcom to manage tender process and implementation programme |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

| Financial | Revised Estimate: | £8,000 |  |
| --- | --- | --- | --- |
| Summary | Slippage From 2005/06: | £16,000 |  |
|  | Approved Budget for Current Year: | £16,000 |  |
|  | Expected Total Cost of Scheme: | £50,182 |  |
|  | Approved by Committee: | Council |  |
|  | Date: | 2 March 2004 |  |
|  | Minute Ref: | 762 |  |

|  |  |  |  |  |  | Cost Centre | RTELE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Expenditure Analysis |  |  |  | Actual Expenditure 2004/05 £ | Actual Expenditure 2005/06 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  | 13,600 | 20,581 | 8,000 | 42,181 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | TOTAL |  |  | 13,600 | 20,581 | 8,000 | 42,181 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2004 |  | Tenders processed and preferred supplier chosen (Philips). Initial project plan meeting held in June. Implementation plan agreed. Next meeting 12 July 2004. Hoping to go live by middle September 2004. |  |  |  |  |  |
| End Dec 2004 |  | Payment withheld until new system available. New upgraded system installed 17 January 2005. Will anticipate releasing payment by end of January 2005 when I am happy that it is working properly. |  |  |  |  |  |
| End June 2005 |  | Regular meetings have taken place with Philips Telecommunications over the course of the last 6 months whilst the system continued to be tested. We now have an engineer on site 3 days per week to roll out the PC application to all departments during the next month or so. At the last meeting with Philips we agreed to pay 60% of the original invoice (£24,182.92). This will leave an outstanding balance of £16,121.94 plus a maintenance contract for 12 months at a cost of £2,749.50. |  |  |  |  |  |
| End Sept 2005 |  | Continue to experience problems with the telephone system in respect of stability. Philips has accepted that it is unrealistic for the Council to continue in this manner and have decided to remove the system totally and replace with a new and more stable system. Representatives from Philips will meet with CMT on 9 November to agree a way forward. Full payment for the system is still being withheld. |  |  |  |  |  |
| End Dec 2005 |  | Following meeting with Philips, agreed that current system would be replaced by a new switchboard system in January 2006 at no extra cost. Still withholding final settlement until new system is fully operational and all staff trained. |  |  |  |  |  |
| End Sept 2006 |  | New switchboard product installed but continue to experience problems. Negotiations continue with Philips and they have agreed to reduce final bill to £8k. We are still withholding payment until technical issues have been sorted; especially as new problems have arisen since contact centre online. |  |  |  |  |  |
| End Dec 2006 |  | Still testing the system and particularly the interface with the MacFarlane Call Centre Software. Discussions to resolve technical issues still ongoing. Final payment still withheld. |  |  |  |  |  |
| End September 2007 |  | Technical issues resolved and installation signed off. Final payment made. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | TRING |
| Name of Scheme | GRANT AND LOAN TO TRINITY |  |  |  |
| Officer Responsible | MARSHAL SCOTT |  |  |  |
| Description of Scheme | To support the purchase of St Mary’s Centre |  |  |  |
| Benefits of Scheme | To help support the creation of the proposed Arts Centre |  |  |  |
| Project Timetable | Start Date | Summer 2007 |  |  |
|  | Completion Date | N/A |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Dependant on Trinity progressing scheme, receiving planning permission and support from North West Development Agency/Clitheroe the Future |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Loss of interest on Capital Sum/Interest on amount borrowed |  |  |  |

|  |  |  |  |  |  | Cost Centre | TRING |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £60,000 |  |
|  | Additional approval: |  |  |  |  | £150,000 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £210,000 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 6 March 2007 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  | 210,000 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 210,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End September 2007 |  | Trinity are awaiting North West Development Agency approval for their support of the scheme. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | UPFIN |
| Name of Scheme | UPGRADE OF FINANCIAL LEDGER SYSTEM |  |  |  |
| Officer Responsible | JANE PEARSON |  |  |  |
| Description of Scheme | Upgrade financial system to include e-procurement system |  |  |  |
| Benefits of Scheme | More efficient system of ordering and better, more up-to-date, financial ledger system |  |  |  |
| Project Timetable | Start Date | October 2005 |  |  |
|  | Completion Date | June 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Limited staff resources and competing workloads |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Hopefully but may impact on other aspects of financial services work |  |  |  |
| What are the revenue implications of the scheme? | Can be met within existing revenue budget |  |  |  |

|  |  |  |  |  |  | Cost Centre | UPFIN |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Original Estimate: |  |  |  |  | £10,000 |  |
| Summary | Approved Budget: |  |  |  |  | £101,100 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £61,418 |  |
|  | Approved by Committee: |  |  |  |  |  |  |
|  | Date: |  |  |  |  |  |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2005/06 £ | Actual Expenditure 2006/07 £ | Estimated Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  | 46,479 | 4,139 | 10,800 | 61,418 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  | 46,479 | 4,139 | 10,800 | 61,418 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Sept 2005 |  | Hardware purchased and installed. Software arrived and loaded, implementation begun. |  |  |  |  |  |
| End Dec 2005 |  | Conversion of existing data underway. Software consultant on site on a regular basis. Plan to go live April 2006. |  |  |  |  |  |
| End March 06 |  | Conversion plans finalised. Plan to go live April/May 2006. Training of users underway. |  |  |  |  |  |
| End Sept 06 |  | New financials system fully working live date May 2006. all data successfully migrated from Powersolve and balanced to Financials. All interfaces written and correctly working. |  |  |  |  |  |
| End Dec 06 |  | The final figures need to be agreed with Civica however, members will recall that significant savings were likely to be made due to the joint procurement with neighbouring East Lancashire Authorities. It appears that we will save around £40k. |  |  |  |  |  |
| End September 2007 |  | New scanner purchased and installed for creditor image storage. Other residual items have been ordered and will arrive shortly. Scheme will be complete shortly. Overall saving on scheme expected to be just under £40,000. |  |  |  |  |  |

# LICY & FINANCE COMMI