RIBBLE VALLEY BOROUGH COUNCIL

INFORMATION

REPORT TO PLANNING AND DEVELOPMENT COMMITTEE

Agenda Item No

meeting date: 	27 NOVEMBER 2007

title:	CAPITAL MONITORING 2007/08

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

- PURPOSE

  - To update members with progress on the Capital Programme for this committee for the current financial year.

- BACKGROUND

  - The Capital Programme for 2007/08 was approved in February 2007.  In the March cycle of committee meetings capital reports were considered which included capital evaluation statements giving full details of all new schemes for the forthcoming year.

- PROGRESS TO DATE

  - The table below shows a financial summary of the progress on the capital programme.

| # Budget Analysis |  |  |  | Expenditure Analysis |
| --- | --- | --- | --- | --- |
| Original | Slippage | Additional | Total | Total |
| Estimate |  | Approvals | Approved | Expenditure |
| 2007/08 |  |  | Budget | To Date |
| £ | £ | £ | £ | £ |
| 22,000 | 33,820 | 0 | 55,820 | 17,461 |

  - Annex 1 shows the full programme by scheme.

- CAPITAL EVALUATION STATEMENTS

  - As most members will be aware the individual officers responsible for schemes in the capital programme complete an evaluation sheet prior to the start of the scheme.  Statements are then updated to show progress/any changes and reported to committee ideally on a quarterly basis.

  - The statements are attached at Annex 2 (YELLOW) and have been updated by the individual officers to show ‘Progress to End of September 2007’.

5	CONCLUSION

  - All three schemes for this committee have been carried forward as slippage from previous years.  After reviewing the comments provided on the evaluation statements by the responsible officers it appears these schemes are either complete or will be by the end of the financial year which is good news.

- RECOMMENDED THAT COMMITTEE

  - Review the capital evaluation sheets to consider the progress made and any comments members may wish to make.

FINANCIAL SERVICES MANAGER

PD8-07/JP/AC

19 NOVEMBER 2007

| Policy and Finance Committee Capital Programme 2007/08 |  | Budget Analysis |  |  |  | Expenditure Analysis ### ANNEX 1 |
| --- | --- | --- | --- | --- | --- | --- |
| Schemes | budget holder | Original | Slippage | Additional | Total | Total |
|  |  | Estimate |  | Approvals | Approved | Expenditure |
|  |  | 2007/08 |  |  | Budget | To Date |
|  |  | £ | £ | £ | £ | £ |
| Car Parks Rolling Programme 05/06 | gj | 22,000 | -9,950 |  | 12,050 | 312 |
| Car Parks Rolling Programme 06/07 | gj |  | 26,770 |  | 26,770 | 149 |
| Replace screens and ergonomices CCTV system | gj |  | 17,000 |  | 17,000 | 17,000 |
| Total Planning and Development Committee |  | 22,000 | 33,820 | 0 | 55,820 | 17,461 |

##### ANNEX 2

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CARPH |
| Name of Scheme | CAR PARKS ROLLING PROGRAMME 2005/06 |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Improvements to car parks at Chipping |  |  |  |
| Benefits of Scheme | Housing and public car park which meets the expectations of those using it and which meets nationally agreed standards. |  |  |  |
| Project Timetable | Start Date | February 2007 |  |  |
|  | Completion Date | April 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | We have yet, despite exhaustive efforts to do so, to complete the negotiation regarding a new base for the car park and toilets at Chipping. All delay is due to the Trustees. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes, provided the lease is sorted soon. |  |  |  |
| What are the revenue implications of the scheme? | Assuming that the introduction of charging for parking on this car park follows the improvement works there will be additional parking revenue generated. |  |  |  |

|  |  |  |  |  |  | Cost Centre | CARPH |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £12,050 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £37,220 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2005/06 £ | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  | 1,455 | 16,672 | 12,050 | 30,177 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  | 6,667 | 376 | 0 | 7,043 |
|  | TOTAL |  |  | 8,122 | 17,048 | 12,050 | 37,220 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Oct 2006 |  | Several meetings have been held with the Trustees and/or their Agents to date and whilst there is an agreement is principle to lease the car park and toilets to the council we have get to receive any formal proposals in writing. All delays are as a consequence of the difficulties with the Trustees. Until they are fully resolved work will not get underway. |  |  |  |  |  |
| End Dec 2006 |  | Pay and Display introduced at Sabden car park. Works to be carried out at Bolton by Bowland car park including resurfacing shortly. |  |  |  |  |  |
| End September 2007 |  | Works complete. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CARPI |
| Name of Scheme | CAR PARKS ROLLING PROGRAMME 2006/07 |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | To improve the overall standard of the car parks in the Borough. Work is likely to be undertaken at the car park at Chipping subject to agreeing the terms of a new lease with the Trustees. |  |  |  |
| Benefits of Scheme | Having public car parks which meet the expectation of their users and meet nationally recognised standards. |  |  |  |
| Project Timetable | Start Date | August 2006 |  |  |
|  | Completion Date | March 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Agreement of new lease with Trustees |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Only if staff are retrained and not transferred to the County Council on an arrangement of the termination of the Lancashire Highways Partnership. |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | CARPI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £26,770 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £41,200 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  | 4,737 | 26,770 | 31,507 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  | 9,695 |  | 9,695 |
|  | TOTAL |  |  |  | 14,432 | 26,770 | 41,202 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Sept 06 |  | Discussions are still ongoing with regard to new lease for Chipping car park |  |  |  |  |  |
| End Dec 06 |  | Draft lease now received from trustees of Chipping car park and currently being evaluated by our Legal Section. Anticipate this budget will need to be moved back to 2007/08 |  |  |  |  |  |
| End Sept 07 |  | Lease complete. Parking regulation order yet to be approved by Planning and Development Committee. Design work about to start but work will not commence until alterations to public conveniences are nearing completion. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | ERGTV |
| Name of Scheme | REPLACE SCREENS AND ERGONOMICS – CCTV SYSTEM |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Our CCTV monitoring services are currently provided by Broadland Guarding. They recently brought to our attention a number of concerns, including discomfort of operators therefore an ergonomic risk assessment was carried out. Following the risk assessment it has become necessary for the health and safety of the operation to redesign the layout of the office and the operating console. In doing so, taking into consideration the life expectancy of the display screen, it would be beneficial to change the screens to flat screens at the same time. Possible implications of not carrying out the required works are that Broadland Guarding may not be happy to carry on providing surveillance and we may be responsible for any future claims. |  |  |  |
| Benefits of Scheme | A safe and efficient working environment. |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | January 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | The project timetable may be affected depending on the priority given to this work. The full cost can only be established when a full design of the scheme has been undertaken. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Only if staff are retained and not transferred to the County Council as a consequence of the termination of the Lancashire Highways Partnership. |  |  |  |
| What are the revenue implications of the scheme? | None. |  |  |  |

|  |  |  |  |  |  | Cost Centre |  | ERGTV |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  | £17,000 |  |  |  |  |
| Summary | Expected Total Cost of Scheme: |  |  | £17,000 |  |  |  |  |
|  | Approved by Committee: |  |  | Full Council |  |  |  |  |
|  | Date: |  |  | 28 February 2006 |  |  |  |  |
|  | Minute Ref: |  |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  | Total Expenditure £ |  |  |  |  |
|  | Land |  |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |  |
|  | Other Costs |  |  | 16,000 |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |  |
|  | Internal Salaries |  |  | 1,000 |  |  |  |  |
|  | TOTAL |  |  | 17,000 |  |  |  |  |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |  |
| End March 2006 |  | Subject to having sufficient staff resources available an assessment of the overall objectives of the scheme will be undertaken by the end of May. This will produce a draft design proposal for estimating purposes. |  |  |  |  |  |  |
| End September 2007 |  | Work complete. |  |  |  |  |  |  |