# RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO HOUSING COMMITTEE

Agenda Item No

meeting date: 	3 DECEMBER 2007

title:	REVENUE MONITORING 2007/08

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	ROBIN BRAMHALL

# 1	PURPOSE

  - To report on the progress of revenue expenditure and income on housing revenue account and housing general fund for the period 1 April to 30 September 2007.

  - Expenditure within the housing revenue account and housing general fund advances the Council’s ambition to match the supply of homes within the Ribble Valley area with the identified housing needs.

  - Relevance to the Councils ambitions and priorities:

- In accordance with corporate plan objective 2.3, this report provides members with information to ensure that budget allocation and expenditure is in line with corporate priorities.

# BACKGROUND

# 2.1				The Council at their meeting on 27 February 2007 agreed the Budget for 2007/08. The committee should consider, on a regular basis, how expenditure and income is progressing against the approved figures.

# 3  	ISSUES AND FINANCIAL IMPLICATIONS

3.1	Housing Revenue Account (HRA)

The table below compares actual expenditure and income within the housing revenue account for the first half of the financial year with the original estimate profiled for the same period. To date there is a net saving of £5,850. The main reasons for this are shown in Annex 1.

|  | Original Estimate £ | Actual £ | Difference £ |
| --- | --- | --- | --- |
| Repairs and Maintenance | 280,780 | 232,270 | -48,510 |
| Supervision and Management | 75,030 | 119,050 | 44,020 |
| Accommodation for the Aged | 189,960 | 188,600 | -1,360 |
|  | 545,770 | 539,920 | -5,850 |

  - Housing General Fund

The comparable figures are as follows:

|  | Original Estimate £ | Actual £ | Difference £ |
| --- | --- | --- | --- |
| Benefits | -98,160 | -110,550 | -12,390 |
| Homelessness | 15,220 | 25,860 | 10,640 |
| Improvement Grants | 1,260 | 260 | -1,000 |
| Rural Housing | -19,110 | -14,980 | 4,130 |
|  | -100,790 | -99,410 | 1,380 |

The main reasons for these differences are also shown in Annex 1.

4						CONCLUSION

4.1 	The comparison between actual and budgeted expenditure shows a small net saving on housing revenue account and a small net increase on housing general fund after six months of this financial year.

ROBIN BRAMHALL

SENIOR ACCOUNTANT

H9-07/RB/AC

11 OCTOBER 2007

Annex 1

Housing Committee

Variations in excess of £1,000

| Housing Revenue Account | £ | £ | Reason |
| --- | --- | --- | --- |
| Repairs and Maintenance |  |  |  |
| Day to Day Repairs | -2,470 |  |  |
| General Repairs | -1,810 |  |  |
| Disabled Repairs | 14,410 |  |  |
| Gas Repairs | -8,390 |  |  |
| Re- Lets | -20,020 |  |  |
| Major Re-Lets | 7,740 |  |  |
| Gas Service | -5,400 |  |  |
| Depot Wages | 4,790 |  |  |
| Contingency | -37,360 |  |  |
|  |  | -48,510 | Overall payments behind Budget profile |
| Supervision and Management |  |  |  |
| House Clearances and other | -2,250 |  | Payments behind Budget profile |
| Consultants Fees | 48,370 |  | Majority of this to be recovered |
| Tenants Participation/ Consultants | -2,100 |  | Payments behind Budget profile |
|  |  | 44,020 |  |
| Accommodation for the Aged |  |  |  |
| Salaries and Wages | 7,140 |  | Additional expenditure, in part due to Job Evaluation |
| Repairs and Maintenance | 760 |  | Payments ahead of Budget profile |
| Gas | -9,260 |  | Payments behind profile |
|  |  | -1,360 |  |
|  |  | -5,850 |  |

| Housing General Fund | £ | £ | Reason |
| --- | --- | --- | --- |
| Housing and Council Tax Benefits |  |  |  |
| Rent Allowance Payments | -5,460 |  | Payments behind profile |
| Council Tax Benefits | 7,700 |  | Benefits granted ahead of profile |
| Rent Rebates | 8,670 |  | Rebates granted ahead of profile |
| Non HRA Rent Rebates | -3,000 |  | Expenditure behind budget profile |
| Rent Allowance Subsidy | 16,800 |  | Subsidy received behind profile |
| Council Tax Rebates subsidy | 5,380 |  | Subsidy received behind profile |
| Rent Rebates Subsidy | 5,090 |  | Subsidy received behind profile |
| Housing Benefits postage | -1,750 |  | Expenditure behind budget profile |
| Housing Benefits Software | 19,760 |  | Additional expenditure - financed from Local Housing Allowance |
| Housing Benefits Other staff expenditure | 2,080 |  | Additional expenditure - financed from Local Housing Allowance |
| Benefits Admin Subsidy | -67,660 |  | Additional Subsidy received re Local Housing Allowance |
| Other expenditure | 0 |  | Payments behind profile |
|  |  | -12,390 |  |
| Homelessness |  |  |  |
| Contract payments | 2,540 |  | Payments ahead of profile |
| Homelessness Subsidy | 7,500 |  | No subsidy received so far this year |
| Joiners Arms - Salaries | 1,800 |  | Expenditure ahead of budget profile |
| -Purchase of equipment and materials | -1,200 |  | Expenditure behind budget profile |
|  |  | 10,640 |  |
| Improvement Grants |  |  |  |
| Consultants costs |  | -1,000 | Expenditure behind budget profile |
| Rural Housing |  |  |  |
| Other Income |  | 4,130 | Income received behind Budget profile |
|  |  | 1,380 |  |

# Text boxes

INFORMATION

IINFORMATION