RIBBLE VALLEY BOROUGH COUNCIL

DECISION

REPORT TO COMMUNITY COMMITTEE

Agenda Item No

meeting date: 	15 JANUARY 2008

title:	REVISED CAPITAL PROGRAMME 2007/08 AND PROPOSED

PROGRAMME 2008/13

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

1	PURPOSE

1.1	To approve the revised programme for the current year and also the future five-year capital programme for this committee.

2	BACKGROUND

2.1	This report will review the following:

i)	The current year's programme.

ii)	Draft programme of schemes to be carried out in the following five years (2008/09 to 2012/13).

3	ORIGINAL PROGRAMME 2007/08 – CURRENT FINANCIAL YEAR

3.1	The original capital programme for the current year included schemes at a total estimated cost of £1,049,510.

3.2	Unfinished schemes from 2006/07, totalling £153,200, have been added to the original programme.  This is shown in Annex 1 and known as slippage.

4	REVISING THE CURRENT YEAR'S PROGRAMME

4.1	We have now discussed in some detail each scheme in the programme with budget holders and the Capital Working Group and revised the programme to reflect likely expenditure this year.  This is shown in Annex 1, alongside the original estimate.

4.2	Updated capital evaluation forms completed by the responsible officers, for all these schemes were reported to committees in the previous cycle.

4.3	In summary, the revised programme is:

| Total Approved Budget £ | Revised Estimate for Current Year £ | Expenditure to Date £ |
| --- | --- | --- |
| 2,186,550 | 2,781,580 | 945,281 |

5	DRAFT PROGRAMME 2008/09 TO 2012/13

5.1	New schemes have been put forward by officers to form part of our five-year capital programme.  Annex 2 (GREEN) shows the draft programme for this committee.

5.2	However, this is really only the first attempt to ascertain future schemes.  Therefore, Annex 2 is a possible programme that will require further consideration by the Budget Working Group and by Policy and Finance Committee who will want to make sure that it is affordable, both in capital and revenue terms.

5.3	A new capital scheme pro forma has been completed for any new schemes added to the five year programme by the relevant officer.  These are attached at Annex 3 (BLUE).

5.4	Members should therefore consider the new schemes and indeed the existing schemes as shown  in Annex 2 and put forward any amendments you may wish to make at this stage.

5.5	Capital evaluation forms for all new schemes approved for next year (2008/09) will be completed and reported to committees in the next cycle.

5.6	A summary of the five-year programme for Community Committee is shown below:

| 2008/09 £ | 2009/10 £ | 2010/11 £ | 2011/12 £ | 2012/13 £ |  | Total £ |
| --- | --- | --- | --- | --- | --- | --- |
| 3,753,480 | 1,001,000 | 408,100 | 93,400 | 332,000 |  | 5,587,980 |

6	RECOMMENDED THAT COMMITTEE

6.1	Approve the revised capital programme for 2007/08 as set out in Annex 1.

6.2	Consider the future five-year programme for 2008/09 to 2012/13 as set out in Annex 2 and agree any amendments you wish to make.

FINANCIAL SERVICES MANAGER

CM1-08/JP/AC

7 JANUARY 2008

|  |  | Budget Analysis |  |  |  |  |  | Expenditure Analysis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost | Schemes | Original | Slippage | Additional | Total | Revised | Budget | Total |
| Centre |  | Estimate |  | Approvals | Approved | Estimate | moved to | Expenditure |
|  |  | 2007/08 |  |  | Budget |  | 2008/09 | To Date |
|  |  | £ | £ | £ | £ | £ | £ | £ |
| BADWC | Badger Well Water Culvert Collapse |  |  | 10,000 | 10,000 | 10,000 |  | 0.00 |
| BPSCT | Brungerley Park Sculpture Trial |  |  | 14,620 | 14,620 | 14,620 |  | 8,589.72 |
| CCSHE | Provision of shelter in Woodland Cemetery | 8,500 |  |  | 8,500 | 8,500 |  | 0.00 |
| CSLOT | Castle Lottery scheme Phase 2 | 33,750 | 9,910 |  | 43,660 | 902,000 |  | 559,501.01 |
| EDCHR | Edisford Changing Rooms | 65,000 |  |  | 65,000 | 0 | 65,000 | 502.40 |
| FITRM | Relocate fitness room at LSC to Longridge Civic Hall | 18,600 |  | 196,000 | 214,600 | 214,600 |  | 0.00 |
| GALBO | Replace Boiler at Platform Gallery | 11,000 |  |  | 11,000 | 11,000 |  | 8,633.00 |
| GFCYC | Gisburn Forest Park Cycling Trails | 20,000 |  |  | 20,000 | 8,000 | 12,000 | 0.00 |
| KEEPR | Castle Keep Repairs - Phase 1 |  | 48,480 |  | 48,480 | 74,050 |  | 73,828.92 |
| LFIRD | Provision of Fire Escape at Longridge Depot | 6,300 | -1,510 |  | 4,790 | 4,790 |  | 2,492.00 |
| LOCHG | Grant Aid to Longridge Action Group re Civic Hall |  | 10,000 | -10,000 | 0 | 0 |  | 0.00 |
| LROOF | Longridge Sports Centre Roof |  |  | 61,800 | 61,800 | 39,650 | 1,380 | 39,651.47 |
| LSKAT | Longridge Skate Park Retention |  |  | 3,000 | 3,000 | 3,340 |  | 379.84 |
| LSREC | Longridge Sports Centre Reception | 54,410 |  | -54,410 | 0 | 0 |  | 109.90 |
| PBOIL | Pool - Replace boiler and calorifier | 96,300 |  |  | 96,300 | 96,300 |  | 11,420.00 |
| PCCHI | Refurbishment of Chipping Toilets | 75,000 |  | 8,800 | 83,800 | 90,300 |  | 60,369.19 |
| PCRPE | Replace Slaidburn Toilets |  | 2,500 |  | 2,500 | 2,500 |  | 2,444.15 |
| PCWHA | Funding towards reconstruction of Whalley Toilets | 50,000 |  |  | 50,000 | 0 | 50,000 | 0.00 |
| PESSU | Replace Suzuki Van - PJ02 NNA | 10,000 |  |  | 10,000 | 10,120 |  | 10,106.62 |
| PLAYH | Improvements to children's play areas | 50,000 |  |  | 50,000 | 50,000 |  | 33,057.11 |
| POENE | Energy Efficiency measures to Ribblesdale Pool | 104,500 |  |  | 104,500 | 104,500 |  | 1,552.23 |
| POSTW | Replace Steel Windows to building at Ribblesdale Pool | 36,400 |  |  | 36,400 | 36,400 |  | 0.00 |
| RALSH | Replace Grounds Maintenance Allet Shaver with Dennis cylinder mower | 2,245 |  |  | 2,245 | 2,250 | 0 | 2,245 |
| RCOLT | Replace N313 SWK Dennis Refuse Collection Vehicle | 180,000 |  |  | 180,000 | 180,000 |  | 0 |
| REBIN | Recycling and Residual Waste Containers | 172,500 |  |  | 172,500 |  | 172,500 | 0 |
| RGBUF | Replace Grounds Maintenance 4 Allett Buffalo mowers with 1 Dennis | 6,985 |  |  | 6,985 | 6,980 |  | 6,985 |
| RGDCW | Replace Grounds Maintenance Hayter ride-on N383 DCW | 20,800 |  |  | 20,800 | 20,700 |  | 20,700 |
| RGMOW | Purchase of 4 mowing machines & Trailer | 7,700 |  |  | 7,700 | 5,200 |  | 5,159 |
| RGOFR | Replace Grounds Maintenance G190 OFR mini tractor | 9,000 |  |  | 9,000 | 9,000 |  | 9,000 |
| RIBCA | Refurbishment of Ribchester Public Conveniences | 37,200 |  |  | 37,200 | 37,200 |  | 17,887 |
| RLIFT | Bin Lifts (x2) for existing Refuse Vehicles | 30,900 |  |  | 30,900 |  | 30,900 | 0 |
| ROSEG | Rose Garden Castle Grounds |  |  |  |  | 56,000 |  | 48,802 |
| RPCHA | Ribblesdale Pool - Refurbish Staff changing rooms & external store |  | 6,700 |  | 6,700 | 7,100 |  | 7,104 |
| RVERG | Replace Grounds Maintenance 3 Blade Verge Cutter Haytor Condor | 4,500 |  |  | 4,500 | 4,500 |  | 4,497 |
| RWFBU | Replace Grounds Maintenance Vehicle R485 FBU Iveco 7.5tonne | 37,000 |  |  | 37,000 | 35,100 |  | 35,090 |
| RWKEG | Replace P715 KEG Ford General Works Vehicle | 15,400 |  |  | 15,400 | 12,100 |  | 12,040 |
| RWXCK | Replace Grounds Maintenance Vehicle P996 XCK with Transit van | 13,500 |  |  | 13,500 | 11,800 |  | 11,726 |
| SDIMP | Improvements to Salthill Depot budget moved from 05/06 | 6,530 |  |  | 6,530 | 7,000 |  | 7,004 |
| SYNCA | Longridge Sports Centre Replace carpet on synthetic pitch | 133,900 |  |  | 133,900 |  | 133,900 | 0 |
|  | Total Community Committee | 1,049,510 | 153,200 | 10,000 | 1,212,710 | 1,077,870 | 494,310 | 711,810 |

| Page no | Scheme | 2008/09 | 2009/10 | 2010/11 | 2011/12 | 2012/13 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | £ | £ | £ | £ | £ | £ |
|  | Community Committee |  |  |  |  |  |  |
|  | Public Conveniences |  |  |  |  |  |  |
|  | Replace & increase size of Dunsop Bridge Toilets |  |  | 121,500 |  |  | 121,500 |
| ## 8 | Refurbishment of Clitheroe Market Toilets |  | 39,000 |  |  |  | 39,000 |
| ## 10 | Refurbishment of Castle Field Toilets |  |  |  | 43,400 |  | 43,400 |
|  | Add budget moved from 2007/08 - Funding towards Whalley Toilets | 50,000 |  |  |  |  | 50,000 |
|  | Outdoor Recreation |  |  |  |  |  |  |
|  | Improvements to children's play areas | 50,000 | 50,000 | 50,000 | 50,000 | 50,000 | 250,000 |
| 12 | Replacement of Outdoor Recreation Equipment | 21,000 |  |  |  |  | 21,000 |
|  | Edisford Changing Rooms | 150,000 |  |  |  |  | 150,000 |
|  | Add budget for Edisford Changing Rooms moved from 2007/08 | 65,000 |  |  |  |  | 65,000 |
|  | Calderstones Open Space | 75,000 |  |  |  |  | 75,000 |
| 14 | Brungerly Park Footpath | 115,000 |  |  |  |  | 115,000 |
|  | Add budget moved from 2007/08 Gisburn Forest Park Cycling Trails | 12,000 |  |  |  |  | 12,000 |
|  | Sports Development |  |  |  |  |  |  |
|  | Grant Aid to Longridge Action Group re Civic Hall | 90,000 |  |  |  |  | 90,000 |
| 16 | Replace Equipment at West Bradford Community Gym | 13,900 |  |  |  | 17,000 | 30,900 |
|  | Clitheroe Castle |  |  |  |  |  |  |
|  | Castle Lottery scheme | 2,308,300 | 65,000 |  |  |  | 2,373,300 |
|  | Improvements to Clitheroe Castle Keep | 110,000 |  |  |  |  | 110,000 |
| 18 | Improvements to grounds and surrounds of Castle | 32,000 | 32,000 |  |  |  | 64,000 |
|  | Clitheroe Market |  |  |  |  |  |  |
| 20 | Replacement of Stalls |  | 100,000 |  |  |  | 100,000 |
| 22 | Replacement of Paving as part of Redevelopment scheme |  | 400,000 |  |  |  | 400,000 |
|  | Clitheroe Cemetery |  |  |  |  |  |  |
| 24 | Purchase of land | 42,000 |  |  |  |  | 42,000 |
|  | Longridge Sports Centre: |  |  |  |  |  |  |
|  | Add budget moved from 2007/08 - Roof Retention | 1,380 |  |  |  |  | 1,380 |
|  | Add budget moved from 2007/08 - Synthetic Pitch | 133,900 |  |  |  |  | 133,900 |
|  | Refuse Collection |  |  |  |  |  |  |
|  | Replace V052 FRL Dennis | 180,000 |  |  |  |  | 180,000 |
|  | Replace V052 FRJ Dennis |  | 180,000 |  |  |  | 180,000 |
|  | Replace V052 FRK Dennis |  |  | 180,000 |  |  | 180,000 |
| 26 | Replace Refuse Collection/Recycling vehicle |  |  |  |  | 190,000 | 190,000 |
|  | Recycling and Residual Waste Containers | 236,000 |  |  |  |  | 236,000 |
| 28 | Repair/Replace Floors in Waste Transfer Station |  |  |  |  | 75,000 | 75,000 |
| 30 | Wheeled Bin Lifting Equipment | 40,000 |  |  |  |  | 40,000 |
|  | General Works |  |  |  |  |  |  |
|  | Replace V955 EVM JCB |  |  | 25,700 |  |  | 25,700 |
|  | Replace PF03 HFA Ford Transit |  | 15,400 |  |  |  | 15,400 |
|  | Replace PF03 HEU Ford Transit |  | 15,400 |  |  |  | 15,400 |
|  | Replace PF03 HFE Ford Transit |  | 15,400 |  |  |  | 15,400 |
|  | Replace PE54 YXF |  | 15,400 |  |  |  | 15,400 |
|  | Replace Replacement for R675 HCW (PO54 COA) |  | 30,900 |  |  |  | 30,900 |
|  | Replace Replacement for P291 RCW (P054 COH) |  |  | 30,900 |  |  | 30,900 |
|  | Small Jetting Machine |  | 20,600 |  |  |  | 20,600 |
| 32 | Improvements to vehicle repair workshop | 18,000 |  |  |  |  | 18,000 |
| 34 | Reroofing work to Longridge Depot |  | 20,300 |  |  |  | 20,300 |
|  | Outdoor Recreation Vehicles and Plant: |  |  |  |  |  |  |
|  | Replace P053 WYW |  | 1,600 |  |  |  | 1,600 |
| 36 | Replace Pest Control Vehicle | 10,000 |  |  |  |  | 10,000 |
|  | Total Community Committee | 3,753,480 | 1,001,000 | 408,100 | 93,400 | 332,000 | 5,587,980 |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | Rod Pearce |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Refurbishment at Market WC’s |  |
| Full Details of Scheme |  | Full Refurbishment of internals to Market WC’s to improve anti vandal measures. |  |
| Links to Corporate Objectives |  | Make people’s lives safer and healthier |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 35,000 |  |
|  | Fees |  |  |
|  | Internal Staff Salaries | 4,000 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 39,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | April |  |
|  | scheme completion | June |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2009/10 |  | If possible |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | Rod Pearce |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Refurbishment of Castle Field WC’s |  |
| Full Details of Scheme |  | Existing WC requires internal refurbishment, retiling, floor covering, anti vandal fitting. This WC experiences ongoing vandalism. |  |
| Links to Corporate Objectives |  | Make people’s lives safer and healthier. Protect environmental quality of area |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 39,400 |  |
|  | Fees | 4,000 |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 43,400 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | November |  |
|  | scheme completion | March |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2012/13 |  | 2011/12 if possible |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | GRAHAM JAGGER |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Replacement of outdoor recreation equipment. |  |
| Full Details of Scheme |  | Replace carpet and repair sub structure of artificial cricket wicket at Roefield Playing Fields, Clitheroe - £6,000 Replace goal posts on 13 football pitches - £15,000 |  |
| Links to Corporate Objectives |  | Community Strategy - Health and Well-being Corporate performance and Improvement Plan - To make peoples lives safer and healthier |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 20,500 | Installation of goal posts by general Works Section. |
|  | Fees |  |  |
|  | Internal Staff Salaries | 500 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 21,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | APRIL 2008 | Artificial cricket wicket so ready for season |
|  | scheme completion | JULY 2008 | Install new goal posts ready for start of season in August. |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |
|  | Possible grant aid from Football Association towards cost of new goal posts. |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | GRAHAM JAGGER |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Repairs to collapsed footpath in Brungerly Park, Clitheroe. |  |
| Full Details of Scheme |  | Repair the well-used walk footpath which forms part of the Ribble Way in Brungerly Park. - full repair, reinstatement of footpath and stabilisation of riverbank and adjoining slopes - £115,000 (b) stabilisation of riverbank and associated works to trees, etc and diversion of footpath so closing off central section of river walk path - £60,000 |  |
| Links to Corporate Objectives |  |  |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 100,000 | Estimate for scheme (a) |
|  | Fees | 10,000 |  |
|  | Internal Staff Salaries | 5,000 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 115,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | NOV 2008 |  |
|  | scheme completion | FEB 2009 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2008/09 |  |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | Tracy Balko |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | West Bradford Community Gym. Based in West Bradford Village Hall. Replacement of outdated equipment |  |
| Full Details of Scheme |  | The Community gym at West Bradford Village hall has been operating successfully since 2000. RVBC run Fitness for Life exercise referral sessions 3 days a week and also run cardiac rehabilitation sessions at the facility. The programme is successful as we offer a safe and none-intimidating environment where clients with health problems can gain the benefits of physical activity at their own level. It is a dual usage facility and is used by West Bradford Gym Club in the evenings. Most of the cardiovascular and resistance equipment was originally installed at Longridge Sports Centre and was moved to West Bradford in 2000 making it approximately 14/15 years old. The equipment is outdated and the resistance equipment is not suitable for the majority of our clients (GP and cardiac rehab referrals) If more appropriate and safer equipment was installed we would be able to accommodate more clients at our sessions. |  |
| Links to Corporate Objectives |  | Making lives safer and HEALTHIER Access for all |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor |  |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | £30,900 | Equipment |
|  |  | £30,900 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  | None | The sessions are self-financing and clients pay a nominal charge, existing budgets cover any additional running costs (maintenance, servicing etc.) |
| Timescale (incl any key dates) |  | N/A | Ongoing project, we are looking to replace outdated equipment |
|  | eg start on site |  |  |
|  | scheme completion |  |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2008/9 | £13,900 | To replace CV and Resistance Equip |
|  | 20012/13 | £17,000 | To replace treadmills and rowers |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |
|  | NA |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | GRAHAM JAGGER |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Improvements to grounds and surrounds of Clitheroe Castle. |  |
| Full Details of Scheme |  | Repairs and reconstruction of roads, paths, walks, railings and improvements to landscaped areas in and around the grounds of Clitheroe Castle to compliment the work being done to the main buildings around the Museum. |  |
| Links to Corporate Objectives |  | To protect and enhance the existing environmental quality of our area. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 60,000 | Spread over 2 financial years |
|  | Fees |  |  |
|  | Internal Staff Salaries | 4,000 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 64,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | SEPT 2008 |  |
|  | scheme completion |  |  |
|  | other dates… | JUNE 2009 |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2008/9 | 32,000 |  |
|  | 2009/10 | 32,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | James Russell |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Estimated cost of replacement of market stalls as part of Clitheroe Market redevelopment scheme to provide office for Ribble Valley Homes. |  |
| Full Details of Scheme |  | To make provision to replace existing market stalls to improve visual amenity, layout and weather protection to complement prestigious redevelopment of central location. |  |
| Links to Corporate Objectives |  | Make peoples lives safer and healthier To protect and enhance the existing environmental quality of our area |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 25,000(est) |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 100,000 (est) |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site |  |  |
|  | scheme completion |  |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2009/10 | 100,000 (est) | Make provision for investment in site development. |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | Rod Pearce |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Estimated cost of replacement of market paving as part of Clitheroe Market redevelopment scheme to provide office for Ribble Valley Homes. |  |
| Full Details of Scheme |  | To make provision to replace the longstanding and ongoing defective paving to the market pedestrian area to complement Ribble Valley Homes office development project. |  |
| Links to Corporate Objectives |  | Make peoples lives safer and healthier To protect and enhance the existing environmental quality of our area |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 400,000 | (Estimate) |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 400,000 | (Estimate) |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site |  |  |
|  | scheme completion |  |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2009/10 | 400,000 | Make provision for investment in site development |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | James Russell |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Purchase of adjacent land to Clitheroe Cemetery to permit eventual extension of lawn cemetery which has estimated capacity for approximately 10 years. There will need to be a further capital scheme developed to erect fencing and provide necessary infrastructure to enable burials. |  |
| Full Details of Scheme |  | Purchase of adjacent land to Clitheroe Cemetery to permit eventual extension of lawn cemetery subject to geological survey. Plot of land approximately 9 acres. Will require planning permission for change of use. |  |
| Links to Corporate Objectives |  | Make peoples lives safer and healthier To protect and enhance the existing environmental quality of our area |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land | 37,000 | Initial purchase |
|  | Contractor |  |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | 5,000 (Estimate) | Geological survey, conveyancing, planning application and repairs to perimeter fencing |
|  |  | 42,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site |  |  |
|  | scheme completion |  |  |
|  | other dates… | April 2008 | To be included in the Capital Programme |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | To be determined | 42,000 | (Estimate) |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |
|  | None |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | GRAHAM JAGGER |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Purchase of a new refuse collection/recycling vehicle to replace one in the fleet. |  |
| Full Details of Scheme |  | Part of vehicle replacement programme to ensure fleet is efficient, effective and fit for purpose. |  |
| Links to Corporate Objectives |  | Environmental Excellence. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 190,000 |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 190,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site |  |  |
|  | scheme completion |  |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2012/13 |  |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | GRAHAM JAGGER |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Repair/replace floors in Waste Transfer Station at Salthill Depot, Clitheroe. |  |
| Full Details of Scheme |  | Carry out repairs to or replacement of floors in both the residual waste and recyclate buildings at the Waste Transfer Station due to wear and tear. |  |
| Links to Corporate Objectives |  | To maintain the Waste transfer Station which supports the refuse collection and recycling service provided by the Council. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 70,000 |  |
|  | Fees |  |  |
|  | Internal Staff Salaries | 5,000 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 75,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | SEPT 2012 |  |
|  | scheme completion | NOV 2012 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | GRAHAM JAGGER |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Wheeled Bin Lifting Equipment. |  |
| Full Details of Scheme |  | Fit triple bin lift to VX53 TZJ so that the vehicle can be retained and used as spare vehicle when another is off the road for repairs and maintenance. Without this there will be no spare vehicle available to support the service |  |
| Links to Corporate Objectives |  | To support the 3 stream refuse collection and recycling service |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | £40,000 |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | £40,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site |  |  |
|  | scheme completion |  | Fit new equipment in May/June 2008 |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | GRAHAM JAGGER |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Improvements to vehicle repair workshop. |  |
| Full Details of Scheme |  | Either - extend existing maintenance pit for health & safety reasons or - fill in maintenance pit and purchase equipment capable of lifting the new heavier and longer refuse collection and recycling vehicles so maintenance can take place under the vehicles. |  |
| Links to Corporate Objectives |  | So that vehicles can be repaired and maintained in order to provide statutory and essential services. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 17,000 |  |
|  | Fees |  |  |
|  | Internal Staff Salaries | 1,000 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 18,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  | 500 | Cost of servicing vehicle lifting equipment |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | APRIL 2008 | Evaluate options and other prices |
|  | scheme completion |  |  |
|  | other dates… | JULY 2008 | Issue orders/carry out work. |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2008/9 |  |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | Rod Pearce |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Re roofing work to Longridge Depot |  |
| Full Details of Scheme |  | Existing roof covering is beyond effective life. Scheme to strip off coverings, carry out timber repairs re-felt, batten. Re slate, replace rainwater goods. |  |
| Links to Corporate Objectives |  | Make people’s lives safer and healthier Protect environmental quality of area |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 18,000 |  |
|  | Fees |  |  |
|  | Internal Staff Salaries | 1,800 |  |
|  | Planning/Build Regs Fees | 500 |  |
|  | Other costs |  |  |
|  |  | 20,300 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | e.g. start on site | August |  |
|  | scheme completion | September |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year e.g. | £ |  |
|  | 2012/2013 |  | Really needs bringing forward 2009/10 latest |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| ## Name of Officer Responsible |  | James Russell |  |
| Committee |  | COMMUNITY |  |
| Brief Description of Scheme |  | Routine renewal of Pest Control Vehicle with Fiat Doblo 1.3SX Diesel white panel van |  |
| Full Details of Scheme |  | Routine replace of Suzuki Carry 1.3 ( PJ02 NNA ) with Fiat Doblo 1.3 SX Diesel |  |
| Links to Corporate Objectives |  | Make peoples lives safer and healthier Improved vehicle safety for operative |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Vehicle | 8,500 | Initial purchase OTR |
|  | Contractor |  |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | 1,500 | Vehicle modification for purpose |
|  |  | 10,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site |  |  |
|  | scheme completion |  |  |
|  | other dates… | April 2008 | Purchase early in next financial year |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/8 | 10,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |
|  | Vehicle to be replaced is owned by RVBC and should be some capital from sale of vehicle. |  |  |