# RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO HEALTH AND HOUSING COMMITTEE

Agenda Item No

meeting date: 	24 JULY 2008

title:	CAPITAL OUTTURN 2007/08

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

1	PURPOSE

  - To inform you of the final outturn on our capital programme for 2007/08 for this committee.

- BACKGROUND

  - The Capital Programme for the Housing Committee consisted of 5 schemes.  These were either

- New schemes approved as part of the 5 year capital programme in February 2007

OR

- Schemes with slippage from 2006/07

  - During the financial year completed capital evaluation sheets for all schemes have been reported to committee.

  - As part of the closure of our accounts process, scheme expenditure has been capitalised and added to our balance sheet or charged to revenue where appropriate.

  - Please note this report refers to the capital programme for the schemes approved for Housing Committee for the 2007/08 financial year and thus does not include schemes which reflect the new responsibilities for Health and Housing Committee following the changes to Terms of Reference in May 2008.

- FINANCIAL PERFORMANCE

  - Summary

| BUDGET ANALYSIS | EXPENDITURE | SLIPPAGE |
| --- | --- | --- |
| Original Estimate £ | Slippage from 06/07 £ | Additional Approvals £ | Total Approved Budget £ | Revised Estimate £ | Actual Expenditure £ | Slippage to 08/09 £ |
| 1,201,800 | -28,200 | 74,700 | 1,248,300 | 1,271,600 | 1,138,909 | 128,290 |

  - Annex 1 to this report compares the budget for each scheme with actual expenditure.

  - You will see actual expenditure for Housing Revenue Schemes was more or less the same as the revised estimate.  Due to the housing stock transfer a concerted effort was made to finish all schemes by 31 March 2008.  This was achieved with only retentions outstanding and these have been brought into the programme as creditors.  Therefore the Housing Revenue Capital Programme has now been finished with no slippage into 2008/09.  The Major Repairs Allowance (MRA) available was fully utilised in the financing of the programme.  This was important as any unused MRA may have had to be returned to the Government.

- SLIPPAGE

  - Where capital schemes are unfinished at the end of the financial year and there is a corresponding remaining unspent budget this is known as slippage and the budget is carried forward into the next financial year.

  - For this committee there were two schemes with slippage into 2008/09.  There was no expenditure in 2007/08 for the Equity Release Loans Scheme.  However the slippage for this scheme was reduced by £8,820 to cover the overspend on the Disabled Facilities Grants scheme.

| Cost Centre | Schemes | Slippage Into 2008/09 £ |
| --- | --- | --- |
|  | Community |  |
|  | Housing General Fund Schemes |  |
| LANGR | Landlord/Tenant Grants | 15,110 |
| EQUIT | Equity Release Loans | 113,180 |
|  | Total Health & Housing | 128,290 |

- CONCLUSION

  - The capital accounts for 2007/08 have now been closed.  Schemes with slippage have been carried forward into 2008/09.

# FINANCIAL SERVICES MANAGER

# HH8-08/JP/AC

15 JULY 2008

| Cost Centre | Schemes | Original Estimate 2007/08 £ | Slippage £ | Additional Approvals £ | Total Approved Budget £ | Revised Estimate £ | Budget Moved to 2008/09 £ | Actual Expenditure £ | Slippage into 2008/09 £ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Housing General Fund Schemes |  |  |  |  |  |  |  |  |
| LHOME | Improvements to Longridge Homeless Facility |  | 10,700 |  | 10,700 | 10,000 |  | 10,086 |  |
|  | Improvement Grants: |  |  |  |  |  |  |  |  |
| LANGR | Landlord/Tenant Grants | 100,000 | 13,100 |  | 113,100 | 113,100 |  | 97,994 | 15,110 |
| EQUIT | Equity Release Loans | 138,000 |  |  | 138,000 | 122,000 |  | 0 | 113,180 |
| DISCP | Disabled Facilities Grants | 120,000 |  |  | 120,000 | 160,000 |  | 168,817 |  |
|  | Total Housing General Fund | 358,000 | 23,800 | 0 | 381,800 | 405,100 | 0 | 276,897 | 128,290 |
|  | Housing Revenue Schemes |  |  |  |  |  |  |  |  |
| IMPCN | Council House Improvements 2007/08 | 843,800 | -52,000 | 74,700 | 866,500 | 866,500 |  | 862,012 |  |
|  | Total Housing Revenue Schemes | 843,800 | -52,000 | 74,700 | 866,500 | 866,500 | 0 | 862,012 | 0 |
|  | Total Housing Committee | 1,201,800 | -28,200 | 74,700 | 1,248,300 | 1,271,600 | 0 | 1,138,909 | 128,290 |

# Text boxes

INFORMATION