RIBBLE VALLEY BOROUGH COUNCIL

INFORMATION

REPORT TO POLICY AND FINANCE COMMITTEE

Agenda Item No

meeting date: 	29 JULY 2008

title:	CAPITAL OUTTURN 2007/08

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

1	PURPOSE

  - To inform you of the final outturn on our capital programme for 2007/08 for this committee.

- BACKGROUND

  - The Capital Programme for this Committee consisted of 10 schemes.  These were either

- New schemes approved as part of the 5 year capital programme in February 2007

- Schemes with slippage from 2006/07

- New additional approvals brought into the programme during the course of the year.

  - During the financial year completed capital evaluation sheets for all schemes have been reported to committee.

  - As part of the closure of our accounts process, scheme expenditure has been capitalised and added to our balance sheet or charged to revenue where appropriate.

- FINANCIAL PERFORMANCE

  - Summary

| BUDGET ANALYSIS |  |  |  |  | EXPENDITURE | SLIPPAGE |
| --- | --- | --- | --- | --- | --- | --- |
| Original Estimate £ | Slippage from 06/07 £ | Additional Approvals £ | Total Approved Budget £ | Revised Estimate £ | Actual Expenditure £ | Slippage to 08/09 £ |
| 87,800 | 112,320 | 795,000 | 995,120 | 125,780 | 68,712 | 53,030 |

  - Annex 1 to this report compares the budget for each scheme with actual expenditure.

- SLIPPAGE

  - Where capital schemes are unfinished at the end of the financial year and there is a corresponding remaining unspent budget this is known as slippage and the budget is carried forward into the next financial year.

  - For Policy and Finance Committee there are 2 schemes with slippage.  These are shown below

| Cost Centre | Schemes | Slippage Into 2008/09 £ |
| --- | --- | --- |
| CIVHS | Civic Suite - DDA & Impts to stored water system | 14,520 |
| EGIIV | E Government Initiative | 38,510 |
|  | # Total | 53,030 |

- CONCLUSION

  - The capital accounts for 2007/08 have now been closed.  Schemes with slippage have been carried forward into 2008/09.

- FINANCIAL SERVICES MANAGER

- PF37-08/JP/AC

22 JULY 2008

|  |  |  | Budget Analysis |  |  |  |  |  | Expenditure Analysis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost | Schemes | budget holder | Original | Slippage | Additional | Total | Revised | Budget | Total |
| Centre |  |  | Estimate |  | Approvals | Approved | Estimate | moved to | Expenditure |
|  |  |  | 2007/08 |  |  | Budget |  | 2008/09 | To Date |
|  |  |  | £ | £ | £ | £ | £ | £ | £ |
|  | Policy & Finance Committee |  |  |  |  |  |  |  |  |
| CIVHS | Civic Suite - DDA & Impts to stored water system | rp |  | 25,950 |  | 25,950 | 25,950 |  | 11,428.41 |
| CROOM | Computer Server Room Improvements | ph |  | 11,940 |  | 11,940 | 11,940 |  | 11,126.89 |
| EENAB | eEnabling Members | msm |  | 3,200 |  | 3,200 | 0 |  | 0.00 |
| EGIIV | E Government Initiative | ml |  | 53,230 |  | 53,230 | 43,230 |  | 4,722.20 |
| OFCEI | Fire safety improvements to council office ceilings | rp | 21,600 |  |  | 21,600 | 21,600 |  | 24,781.31 |
| PRRIS | Replace Risograph Printer | msm | 6,200 |  |  | 6,200 | 6,200 |  | 0.00 |
| ROEFL | Roefield Loan | ms |  |  | 645,000 | 645,000 | 0 | 645,000 | 0.00 |
| RTELE | Replace Telephone system | msm |  | 8,000 |  | 8,000 | 6,860 |  | 6,860.40 |
| TRING | Grant/Loan to Trinity | ms | 60,000 |  | 150,000 | 210,000 | 0 | 210,000 | 0.00 |
| UPFIN | Upgrade of Financial Ledger System | jp |  | 10,000 |  | 10,000 | 10,000 |  | 9,792.40 |
|  | Total Policy & Finance Committee |  | 87,800 | 112,320 | 795,000 | 995,120 | 125,780 | 855,000 | 68,711.61 |