# RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO COMMUNITY SERVICES COMMITTEE

Agenda Item No

meeting date: 	4 NOVEMBER 2008

title:	CAPITAL PROGRAMME 2008/09

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	LAWSON ODDIE

# 1	PURPOSE

1.1	To inform members of progress to date with the capital programme for this committee for the current financial year.

# 2	BACKGROUND

  - Full Council approved the 5 year capital programme for 2008/13 on 4 March 2008.

  - At the Annual Council Meeting on 13 May 2008 the Terms of Reference for each committee were agreed.  This has meant some changes regarding which committee’s capital schemes should be reported to.  For example Car Parking now falls within the functions for this committee rather that Planning and Development.  The Capital Programme has now been revised to reflect these changes.

- 2008/09 SCHEMES

  - The programme for the year consists of schemes slipped from 2007/08 and also new schemes approved as part of the council’s 5 year capital programme.

  - Annex 1 shows the full programme by scheme along with the budget and expenditure to date.

  - Responsible officers have been asked to update the capital evaluation sheets to give an indication of progress with their schemes.  These are attached at Annex 2.

- CONCLUSION

  - Progress has been made on some schemes with others yet to commence.

  - Members should consider the report and make any comments regarding specific schemes felt necessary.

# LAWSON ODDIE

# TECHNICAL ACCOUNTANT

# CM9-08LO/AC

# 24 OCTOBER 2008

| Cost Centre | Schemes | BUDGET ANALYSIS | EXPENDITURE ANALYSIS |
| --- | --- | --- | --- |
|  |  | Original Estimate 2008/2009 £ | Slippage £ | Additional Approvals £ | Total Approved Budget £ | Total Expenditure to Date £ |
| BADWC | Badger Well Water Culvert Collapse |  | 8,830 |  | 8,830 | 0 |
| BPSCT | Brungerly Park Sculpture Trial |  | 1,450 | 10,900 | 12,350 | 528 |
| BRPIN | Brungerly Park Footpath Investigative Work |  |  | 3,000 | 3,000 | 0 |
| CALOP | Calderstones Open Space | 75,000 |  |  | 75,000 | 4,429 |
| CARPH | Car Parks Rolling Programme slippage from prev years |  | 33,740 |  | 33,740 | 18,659 |
| CARPJ | Car Parks Rolling Programme 2008/09 | 41,200 |  |  | 41,200 | 3,393 |
| CSLOT | Castle Lottery scheme | 2,308,300 | -158,940 |  | 2,149,360 | 836,303 |
| EDCAF | Redevelopment of Edisford Café Site |  |  | 15,000 | 15,000 | 0 |
| FITRM | Relocate fitness room at LSC to Longridge Civic Hall |  | 214,600 |  | 214,600 | 165 |
| GFCYC | Gisburn Forest Park Cycling Trails | 12,000 | 8,000 |  | 20,000 | 0 |
| KEEPB | Repointing Internal & External Walls to Clitheroe Castle Keep | 84,400 |  | 10,000 | 94,400 | 0 |
| LROOF | Longridge Sports Centre Roof Retention | 1,380 |  |  | 1,380 | 0 |
| OUTEQ | Replacement of Outdoor Recreation Equipment | 10,000 |  |  | 10,000 | 3,338 |
| PCCHI | Refurbishment of Chipping Toilets |  | 12,350 |  | 12,350 | 0 |
| PCWHA | Funding towards Whalley Toilets | 50,000 |  | 20,000 | 70,000 | 0 |
| PLAYH | Improvements to children's play areas |  | 11,940 |  | 11,940 | 6,650 |
| PLAYJ | Improvements to children's play areas | 50,000 |  | 3,000 | 53,000 | 11,106 |
| POENE | Pool - Replace boiler and energy efficiency measures |  | 84,620 | -20,530 | 64,090 | 9,346 |
| POSTW | Replace Steel Windows to building at Ribblesdale Pool |  | 15,970 |  | 15,970 | 0 |
| RCOLT | Replace Refuse Collection Vehicle |  | 169,700 |  | 169,700 | 170,159 |
| REBIN | Recycling and Residual Waste Containers | 236,000 | 136,030 |  | 372,030 | 367,022 |
| RWFRL | Replace V052 FRL Dennis Refuse Vehicle | 180,000 |  |  | 180,000 | 0 |
| SYNCA | Add budget moved from 2007/08 - Longridge Sports Synthetic Pitch | 133,900 |  | 47,600 | 181,500 | 41,605 |
| WLIFT | Wheeled Bin Lifting Equipment | 40,000 |  |  | 40,000 | 0 |
|  | Total Community Services Committee | 3,222,180 | 538,290 | 88,970 | 3,849,440 | 1,472,703 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | BADWC |
| Name of Scheme | Badger Well Water Culvert Collapse |
| Officer Responsible | JOHN EDWARDS |
| Description of Scheme | To carry out necessary remedial works at Badger Well Water, Sabden due to Culvert Collapse. |
| Benefits of Scheme | To protect and enhance the environmental quality of our area |
| Project Timetable | Start Date | Jan 08 |
|  | Completion Date | Oct 08 |
|  | Any Other Key Dates | Description of Work |
|  |  | Restoration of Culvert collapse |
| Indication of any problems which may ultimately affect either the project timetable or final costs | An investigation has been carried out to establish land ownership, as the landowner is responsible for the repair under land drainage legislation. However a land registry search has returned information that the land in the vicinity of the culvert collapse is unregistered. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | BADWC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08: | £8,830 |  |
|  | Total Approved Budget for Scheme: | £10,000 |  |
| Summary | Expected Total Cost of Scheme: | £10,000 |  |
|  | Approved by Committee: | Policy & Finance |
|  | Date: |  |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 1,170 | 8,830 | 10,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  | 1,170 | 8,830 | 10,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End September 2007 | As reported to community committee. Property flooding has occurred in Sabden. This scheme is necessary to carry out identified works and reduce the risk of further flooding from Badger Well Water. |
| End June 2008 | No progress since January 2008 due to other commitments but anticipated completion is Oct 2008. |
| End Sept 2008 | No further progress. Anticipated completion date is now December 2008 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | BPSCT |
| Name of Scheme | REPLACEMENT OF BRUNGERLEY SCULPTURE TRAIL |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | Replace public art pieces in Brungerley Park |
| Benefits of Scheme | Improve environment of park |
| Project Timetable | Start Date | April 2003 |
|  | Completion Date | March 2009 |
|  | Any Other Key Dates | Description of Work |
|  | Develop annual projects to replace one sculpture each year for the duration of the project |
| Indication of any problems | None, although each piece will rely on a partnership between community groups and artists |

| External Grants Rec'd/to be received Brungerly Park Sculpture Trail Grant from Market Towns Initiative 12,000 LCC - Brungerly Park Sculpture Trail Grant 4,500 LCC in 2008/9 5,700 Lancashire Wildlife Trust (in 08/09) 5,200 27,400 |
| --- |
| Financial | Slippage from 2007/08: | £1,450 |  |
|  | Add grant funding to be received for project in 08/09: | £10,900 |  |
|  | Budget for current year: | £12,350 |  |
|  | Expected Total (Gross) Cost of Scheme: | £48,216 |  |
|  | Approved by Committee: | Council |
|  | Date: | 4 March 2003 |
|  | Minute Ref: |  |
| Expenditure Analysis |  | Actual Expenditure 2003/04 £ | Actual Expenditure 2006/07 £ | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Cost of Scheme £ |
|  | Cost of Work | 110 | 22,586 | 13,170 | 12,350 | 48,216 |
|  | Other Costs |  |  |  |  |  |
|  | TOTAL | 110 | 22,586 | 13,170 | 12,350 | 48,216 |

|  |  |  |  |  | Cost Centre | BPSCT |
| --- | --- | --- | --- | --- | --- | --- |
| End August 2003 | Potential to expand trail. External funding is being explored before project is started. Still able to implement original timetable. |
| End Dec 2003 | Work still being carried out on project details. |
| End June 2004 | Waiting to see if our investment can be matched through money within the Market Towns Initiative to provide an enhanced scheme. |
| End Nov 2004 | As above, however need to set a deadline with Clitheroe the Future to determine whether an enhanced scheme is possible otherwise Ribble Valley to run its own scheme early next year. Due to this suggest money moved to 2005/06. |
| End June 2005 | In final stages of securing match funding. Will shortly be commencing scheme. Artist to start work. |
| End Sept 2005 | Awaiting to confirm funding via Clitheroe the Future. Sent out initial expressions of interest for commissions for local artist to start the work. |
| End Dec 2005 | Work to start January 2006. |
| End March 2006 | Problems in delay in securing matched funding via Clitheroe The Future. Just heard that we have £12,000 and so are able to start someone. Artists have been commissioned but this will mean that the bulk of the expenditure will be in 2006/07. |
| End Sept 2006 | Sculptures being made for 2006-07 expenditure for installation from Dec – March. |
| End Dec 2006 | Plan to install sculptures for end March |
| End Sept 2007 | Four new sculptures installed and one to be installed in October 07 to complete Phase 1. Match funding for Phase 2 from LCC Arts Unit and Wildlife Trust. Brief for artists now released and artist’s selection by end of October. Installation from Nov – March 08 for 2007/08 expenditure. |
| End June 2008 | Installation of 6 new sculptures by Dec 08. Delay due to artists kiln scorching original pieces. Julie Ann Seaman piece installed early 2008. Phase 3 brief to incorporate signage, map, leaflet production. Brief to be sent by Dec 2008. Additional Funding to be received in 2008/09 of £5,700 from LCC and £5,200 already received in April 2008 from Lancs Wildlife Trust. |
| End Sept 2008 | Currently working to the previously stated deadline. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | BRPIN |
| Name of Scheme | Brungerly Park Footpath Investigation |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Desktop study and borehole survey to collapsed footpath |
| Benefits of Scheme | Ultimately potential reopening of closed section of Brungerly Park footpath, |
| Project Timetable | Start Date | Sept 2008 |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
|  |  | External funding options be investigated |
| Indication of any problems which may ultimately affect either the project timetable or final costs |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose |  |
| What are the revenue implications of the scheme? |  |

|  |  |  |  |  |  | Cost Centre | BRPIN |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £3,000 |  |
| Summary | Expected Total Cost of Scheme: | £3,000 |  |
|  | Approved by Committee: | Policy & Finance |
|  | Date: |  |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 3,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 3,000 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2008 |  |
| End Sept 2008 | Site investigation work has now been completed and the results are now awaited from Lancashire County Council |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CALOP |
| Name of Scheme | Calderstones Open Space |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Development of open space and woodland area for recreation purposes. |
| Benefits of Scheme | Improved facilities for the benefit of residents of estate |
| Project Timetable | Start Date | June 2008 |
|  | Completion Date | March 2010 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Contamination of land and uncovering of underground structures. Weather conditions. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Groundwork are being used to help prepare the scheme and carry out consultation with the residents. Some work will be carried out by our own staff. |
| What are the revenue implications of the scheme? | There will be new facilities and equipment that will need to be maintained in the future. |

|  |  |  |  |  |  | Cost Centre | CALOP |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £75,000 |  |
| Summary | Expected Total Cost of Scheme: | £75,000 |  |
|  | Approved by Committee: | Policy & Finance |
|  | Date: |  |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 54,300 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  | 18,700 |
|  | Internal Salaries |  |  |  |  | 2,000 |
|  | TOTAL |  |  |  |  | 75,000 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2008 | Groundwork appointed to prepare Woodland Management Plan, carry out consultation with residents our scheme details and bring in additional funding. |
| End Sept 2008 | Consultation with residents is underway following preparation of a draft scheme by Groundwork based on previous household survey results. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CARPH |
| Name of Scheme | CAR PARKS ROLLING PROGRAMME SLIPPAGE FROM 2005/06 and 2006/07 |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Improvements to car park at Chipping |
| Benefits of Scheme | Housing and public car park which meets the expectations of those using it and which meets nationally agreed standards. |
| Project Timetable | Start Date | February 2007 |
|  | Completion Date | September 2008 |
|  | Any Other Key Dates | Description of Work |
|  |  | Refurbishment of car park including installation of P&D equipment |
| Indication of any problems which may ultimately affect either the project timetable or final costs | We have yet, despite exhaustive efforts to do so, to complete the negotiation regarding a new base for the car park and toilets at Chipping. All delay is due to the Trustees. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes, provided the lease is sorted soon. |
| What are the revenue implications of the scheme? | Assuming that the introduction of charging for parking on this car park follows the improvement works there will be additional parking revenue generated. |

|  |  |  |  |  |  | Cost Centre | CARPH |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08 (to incl slippage from CARPI): | £33,740 |  |
| Summary | Expected Total Cost of Scheme: | £63,342 |  |
|  | Approved by Committee: | Council |
|  | Date: | 1 March 2005 |
|  | Minute Ref: |  |
| Expenditure Analysis |  | Actual Expend 2005/06 £ | Actual Expend 2006/07 £ | Actual Expend 2007/08 £ | Expected Expend 2008/09 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work | 1,455 | 16,672 | 3,390 | 33,740 | 55,257 |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries | 6,667 | 376 | 1,042 |  | 8,085 |
|  | TOTAL | 8,122 | 17,048 | 4,432 | 33,740 | 63,342 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End Oct 2006 | Several meetings have been held with the Trustees and/or their Agents to date and whilst there is an agreement is principle to lease the car park and toilets to the council we have get to receive any formal proposals in writing. All delays are as a consequence of the difficulties with the Trustees. Until they are fully resolved work will not get underway. |
| End Dec 2006 | Pay and Display introduced at Sabden car park. Works to be carried out at Bolton by Bowland car park including resurfacing shortly. |
| End June 2008 | Work has started on site with an anticipated completion of Sept 2008. |
| End Sept 2008 | All work complete and charging for parking started on Monday 13 October 2008. Awaiting the final account from the contractor for payment |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CARPJ |
| Name of Scheme | CAR PARKS ROLLING PROGRAMME 2008/09 |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Improvements to Car Parks |
| Benefits of Scheme | To bring car parks to an acceptable standard |
| Project Timetable | Start Date | June 2008 |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
|  |  | Various improvements to car parks |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? |  |

|  |  |  |  | Cost Centre | CARPJ |
| --- | --- | --- | --- | --- | --- |
| Summary | Expected Total Cost of Scheme: | £41,200 |  |
|  | Approved by Committee: | Council |
|  | Date: | 4 March 2008 |
|  | Minute Ref: |  |
| Expenditure Analysis |  | Expected Expenditure 2008/09 £ | Total Cost of Scheme £ |
|  | Land |  |  |
|  | Cost of Work | 41,200 | 41,200 |
|  | Other Costs |  |  |
|  | External Fees |  |  |
|  | Internal Salaries |  |  |
|  | TOTAL | 41,200 | 41,200 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2008 | Works to chipping car park will be funded from the slippage on CARPH with the balance being met from this budget. The remaining funds will be used to finance other improvements to car parks across the borough by the end of the financial year. |
| End Sept 2008 | Approximately £13,000 of this budget has been spent as part of the cost of the refurbishment of Chipping car park. The balance (£28,000) will be spent within 2008/2009 on upgrading other car parks, which are likely to be North Street, Clitheroe and Berry Lane (Barclay Road), Longridge. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CSLOT |
| Name of Scheme | CASTLE LOTTERY SCHEME |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | Redevelopment of Castle Museum and associated buildings into all-weather visitor attraction |
| Benefits of Scheme | Future sustainability of Museum Sound Archive and Parks Buildings |
| Project Timetable | Start Date | September 2007 |
|  | Completion Date | Spring 2009 |
|  | Any Other Key Dates | Description of Work |
|  | 8th March | - HLF Panel Date |
| Indication of any problems which may ultimately affect either the project timetable or final costs | A negative decision from HLF |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | No, external Project Managers have been appointed |
| What are the revenue implications of the scheme? | To be confirmed through negotiation with county museum service |
| Scheme Funding | Heritage Lottery Fund 1,835,260 Ribble Valley existing Capital Programme 176,160 Clitheroe The Future NWDA 250,000 NWDA 2nd grant…… ……………………… … 305,000 SITA 135,000 Private Sector Sponsorship 100,000 Friends of Clitheroe Castle 16,245 Clitheroe Town Council 5,000 2,822,665 Cost of Scheme 3,275,319 Shortfall 452,654 RVBC extra funding (600k – 305k to fund … -295,000 other schemes re NWDA grant) Shortfall still to find 157,654 |

|  |  |  |  |  |  | Cost Centre | CSLOT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £2,308,300 |  |
|  | Slippage from 2007/08: | -£158,940 |  |
| Summary | Budget for year: | £2,149,360 |  |
|  | Total cost of scheme: | £3,275,319 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Expected Expenditure 2009/10 £ | Total £ |
|  | Construction Works | 762,943 | 1,574,164 |  | 2,337,107 |
|  | Exhibition Fit-Out |  | 379,500 |  | 379,500 |
|  | Other Fit-Out |  | 19,725 | 52,198 | 71,923 |
|  | Professional Fees | 253,779 | 142,782 |  | 396,561 |
|  | RVBC Supply Items |  |  | 4,270 | 4,270 |
|  | Decant & Storage | 28,887 | 5,571 |  | 34,458 |
|  | Phase 1 expenditure /promotional activities | 7,968 |  | 8,532 | 16,500 |
|  | Internal Salaries | 7,360 | 27,640 |  | 35,000 |
|  | TOTAL | 1,060,937 | 2,149,382 | 65,000 | 3,275,319 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End Sept 2007 | Main contract let and due for completion November 2008. Scheme completion estimated Spring 2009. |
| End June 2008 | Overall project within original timescale |
| End Sept 2008 | Overall project still within original timescales. Work packages for fit-out have been tendered and now ready to issue contracts |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | EDCAF |
| Name of Scheme | REDEVELOPMENT OF EDISFORD CAFÉ SITE TO CREATE THREE RENTAL PLOTS |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Demolition of the existing Edisford Café building and the provision of three plots for mobile catering units to trade from |
| Benefits of Scheme | New and more catering facilities at Edisford could enhance the site and encourage more visitors to the area |
| Project Timetable | Start Date |  |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Weather conditions; Hazardous materials found during demolition; Ground conditions; Lack of interested parties in providing the service |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | An income will be generated from renting each of the plots |

|  |  |  |  |  |  | Cost Centre | EDCAF |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £15,000 |  |
| Summary | Expected Total Cost of Scheme: | £15,000 |  |
|  | Approved by Committee: | Policy & Finance |
|  | Date: | 23 September 2008 |
|  | Minute Ref: | 438 |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 15,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 15,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End Sept 2008 | The lessee vacated the premises at the end of September 2008. Demolition of the existing building will be carried out during November 2008 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | FITRM |
| Name of Scheme | RELOCATE FITNESS ROOM AT LSC TO LONGRIDGE CIVIC HALL |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | Construction of permanent gym facility at Longridge Civic Hall |
| Benefits of Scheme | To provide better access to facilities and improve sustainability of Civic Hall |
| Project Timetable | Start Date | Dec 2007 |
|  | Completion Date | May 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | The possibility of a permanent replacement over the next 12 months is being explored as this will generate better value for money. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Being worked up as part of service planning process |

|  |  |  |  |  |  | Cost Centre | FITRM |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08: | £214,600 |  |
| Summary | Expected Total Cost of Scheme: | £214,600 |  |
|  | Approved by Committee: | Full Council & Spec P&F |
|  | Date: | 6 March 2007 & 29 Aug 07 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 214,600 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 214,600 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End September 2007 | Joint scheme for construction of children’s centre and gym agreed by Policy and Finance committee. Funding as follows: (Total Cost £214,600) Current capital budget £18,600 Civic Hall Grant £100,000 Transferred from LSC reception capital budget £54,400 PCT Grant £10,000 Sport England £20,000 LSP £11,600 £214,600 |
| End June 2008 | Sport England and LSP funding confirmed. Project on track for mid Sept completion. |
| End Sept 2008 | Handover confirmed for 8 October 2008 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | GFCYC |
| Name of Scheme | GISBURN FOREST PARK CYCLING TRAILS |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Financial support to major improvement scheme |
| Benefits of Scheme | Improved facilities for cyclists and tourism generation |
| Project Timetable | Start Date | April 2007 |
|  | Completion Date | January 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Development of agreed schemes and approval from other partners and funding streams |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | GFCYC |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Slippage from 2007/08: | £8,000 |  |
| Financial | Approved Budget for Current Year: | £12,000 |  |
| Summary | Expected Total Cost of Scheme: | £20,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 20,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 20,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Discussions ongoing with other funding partners |
| End September 2007 | Match funding is currently being secured and commencement of the scheme is expected March 2008. The total amount in the budget will be spent in the 2008/09 financial year alongside a further £160,000 from other funding. |
| End June 2008 | Work on site to extend and improve the mountain bike trails is well underway and an invoice is awaited for the 2007/08 contribution of £8,000. |
| End September 2008 | Invoice for full contribution is expected shortly. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | KEEPB |
| Name of Scheme | CASTLE KEEP IMPROVEMENTS – PHASE 2 |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme |  |
| Benefits of Scheme | Improvements to keep |
| Project Timetable | Start Date |  |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
|  |  | Pointing and repairs to keep retaining wall |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Tenders are above the budget allocation. Project may be reduced to be delivered within the budget. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |
| Funding | £10,000 secured through aggregates levy fund. |

|  |  |  |  |  |  | Cost Centre | KEEPB |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £84,400 |
|  | Additional Approval (Funding from Aggregates Levy Fund): | £10,000 |
| Summary | Expected Total Cost of Scheme: | £94,400 |
|  | Approved by Committee: |  |
|  | Date: |  |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Total Cost of Scheme £ |
|  | Land |  |  |  |
|  | Cost of Work |  |  | 94,400 |
|  | Retention (show separately) |  |  |
|  | Other Costs |  |  |  |
|  | External Fees |  |  |  |
|  | Internal Salaries |  |  |  |
|  | TOTAL |  |  | 94,400 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2008 | £10,000 secured through aggregates levy fund Tender returns being analysed with intention of work being carried out within current museum construction contract. |
| End Sept 2008 | Project due to be completed by the end of December 2008 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | LOCHG |
| Name of Scheme | GRANT AID TO LONGRIDGE ACTION GROUP FOR CIVIC HALL |
| Officer Responsible | CHRIS HUGHES |
| Description of Scheme | Improvements to reception/entrance |
| Benefits of Scheme | Improving access and better use of space |
| Project Timetable | Start Date |  |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Final costs will not change but timetable is reliant on Longridge Action Group signing their lease |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | LOCHG |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08: | £90,000 |  |
|  | Expected Total Cost of Scheme: | £90,000 |  |
|  | Approved by Committee: | Council |
|  | Date: | 2 March 2005 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |
|  | Cost of Work |  |  |  | 90,000 |
|  | Retention (show separately) |  |  |  |
|  | Other Costs |  |  |  |  |
|  | External Fees |  |  |  |  |
|  | Internal Salaries |  |  |  |  |
|  | TOTAL |  |  |  | 90,000 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| June 2005 | Awaiting receipt of proposal from Longridge Action Group. |
| End Sept 2005 | Still awaiting receipt of proposal from Longridge Action Group. |
| End Dec 2005 | Still awaiting receipt of proposal from Longridge Action Group. |
| End Sept 2006 | Designs for new reception being produced |
| End Dec 2006 | Designs still underway for new reception. |
| End September 2007 | Will be used to part fund the re-location of the sports centre gym to the civic hall |
| End June 2008 | As above |
| End Sept 2008 | As above |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | OUTEQ |
| Name of Scheme | REPLACEMENT OF OUTDOOR RECREATION EQUIPMENT |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replace carpet and repair sub structure of artificial cricket wicket at Roefield Playing Fields, Clitheroe Replace goal posts on 13 football pitches |
| Benefits of Scheme | Community Strategy - Health and Well-being Corporate performance and Improvement Plan - To make peoples lives safer and healthier |
| Project Timetable | Start Date |  |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Final costs will not change but timetable is reliant on Longridge Action Group signing their lease |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Possible grant aid from Football Association towards cost of new goal posts. |

.

|  |  |  |  |  |  | Cost Centre | OUTEQ |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved budget for current year: | £10,000 |
|  | Expected Total Cost of Scheme: | £21,000 |
|  | Approved by Committee: | Council |
|  | Date: | 4March 2008 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  | Expected Expenditure 2008/09 £ | Expected Expenditure 2009/10 £ | Total £ |
|  | Land |  |  |  |  |
|  | Cost of Work |  | 10,000 | 11,000 | 21,000 |
|  | Retention (show separately) |  |  |  |
|  | Other Costs |  |  |  |  |
|  | External Fees |  |  |  |  |
|  | Internal Salaries |  |  |  |  |
|  | TOTAL |  | 10,000 | 11,000 | 21,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2008 | New cricket wicket to be carried out week commencing 7 July 2008. Replacement goal posts on order and to be installed ready for start of new football season. |
| End Sept 2008 | The extremely poor weather delayed the laying of the base for the cricket wicket until after the end of the season and led to the cancellation of some scheduled games. The base is now laid and the carpet will be laid prior to the start of the 2009 season. The new goal posts were all in place for the start of the 2008/2009 season. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PCCHI |
| Name of Scheme | REFURBISHMENT OF CHIPPING TOILETS |
| Officer Responsible | SYD CHAMLEY |
| Description of Scheme | Refurbishment of toilets in June with similar schemes recently undertaken |
| Benefits of Scheme | Improvement of facilities for customers. DDA compliance |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | 31 March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Scheme anticipated to overspend due to increase in materials costs since original tender |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | PCCHI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08: | £12,350 |  |
| Summary | Expected Total Cost of Scheme: | £90,300 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 76,100 | 12,350 | 88,450 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs – Electrical |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  | 1,853 |  | 1,853 |
|  | TOTAL |  |  | 77,953 | 12,350 | 90,303 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Scheme initially drawn up 4 years ago requires slight amendments before going out to tender. Lease needs finalising Graham Jagger leading on this no indication of any problems |
| End September 2007 | Work commenced September 2007. |
| End June 2008 | Scheme complete. Retention outstanding will be due in March 2009. Will be a saving on the scheme of approximately £10,000. |
| End Sept 2008 | Scheme complete. Retention outstanding will be due in March 2009. Will be a saving on the scheme of approximately £10,000. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PCWHA |
| Name of Scheme | FUNDING TOWARDS RECONSTRUCTION OF WHALLEY TOILETS |
| Officer Responsible | JOHN HEAP |
| Description of Scheme | Rebuilding of Whalley toilets in conjunction with Whalley Parish Council |
| Benefits of Scheme | Improvement of facilities for customers DDA compliance |
| Project Timetable | Start Date |  |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | No indication of any issues but scheme is being undertaken by Parish Council so scheme not under direct control of Local Authority |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | PCWHA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £50,000 |  |
| Summary | Additional Approval: | £20,000 |  |
|  | Expected Total Cost: | £70,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 70,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 70,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Initial plans drawn up by architects acting for Parish Council, requirements of RVBC have been incorporated into design |
| End September 2007 | Architect producing tender documents on behalf of Whalley Parish Council |
| End June 2008 | Policy and Finance committee agreed to increase the council’s contribution to the Parish Council’s scheme by £20,000 to £70,000. |
| End Sept 2008 | Construction commenced on site. Project management on behalf of Parish Council to be provided by architect. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PLAYH |
| Name of Scheme | IMPROVEMENTS TO CHILDREN’S PLAY AREAS 2007/2008 |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replacement of worn out equipment and general improvements |
| Benefits of Scheme | Quality play areas for children |
| Project Timetable | Start Date | April 2007 |
|  | Completion Date | March 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | PLAYH |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08: | £11,940 |  |
| Summary | Expected Total Cost of Scheme: | £50,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 36,951 | 11,940 | 48,891 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs - Electrical |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  | 1,107 |  | 1,107 |
|  | TOTAL |  |  | 38,058 | 11,940 | 49,998 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | With increase in budget reactive maintenance to children’s play areas can now begin again as well as continuation with replacement and improvement programme |
| End September 2007 | £15k set aside for maintenance due to no revenue budget for such work and £35k for new/replacement equipment. Agreed scheme with Whalley Play Area Group regarding Proctors Field play area for which £5k of capital budget will be used. £17.5k spent on safety surfacing at Highmoor Park Clitheroe. Quote awaited for all necessary maintenance work following insurance company setting out defects on all play areas. |
| End June 2008 | Equipment repairs carried out satisfactorily. |
| End Sept 2008 | All work is now complete |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | PLAYJ |
| Name of Scheme | IMPROVEMENTS TO CHILDREN’S PLAY AREAS |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Replacement of worn out equipment and general improvements |
| Benefits of Scheme | Quality play areas for children |
| Project Timetable | Start Date | April 2008 |
|  | Completion Date | March 2009 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | PLAYJ |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Original Approved Budget: | £50,000 |  |
|  | Additional Approval (Funding - Longridge Town Council) | £ 3,000 |  |
| Summary | Expected Total Cost of Scheme: | £53,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 4 March 2008 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Total Expenditure £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 53,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs – Electrical |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 53,000 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2008 | Part of the budget is being spent on the reintroduction of routine safety inspections and essential repairs. Work is currently underway to improve pedestrian access to and around the play equipment at Proctors Field, Whalley. |
| End Sept 2008 | £15,000 spent on repairs, maintenance and inspections, £38,000 spent on improvements at Proctors Field play area at Whalley |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | POENE |
| Name of Scheme | ENERGY EFFICIENCY MEASURES TO RIBBLESDALE POOL |
| Officer Responsible | SYD CHAMLEY |
| Description of Scheme | Numerous measure to be undertaken at Ribblesdale Pool to improve energy efficiency |
| Benefits of Scheme | Improved energy efficiency, lower carbon footprint |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | March 2009 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Feasibility of wind turbine |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Reduced running costs |

|  |  |  |  |  |  | Cost Centre | POENE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08: | £84,620 |  |
|  | Less Overspend on Pool Boiler Scheme: | -£20,530 |  |
| Summary | Budget for Year: | £64,090 |  |
|  | Expected Total Cost of Scheme: | £83,996 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 18,353 | 64,090 | 84,443 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs - Electrical |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  | 1,523 |  | 1,523 |
|  | TOTAL |  |  | 19,876 | 64,090 | 83,996 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Limited progress due to sickness absence of Principle Building Surveyor |
| End Sept 2007 | Planning permission obtained for wind turbine. However feasibility study being carried out on average wind speed for site. Currently indicating that wind turbine is not feasible. Due to shortfall of boiler replacement scheme (PBOIL) intention is to utilise this scheme to supplement boiler replacement. Funding currently being sought for contribution towards solar hot water panels. |
| End June 2008 | £20,500 overspend on Pool Boiler scheme in 2007/08 offset against slippage on this scheme. In addition expenditure of £8,700 in 08/09 re works to air conditioning also charged to this scheme. Investigation into possibility of solar panels to be carried out. |
| End Sept 2008 | Continuing to investigate the possibility of the use of solar panels. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | POSTW |
| Name of Scheme | REPLACE STEEL WINDOWS TO BUILDING AT RIBBLESDALE POOL |
| Officer Responsible | SYD CHAMLEY |
| Description of Scheme | Replace old and inefficient steel framed windows at Ribblesdale Pool |
| Benefits of Scheme | Improve look of building and contribute to lower maintenance better energy efficiency |
| Project Timetable | Start Date | 1 April 2007 |
|  | Completion Date | February 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | POSTW |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08: | £15,970 |  |
| Summary | Expected Total Cost of Scheme: | £36,400 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 6 March 2007 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 20,426 | 15,970 | 36,396 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs – Electrical |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  | 20,426 | 15,970 | 36,396 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2007 | Quotes to be obtained by end of May 2007 |
| End September 2007 | Specification clarified. Quotes to be received by 19 October 2007. Work to be carried out during boiler replacement closedown. |
| End June 2008 | Work carried out during December/January closure. Scheme complete. Saving on scheme. |
| End Sept 2008 | Work carried out during December/January closure. Scheme complete. Saving on scheme. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RCOLT |
| Name of Scheme | REPLACE REFUSE COLLECTION VEHICLE |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | To replace a vehicle on expiry of its lease |
| Benefits of Scheme | To have a vehicle fleet fit for purpose |
| Project Timetable | Start Date |  |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Manufacture and delivery period depending on type and style of vehicle chosen |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | Costs included our existing budgets |

|  |  |  |  |  |  | Cost Centre | RCOLT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08: | £169,700 |  |
| Summary | Expected Total Cost of Scheme: | £169,700 |  |
|  | Approved by Committee: | Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: | 755 |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Vehicle |  |  |  |  | 169,700 |
|  | Retention (show separately) |  |  |  | 0 |
|  | Other Costs |  |  |  |  | 0 |
|  | External Fees |  |  |  |  | 0 |
|  | Internal Salaries |  |  |  |  | 0 |
|  | TOTAL |  |  |  |  | 169,700 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | A decision has yet to be taken on the type and style of vehicle(s) to be purchased. The work being undertaken in respect of re-designing the collection service will influence the decision on the vehicle(s) bought. |
| End Sept 2006 | The delay in purchasing a new refuse collection vehicle is because decisions have yet to be made about how and when to extend the three-stream refuse collection and recycling service. The type of vehicle will depend on the style of service finally adopted following the evaluation of the trial operation. N313 SWK is to be purchased from lease company to be used as a spare vehicle. |
| End September 2007 | Replacement vehicle ordered following tendering exercise using YPO framework contract. Delivery due February 2008. Cost for all 3 vehicles in programme expected to be under budget by £4,200 as reported to community committee |
| End June 2008 | Vehicle has been returned to manufacturers for modifications to meet the requirements of the specification and is expected to be back in service from week commencing 14 July 2008. |
| End Sept 2008 | Vehicle is in use but is the subject of an engineering inspection by the Freight Transport Association before the final account is to be paid. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | REBIN |
| Name of Scheme | RESIDUAL WASTE BINS – THREE STREAM WASTE COLLECTION |
| Officer Responsible | PETER McGEORGE |
| Description of Scheme | The provision of 140 litre wheeled bins for three stream collection to be introduced borough wide in 2 phases 2007/08 and 2008/09 |
| Benefits of Scheme | The provision of wheeled bins will complete investment for three stream collection borough wide and improve recycling performance |
| Project Timetable | Start Date | Phase 1 completed March 2006 Phase 2 should be completed by Sept 07 Phase 3 should be completed in 2008 |
|  | Completion Date | 2008 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Public participation. Change to cost sharing arrangement. Downturn in market value/price. Production schedules for both vehicles and wheeled bins |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose What are the revenue implications of the scheme? | For Phase 2 will need an additional split bodied vehicle (incl. in Capital Programme £190,000) For Phase 3 will need extra crew (driver + 2 operatives) Recycling credits Phase 2 1,352 x £42.87 = £57,960.24 Phase 3 2,704 x £44.16 = £119,408.64 |

|  |  |  |  |  |  | Cost Centre | REBIN |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Slippage from 2007/08: | £136,030 |  |
| Financial | Original Budget for year: | £236,000 |  |
|  | Total Budget for Year: | £372,030 |  |
| Summary | Expected Total Cost of Scheme: | £815,000 |
|  | Approved by Committee: | Policy & Finance |
|  | Date: | 24 January 2006 |
|  | Minute Ref: |  |
| Expenditure Analysis |  | Actual Expenditure 2005/06 £ | Actual Expenditure 2006/07 £ | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |
|  | Other Costs | 80,500 | 0 | 362,572 | 372,030 | 815,102 |
|  | External Fees |  |  |  |  |  |
|  | TOTAL | 80,500 | 0 | 362,572 | 372,030 | 815,102 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 06 | Bins due to be delivered to households this week. |
| End Sept 2006 | Expenditure completed in 2005/06 with purchase of wheeled bins and introduction of new three-stream collection system to target round. Target round still being evaluated. Delay in development of Waste Transfer facility has affected programme for expansion of wheeled bin delivery. It is now proposed to commence expansion Mid 2007 therefore 2006/07 Budget needs to be included in 2007/08 expenditure. |
| End March 2007 | In January 2007 Community Committee decided to extend the three-stream collection borough wide in two phases. (Phase 2 and 3). Phase 2 to commence as soon as possible and Phase 3 in 2008 we are currently preparing tenders for bins and vehicles. |
| End September 2007 | Community Committee opted to include chips in wheeled bins. Full assessment of properties identified over 97% suitable for wheeled bins. Bins ordered for Phase 2 and 3. Delivery Phase 2 – 1 October 2007 and retrofitting existing bins in November 2007. Total cost £90,100 over budget as reported to September Community Committee. Cost £734,595, Budget £644,500. An extra £90,100 has been added to the 5year Capital Programme in 2008/09. |
| End June 2008 | Currently completing roll out of final phase. Expect final invoice for bins and delivery to be within budget. Scheme will be complete when outstanding bins delivered to properties. No budget provision exists however for replacement bins when stolen or damaged. More significantly the future 5 year capital programme needs to include provision for replacement bins in the longer term. |
| End Sept 2008 | Roll out completed. There are outstanding issues with the supplier and as a result we are withholding payment on invoices to the value of £105,000. However, it is anticipated that these issues will be fully resolved by mid November 2008. |
| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RWFRL |
| Name of Scheme | REPLACE REFUSE VEHICLE – V052 FRL |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme |  |
| Benefits of Scheme |  |
| Project Timetable | Start Date | April 2008 |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose |  |
| What are the revenue implications of the scheme? |  |

|  |  |  |  |  |  | Cost Centre | RWFRL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £180,000 |  |
| Summary | Expected Total Cost of Scheme: | £180,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 4 March 2008 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 180,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 180,000 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2008 | Vehicle received and in use but discussions are underway with manufacturers prior to invoices being paid. |
| End Sept 2008 | The vehicle is now in use |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | SYNCA |
| Name of Scheme | LONGRIDGE SPORTS CENTRE – REPLACE CARPET ON SYNTHETIC PITCH |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme | Contribution to Lancashire County Council (joint use) to replacement of defective playing surface |
| Benefits of Scheme | Health and safety |
| Project Timetable | Start Date | Summer 2006 (grant dependable LCC) Summer 2007 if no grant |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Scheme is joint use and 50% : 50% funded between school and RVBC. May be delayed until summer 2007 if grant from LCC not available to school. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes. LCC will manage scheme. |
| What are the revenue implications of the scheme? | Future maintenance as pitch wears as existing. |

|  |  |  |  |  |  | Cost Centre | SYNCA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2007/08: | £133,900 |  |
|  | Additional Approval: | £47,600 |  |
| Summary | Expected Total Cost of Scheme: | £181,500 |  |
|  | Approved by Committee: | Council |
|  | Date: | 28 February 2007 |
|  | Minute Ref: | 755 |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 181,500 |
|  | Retention (show separately) |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 181,500 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | See problems. |
| End Sept 2006 | As previous awaiting LCC commitment to scheme – expenditure unlikely 07. |
| End Dec 2006 | As end September 2006. |
| End March 2007 | Progress as above scheme budget moved to 2007/08. |
| End Sept 2007 | As above. |
| End June 2008 | Tenders received and discussions underway with school regarding which option is financially viable. Work programmed to be done during school holidays. Awaiting written confirmation form school before appointment of contractor. |
| End Sept 2008 | Works complete and to be handed over to the school and Lancashire County Council shortly. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | WLIFT |
| Name of Scheme | WHEELED BIN LIFTING EQUIPMENT |
| Officer Responsible | GRAHAM JAGGER |
| Description of Scheme |  |
| Benefits of Scheme | To support the introduction of three stream refuse collection |
| Project Timetable | Start Date | April 2008 |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? |  |

|  |  |  |  |  |  | Cost Centre | WLIFT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £40,000 |  |
| Summary | Expected Total Cost of Scheme: | £40,000 |  |
|  | Approved by Committee: | Council |
|  | Date: | 4 March 2008 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 40,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 40,000 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2008 | Quotation has been obtained for a new bin lift and associated equipment. Decision has yet to be taken as to whether to go ahead with this proposal. |
| End Sept 2008 | Equipment on order for fixing to vehicle VX53 TZJ and to be used on spare vehicle to cover for breakdown and when others are being serviced. The project will be completed before Christmas 2008. |

# Text boxes

INFORMATION

Annex 1

Annex 2