RIBBLE VALLEY BOROUGH COUNCIL

INFORMATION

REPORT TO POLICY AND FINANCE COMMITTEE

Agenda Item No

meeting date: 	18 NOVEMBER 2008

title:	CAPITAL MONITORING 2008/09

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	LAWSON ODDIE

- PURPOSE

  - To update members with progress on the Capital Programme for this committee for the current financial year.

- BACKGROUND

  - The Capital Programme for 2008/09 was approved in March 2008.  In the March cycle of committee meetings capital reports were considered which included capital evaluation statements giving full details of all new schemes for the forthcoming year.

- 2008/09 SCHEMES

  - The programme for the year consists of schemes slipped from 2007/08 and also new schemes approved as part of the council’s 5 year capital programme.

  - Annex 1 shows the full programme by scheme along with the budget and expenditure to date.

  - Responsible officers have been asked to update the capital evaluation sheets to give an indication of progress with their schemes.  These are attached at Annex 2.

  - The creation of new Member’s rooms on Level D of the council offices is an additional scheme shown on the summary for this committee. This will be funded from savings on other capital schemes within this current financial year’s programme.

- CONCLUSION

  - There are three schemes for works to the Civic Suite, some of which are slippage from 2007/08.  Following the housing stock transfer Syd Chamley, the Council’s Electrical Services Engineer, is now looking after these schemes.

  - The largest capital scheme for this committee is obviously the Roefield loan. As reported to Policy & Finance Committee, the council has now agreed to a joint scheme to extend the Leisure Centre and provide new council changing facilities for the Edisford sports pitches.

  - At six months through the financial year only approximately 2% of the budget has actually been expended. However, there are a number of scheme that had been completed and invoices had not yet been received from contractors.

- RECOMMENDED THAT COMMITTEE

  - Review the capital evaluation sheets to consider the progress made and any comments members may wish to make.

LAWSON ODDIE

- TECHNICAL ACCOUNTANT

- PF47-08/LO/AC

28 OCTOBER 2008

| Cost Centre | Schemes | BUDGET ANALYSIS |  |  |  | EXPENDITURE ANALYSIS ANNEX 1 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Original Estimate 2008/2009 £ | Slippage £ | Additional Approvals £ | Total Approved Budget £ | Total Expenditure to Date £ |
| CIVBO | Civic Suite - Energy Efficiency Replace Gas fired boilers | 98,800 |  |  | 98,800 | 9,600 |
| CIVHS | Civic Suite - DDA & Impts to stored water system |  | 14,520 |  | 14,520 | 6,863 |
| CIVLF | Civic Suite - Energy Efficiency Replace Light Fittings | 10,300 |  |  | 10,300 | 0 |
| EGIIV | E Government Initiative |  | 38,510 |  | 38,510 | 114 |
| LEADR | Creation of Member’s Rooms on Level D |  |  |  |  | 813 |
| ROEFL | Add budget moved from 2007/08 - Roefield Loan | 645,000 |  |  | 645,000 | 0 |
| SERVB | Computer Server & Bulk Printer Replacement | 8,000 |  |  | 8,000 | 0 |
|  | Total Policy & Finance Committee | 762,100 | 53,030 | 0 | 815,130 | 17,390 |

- ANNEX 2

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CIVBO |
| Name of Scheme | REPLACE BOILER & ENERGY EFFICENCY MEASURES – CIVIC SUITE |  |  |  |
| Officer Responsible | SYD CHAMLEY |  |  |  |
| Description of Scheme | - REPLACE EXISTING BOILERS (2) WITH MORE EFFICIENT BOILERS |  |  |  |
| Benefits of Scheme | Savings due to greater efficiency |  |  |  |
| Project Timetable | Start Date | August 2008 |  |  |
|  | Completion Date | Sept 2008 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  | July 2008 | Submission of tenders |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Tenders could come in higher than budget |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Savings due to greater efficiency |  |  |  |

|  |  |  |  |  |  | Cost Centre | CIVBO |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved Budget for Current Year: |  |  |  |  | £98,800 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £98,800 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 4 March 2008 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 98,800 | 98,800 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 98,800 | 98,800 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2008 |  | Tenders submitted and due to be returned late July 2008. Work to commence August 2008 and be completed by September 2008. |  |  |  |  |  |
| End Sept 2008 |  | Work is almost completed. Yet to complete work on the flue. Final snagging will take place at the end of October/beginning of November. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CIVHS |
| Name of Scheme | DDA AND HEALTH AND SAFETY WORKS TO CIVIC SUITE |  |  |  |
| Officer Responsible | SYD CHAMLEY |  |  |  |
| Description of Scheme | To install lift to allow access to first floor meeting rooms. Refurbish works to comply with DDA and remove Legionnaires risk from existing stored water system. Civic Suite – Lift The lift is necessary as no disabled access is available to the meeting rooms on the first floor or the public gallery. - Installing monitors within reception that transmit live pictures and sound from the council chamber have catered for access to the gallery. - The meeting rooms are however inaccessible for disabled people with walking difficulties attending meetings. This can include members of staff, members of the public, external auditors and members of the Council. - Regarding members of the Council the DDA has been amended in that members are now included within the Act and as such councils cannot discriminate against this group. ## Civic Suite – WCs - The WCs are included for inclusion as it was deemed that they are not really up to a sufficient standard (unlike offices) for the building they are held in. - The main issue however is that the WCs are served from a large water heater that stores hot water. This is defective at the moment and as such is potentially a Legionella bacteria source. The aim is to remove the heater and incorporate instantaneous water heaters therefore eliminating the Legionella risk. - During refurbishment water saving taps would be installed and an anti-slip floor covering. - The whole refurbishment would improve health and safety regarding the WCs. - The disabled WC does not comply with current best practice, building regulations and DDA regarding the equipment within it. |  |  |  |
| Benefits of Scheme | Health and safety improvements and compliance with current legislation |  |  |  |
| Project Timetable | Start Date | July 2006 |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None at this stage |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | £600 annual maintenance repairs to lift |  |  |  |

|  |  |  |  |  |  | Cost Centre | CIVHS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Slippage from 2007/08: |  |  |  |  | £14,520 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £45,005 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2006/07 £ | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  | 17,342 | 11,126 | 14,520 | 42,988 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Internal Salaries |  |  | 1,713 | 302 |  | 2,015 |
|  | TOTAL |  |  | 19,055 | 11,428 | 14,520 | 45,003 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Design work to lift to be commenced/revisited. |  |  |  |  |  |
| End Sept 2006 |  | WC work complete beginning October 2006 lift prices received September 2006 final approval on design October 2006. Work to commence January 2007 completion January 2007. |  |  |  |  |  |
| End Dec 2006 |  | Retention and final account outstanding for toilet work. Lift decision still being considered. Plan to commence before end of financial year. |  |  |  |  |  |
| End September 2007 |  | Lift installation planned for January 2008. |  |  |  |  |  |
| End June 2008 |  | Lift installed. Final invoice paid. Scheme complete. |  |  |  |  |  |
| End Sept 2008 |  | Scheme Completed |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CIVLF |
| Name of Scheme | ENERGY EFFICIENCY REPLACE LIGHT FITTINGS CIVIC SUITE |  |  |  |
| Officer Responsible | SYD CHAMLEY |  |  |  |
| Description of Scheme | - Review by external consultant of energy efficient improvements |  |  |  |
| Benefits of Scheme |  |  |  |  |
| Project Timetable | Start Date | June 2008 |  |  |
|  | Completion Date | February 2009 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Use of Consultant |  |  |  |
| What are the revenue implications of the scheme? |  |  |  |  |

|  |  |  |  |  |  | Cost Centre | CIVLF |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved Budget for Current Year: |  |  |  |  | £10,300 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £10,300 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 4 March 2008 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2008/09 £ | Total Expenditure £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 10,300 | 10,300 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 10,300 | 10,300 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2008 |  | Consultant has now carried out review of energy efficient potential improvements. Awaiting report. |  |  |  |  |  |
| End Sept 2008 |  | Currently waiting for quotations for the work. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | EGIIV |
| Name of Scheme | E-GOVERNMENT INITIATIVE – IEG4 – PHASE 2 |  |  |  |
| Officer Responsible | MARSHAL SCOTT |  |  |  |
| Description of Scheme | To introduce electronic methods of service delivery |  |  |  |
| Benefits of Scheme | Improved access to services |  |  |  |
| Project Timetable | Start Date | April 2005 |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Shortage of staff resources. The number of computer projects to be implemented. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Will be difficult given the Government’s deadlines for priority outcomes |  |  |  |
| What are the revenue implications of the scheme? | Not yet quantified but the Government believes there will be long-term savings from this initiative |  |  |  |

|  |  |  |  |  |  | Cost Centre | EGIIV |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Slippage from 2007/08: |  |  |  |  | £38,510 |  |  |  |  |  |
| Financial | Approved Budget for Current Year: |  |  |  |  | £38,510 |  |  |  |  |  |
|  | Total Budget: |  |  |  |  | £60,000 |  |  |  |  |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £50,005 |  |  |  |  |  |
|  | Approved by Committee: |  |  |  |  | Council |  |  |  |  |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |  |  |  |  |
|  | Minute Ref: |  |  |  |  |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2006/07 £ | Actual Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Expenditure £ |  |  |  |  |
|  | Land |  |  |  |  |  |  |  |  |  |  |
|  | Cost of Work |  |  | 6,773 | 4,722 | 38,510 | 50,005 |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |  |  |  |  |
|  | TOTAL |  |  | 6,773 | 4,722 | 38,510 | 50,005 |  |  |  |  |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |  |  |  |  |
| End June 2005 |  | The £150,000 IEG4 grant money will be funding both the e-Government office and the East Lancashire e-Partnership (ELEP) initiatives. These initiatives consist of joint service delivery, e-Procurement, web interactions and joint e-Consultation. |  |  |  |  |  |  |  | 6,773 |  |
| End Sept 2005 |  | Continuing progress towards meeting the e-Government priority outcomes. Notified by ODPM funds need to be spent by 31 March 2006. |  |  |  |  |  |  |  |  |  |
| End Dec 2005 |  | Funds to be spent by 31 March 2006 to meet priority outcomes. Progress currently being reviewed. |  |  |  |  |  |  |  |  |  |
| End Dec 2006 |  | Evaluation of new projects currently underway. Electronic presentation improvements to Committee Room 1 costing £5,000 are underway. An E-forms package may be purchased at a cost of £7,500. May be some slippage into 2007/08. |  |  |  |  |  |  |  |  |  |
| End September 2007 |  | There is currently £40,000 remaining, which is uncommitted. A review of outstanding egovernment projects will be undertaken. |  |  |  |  |  |  |  |  |  |
| End June 2008 |  | Slippage carried forward of £38,510. Securecode software to be purchased for Cash Receipting system. Decision needs to be taken over use of remaining budget. |  |  |  |  |  |  |  |  |  |
| End Sept 2008 |  | Following feedback from users of the council website £7,000 has been earmarked to purchase an upgraded version of Jadu, which will provide enhanced navigation of the site. The remaining funds will be used to ensure the council complies with the Government Connect requirements |  |  |  |  |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | LEADR |
| Name of Scheme | Creation of Member’s Rooms on Level D |  |  |  |
| Officer Responsible | MICHELLE SMITH |  |  |  |
| Description of Scheme | Changes to level D planning offices to create Leader’s office and new Members Room and purchase of office furniture and equipment. |  |  |  |
| Benefits of Scheme | Improved facilities for members and leader of the council. |  |  |  |
| Project Timetable | Start Date | July 2008 |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | LEADR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £ |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £ |  |
|  | Approved by Committee: |  |  |  |  |  |  |
|  | Date: |  |  |  |  |  |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  |  |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Sept 2008 |  | Office adaptations carried out and Leader’s office now in use. Furniture delivered and IT equipment in place. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | ROEFL |
| Name of Scheme | LOAN TO ROEFIELD |  |  |  |
| Officer Responsible | MARSHAL SCOTT |  |  |  |
| Description of Scheme | Funding to facilitate extension to Roefield Leisure Centre |  |  |  |
| Benefits of Scheme | Improvements to sports facilities |  |  |  |
| Project Timetable | Start Date | unknown |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Ability of Ribble Valley Sports and Recreation Association to raise full funding needed for scheme to go ahead |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | ROEFL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £645,000 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £645,000 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 4 March 2008 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2008/09 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  | 645,000 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 645,000 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2008 |  | Discussions still taking place with Ribble Valley Sports and Recreation Association over final choice of scheme and overall funding. |  |  |  |  |  |
| End Sept 2008 |  | As reported to Policy & Finance Committee, the council has agreed to a joint scheme to extend the Leisure Centre and provide new council changing facilities for the Edisford sports pitches. The estimated loan to the Sports Association has reduced to £485,000. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2008/09 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | SERVB |
| Name of Scheme | COMPUTER SERVER & BULK PRINTER REPLACEMENT |  |  |  |
| Officer Responsible | PETER HOTHERSALL |  |  |  |
| Description of Scheme | Three year project to rationalise the Council’s server utilisation and replacement of the bulk printers. |  |  |  |
| Benefits of Scheme | Ensure that the existing computer servers and printers are replaced before they suffer from age related problems. |  |  |  |
| Project Timetable | Start Date | April 2008 |  |  |
|  | Completion Date | March 2011 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  | Phase 1 completion | March 2009 |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None at present |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Under investigation |  |  |  |

|  |  |  |  |  |  |  | Cost Centre | SERVB |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Original Estimate for Current Year: |  |  |  |  |  | £8,000 |  |
| Summary | Approved Budget: |  |  |  |  |  | £28,000 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  |  | £28,000 |  |
|  | Approved by Committee: |  |  |  |  |  | Council |  |
|  | Date: |  |  |  |  |  | 4 March 2008 |  |
|  | Minute Ref: |  |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  | Estimated Expenditure 2008/09 £ | Estimated Expenditure 2009/10 £ |  | Estimated Expenditure 2010/11 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |  |
|  | Other Costs |  |  | 8,000 | 10,000 |  | 10,000 | 28,000 |
|  | External Fees |  |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |  |
|  | TOTAL |  |  | 8,000 |  | 10,000 | 10,000 | 28,000 |
| Monitoring – Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |  |
| End June 2008 |  | Initial planning stage is now complete. The printer replacement has been placed in year three of the project. We are to purchase and implement a server for initial Server Virtualisation, with a completion date of end Sept 2008. Once this is complete we will use the experience gained to proceed with the rest of the servers. |  |  |  |  |  |  |
| End Sept 2008 |  | Workload commitments mean that the initial Server Virtualisation will now be pushed back to the end of December 2008. |  |  |  |  |  |  |

# LICY & FINANCE COMMI