## Sheet1
| Castle Project Financial Summary |  |  |  | APPENDIX 2
| Stage 2 | Orig Scheme | Latest | Actual Position | Balance Remaining
|  | Budget | Scheme Budget | at 10/3/09
|  | £ | £ | £ | £
Special | Expenditure
Detail Codes | Total expenditure for project (per T&T) | 3223820 | 3223820
analysed as follows:
5630 | Construction Works total | 2337107 | 2290651 | 2105416.84 | 185234.16
5631 | Exhibition Fit-out | 379500 | 263850 | 69985.55 | 193864.45
5632 | Other Fit-out | 110651 | 167107 | 34459 | 132648
5633 | Professional Fees | 396561 | 502211 | 425453.63 | 76757.37
| Total as per HLF | 3223819 | 3223819 | 2635315.02 | 588503.98
Add
| Promotional Activites already incurred - start of project | 6500 | 6500 | 6500 | 0
| Promotional Activties Grand Opening rough estimate | 10000 | 10000 | -15.45 | 10015.45
| Internal Salaries | 35000 | 35000 | 9817.9 | 25182.1
| Grand Total for RVBC | 3275319 | 3275319 | 2651617.47 | 623701.53
Income
To date:
Confirmed income
8740z | Heritage Lottery Fund | 1835000 | 1835000 | 1058836.62 | 776163.38
8741z | Clitheroe the Future NWDA | 250000 | 250000 | 250000 | 0
8742z | SITA | 135000 | 135000 | -15835 | 150835
8743z | Private Sector Sponsorship: | 100000 | 100000 | 0 | 100000
8744z | Friends of Clitheroe Castle | 16245 | 16378 | 16000 | 378
8745z | Clitheroe Town Council | 5000 | 5000 | 0 | 5000
| LSP | 0 | 20000 | 0 | 20000
|  | 2341245 | 2361378 | 1309001.62 | 1052376.38
Unconfirmed Income
8746z | Lancashire Economic Partnership - bid for £670k not successful | 0 | 0 | 0
8746z | Lancashire Economic Partnership - to bid for in 2008 | 100000 | 0 | 0
|  | 100000 | 0 | 0 | 0
| Total Potential Income | 2441245 | 2361378 | 1309001.62 | 1052376.38
| Shortfall/RVBC contribution to project | 834074 | 913941 | 1342615.85 | -428674.85
Less Already in capital programme
| 2007/08 capital budget | 43660 | 43660 | 43660 | 0
| 2008/09 capital budget | 132500 | 132500 | 132500 | 0
|  | 176160 | 176160 | 176160 | 0
| Shortfall | 657914 | 737781 | 1166455.85
(£600k set aside from revenue balances)