RIBBLE VALLEY BOROUGH COUNCIL

DECISION

REPORT TO PLANNING & DEVELOPMENT COMMITTEE

Agenda Item No

meeting date: 	18 JANUARY 2007

title:	REVISED CAPITAL PROGRAMME 2006/07 AND PROPOSED PROGRAMME 2007/12

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

1	PURPOSE

1.1	To approve the revised programme for the current year and also the future five-year capital programme for this committee.

2	BACKGROUND

2.1	This report will review the following:

i)	The current year's programme.

ii)	Draft programme of schemes to be carried out in the following five years (2007/08 to 2011/12).

3	ORIGINAL PROGRAMME 2006/07

3.1	The original capital programme for the current year consisted of two schemes these related to the car parks rolling programme for 2006/07 with a budget of £41,200 and the replacement of screens and ergonomics for our CCTV system  - £17,000.

3.2	Slippage of £29,100 in respect of the car parks rolling programme for 2005/06 has been added to the original programme.  This is shown in Annex 1.

4	REVISING THE CURRENT YEAR'S PROGRAMME

4.1	We have now discussed each scheme in the programme with budget holders and revised the programme to reflect likely expenditure this year.  This is shown in Annex 1, alongside the original estimate.

4.2	Updated capital evaluation forms for both schemes are attached at Annex 2 (YELLOW).

4.3	In summary, the revised programme is:

| Total Approved Budget £ | Revised Estimate for Current Year £ | Expenditure to Date £ |
| --- | --- | --- |
| 87,300 | 46,100 | 7,811 |

5	DRAFT PROGRAMME 2007/08 TO 2011/12

5.1	New schemes have been put forward by officers to form part of our five-year capital programme.  Annex 3 shows the draft programme for this committee.

5.2	You will see no new schemes have been put forward except for the bringing in to the programme of the 5th year for car parks rolling programme in 2011/2012.

5.3	Annex 3 is a possible programme that will require further consideration by the Budget Working Group and by Policy and Finance Committee who will want to make sure that it is affordable, both in capital and revenue terms.

Members should therefore consider the schemes in Annex 3 and any amendments you may wish to make at this stage.

5.4	Capital evaluation forms for all new schemes approved for next year (2007/08) will be completed and reported to committees in the next cycle.

5.5	A summary of the five-year programme for Planning and Development Committee is shown below:

| 2007/08 £ | 2008/09 £ | 2009/10 £ | 2010/11 £ | 2011/12 £ |  | Total £ |
| --- | --- | --- | --- | --- | --- | --- |
| 41,200 | 41,200 | 62,200 | 41,200 | 41,200 |  | 227,000 |

6	RECOMMENDED THAT COMMITTEE

6.1	Approve the revised capital programme for 2006/07 as set out in Annex 1.

6.2	Consider the future five-year programme for 2007/08 to 2011/12 as set out in Annex 3 and agree any amendments you wish to make.

FINANCIAL SERVICES MANAGER

PD2-07/JP/AC

8 JANUARY 2007

##### ANNEX 1

# PLANNING AND DEVELOPMENT COMMITTEE

REVISED CAPITAL PROGRAMME 2006/07

|  |  | Budget Analysis |  |  |  |  |  | Expenditure Analysis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost | Schemes | Original | Slippage | Additional | Total | Revised | Budget | Total |
| Centre |  | Estimate |  | Approvals | Approved | Estimate | moved to | Expenditure |
|  |  | 2006/07 |  |  | Budget |  | 2007/08 | To Date |
|  |  | £ | £ | £ | £ | £ | £ | £ |
|  | Planning & Development Committee |  |  |  |  |  |  |  |
| CARPH | Car Parks Rolling Programme 2005/06 |  | 29,100 |  | 29,100 | 29,100 |  | 6,331 |
| CARPI | Car Parks Rolling Programme 2006/07 | 41,200 |  |  | 41,200 | 0 | 41,200 | 1,480 |
| ERGTV | Replace screens and ergonomics CCTV system | 17,000 |  |  | 17,000 | 17,000 |  | 0 |
|  | Total Planning & Development Committee | 58,200 | 29,100 | 0 | 87,300 | 46,100 | 41,200 | 7,811 |

##### ANNEX 2

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CARPH |
| Name of Scheme | CAR PARKS ROLLING PROGRAMME 2005/06 |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Improvements to car parks at Chipping |  |  |  |
| Benefits of Scheme | Housing and public car park which meets the expectations of those using it and which meets nationally agreed standards. |  |  |  |
| Project Timetable | Start Date | February 2007 |  |  |
|  | Completion Date | April 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | We have yet, despite exhaustive efforts to do so, to complete the negotiation regarding a new base for the car park and toilets at Chipping. All delay is due to the Trustees. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes, provided the lease is sorted soon. |  |  |  |
| What are the revenue implications of the scheme? | Assuming that the introduction of charging for parking on this car park follows the improvement works there will be additional parking revenue generated. |  |  |  |

|  |  |  |  |  |  | Cost Centre | CARPH |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised estimate: |  |  |  |  | £29,100 |  |
| Summary | Approved Budget for Current Year: |  |  |  |  | £29,100 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  | 1,455 | 26,200 | 22,600 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  | 6,667 | 2,900 | 9,567 |
|  | TOTAL |  |  |  | 8,122 | 29,100 | 37,222 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| Oct 2006 |  | Several meetings have been held with the Trustees and/or their Agents to date and whilst there is an agreement is principle to lease the car park and toilets to the council we have get to receive any formal proposals in writing. All delays are as a consequence of the difficulties with the Trustees. Until they are fully resolved work will not get underway. |  |  |  |  |  |
| Dec 2006 |  | Pay and Display introduced at Sabden car park. Works to be carried out at Bolton by Bowland car park including resurfacing shortly. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CARPI |
| Name of Scheme | CAR PARKS ROLLING PROGRAMME 2006/07 |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | To improve the overall standard of the car parks in the Borough. Work is likely to be undertaken at the car park at Chipping subject to agreeing the terms of a new lease with the Trustees. |  |  |  |
| Benefits of Scheme | Having public car parks which meet the expectation of their users and meet nationally recognised standards. |  |  |  |
| Project Timetable | Start Date | August 2006 |  |  |
|  | Completion Date | March 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Agreement of new lease with Trustees |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Only if staff are retrained and not transferred to the County Council on an arrangement of the termination of the Lancashire Highways Partnership. |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | CARPI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £41,200 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £41,200 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 38,000 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  | 1,000 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  | 2,200 |
|  | TOTAL |  |  |  |  |  | 41,200 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Sept 06 |  | Discussions are still ongoing with regard to new lease for Chipping car park |  |  |  |  |  |
| End Dec 06 |  | Draft lease now received from trustees of Chipping car park and currently being evaluated by our Legal Section. Anticipate this budget will need to be moved back to 2007/08 |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | ERGTV |
| Name of Scheme | REPLACE SCREENS AND ERGONOMICS – CCTV SYSTEM |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Our CCTV monitoring services are currently provided by Broadland Guarding. They recently brought to our attention a number of concerns, including discomfort of operators therefore an ergonomic risk assessment was carried out. Following the risk assessment it has become necessary for the health and safety of the operation to redesign the layout of the office and the operating console. In doing so, taking into consideration the life expectancy of the display screen, it would be beneficial to change the screens to flat screens at the same time. Possible implications of not carrying out the required works are that Broadland Guarding may not be happy to carry on providing surveillance and we may be responsible for any future claims. |  |  |  |
| Benefits of Scheme | A safe and efficient working environment. |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | January 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | The project timetable may be affected depending on the priority given to this work. The full cost can only be established when a full design of the scheme has been undertaken. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Only if staff are retained and not transferred to the County Council as a consequence of the termination of the Lancashire Highways Partnership. |  |  |  |
| What are the revenue implications of the scheme? | None. |  |  |  |

|  |  |  |  |  |  | Cost Centre | ERGTV |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £17,000 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £17,000 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  | 16,000 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  | 1,000 |
|  | TOTAL |  |  |  |  |  | 17,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Subject to having sufficient staff resources available an assessment of the overall objectives of the scheme will be undertaken by the end of May. This will produce a draft design proposal for estimating purposes. |  |  |  |  |  |

##### ANNEX 3

| DRAFT 5 yr Capital Programme 2007/12 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Scheme | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | Total |
|  | £ | £ | £ | £ | £ | £ |
| Planning & Development Committee |  |  |  |  |  |  |
| Car Parks Rolling Programme | 41,200 | 41,200 | 41,200 | 41,200 | 41,200 | 206,000 |
| Replace some Car Park ticket machines |  |  | 21,000 |  |  | 21,000 |
| Total Planning & Development | 41,200 | 41,200 | 62,200 | 41,200 | 41,200 | 227,000 |