RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO POLICY & FINANCE COMMITTEE

Agenda Item No

meeting date: 	30 JANUARY 2007

title:	REVISED CAPITAL PROGRAMME 2006/07 AND PROPOSED

PROGRAMME 2007/12

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

1	PURPOSE

1.1	To approve the revised programme for the current year and also the future five-year capital programme for this committee.

2	BACKGROUND

2.1	This report will review the following:

i)	The current year's programme.

ii)	Draft programme of schemes to be carried out in the following five years (2007/08 to 2011/12).

3	ORIGINAL PROGRAMME 2006/07

3.1	The original capital programme for the current year included schemes at a total estimated cost of £129,400.

3.2	Unfinished schemes from 2005/06, totalling £177,400, have been added to the original programme.  This is shown in Annex 1 and known as slippage.

4	REVISING THE CURRENT YEAR'S PROGRAMME

4.1	We have now discussed each scheme in the programme with budget holders and revised the programme to reflect likely expenditure this year.  This is shown in Annex 1, alongside the original estimate.

4.2	Updated capital evaluation forms for both schemes are attached at Annex 2 (YELLOW).

4.3	In summary, the revised programme is:

| Total Approved Budget £ | Revised Estimate for Current Year £ | Expenditure to Date £ |
| --- | --- | --- |
| 306,800 | 290,700 | 100,443 |

5	DRAFT PROGRAMME 2007/08 TO 2011/12

5.1	New schemes have been put forward by officers to form part of our five-year capital programme.  Annex 3 shows the draft programme for this committee.

5.2	However, this is really only the first attempt to ascertain future schemes.  Therefore, Annex 3 is a possible programme that will require further consideration by the Budget Working Group and by Policy and Finance Committee who will want to make sure that it is affordable, both in capital and revenue terms.

5.3	A new capital scheme pro forma has been completed for any new schemes added to the five year programme by the relevant officer.  These are attached at Annex 4 (BLUE).  The re-roofing of the Council Offices scheme at a budget of £221,500 in 2010/11 has been deleted.  The Officer responsible feels that the work carried out recently will extend the life of the roof and any other required works could be carried out from the repairs and maintenance budget.

5.4	Members should therefore consider the schemes in Annex 3 and any amendments you may wish to make at this stage.

5.5	Capital evaluation forms for all new schemes approved for next year (2007/08) will be completed and reported to committees in the next cycle.

5.7	A summary of the five-year programme for Policy and Finance Committee is shown below:

| 2007/08 £ | 2008/09 £ | 2009/10 £ | 2010/11 £ | 2011/12 £ |  | Total £ |
| --- | --- | --- | --- | --- | --- | --- |
| 176,900 | 75,400 | 0 | 0 | 0 |  | 252,300 |

6	RECOMMENDED THAT COMMITTEE

6.1	Approve the revised capital programme for 2006/07 as set out in Annex 1.

6.2	Consider the future five-year programme for 2007/08 to 2011/12 as set out in Annex 3 and agree any amendments you wish to make.

FINANCIAL SERVICES MANAGER

PF3-07/JP/AC

17 JANUARY 2007

ANNEX 1

# POLICY & FINANCE COMMITTEE

REIVSED CAPITAL PROGRAMME 2006/07

|  |  | Budget Analysis |  |  | Expenditure Analysis |
| --- | --- | --- | --- | --- | --- |
| Cost | Schemes | Original | Slippage | Additional | Total | Revised | Budget | Total |
| Centre |  | Estimate |  | Approvals | Approved | Estimate | moved to | Expenditure |
|  |  | 2006/07 |  |  | Budget |  | 2007/08 | To Date |
|  |  | £ | £ | £ | £ | £ | £ | £ |
|  | Policy & Finance Committee |  |  |  |  |  |  |  |
| BADDA | Building alterations - Disability Discrimination Act |  | 10,000 |  | 10,000 | 10,600 |  | 10,565 |
| CHIPP | Chip and Pin Implementation | 10,000 |  |  | 10,000 | 0 |  | 0 |
| CIVHS | Civic Suite - DDA & Impts to stored water system | 45,000 |  |  | 45,000 | 45,000 |  | 19,055 |
| CROOM | Computer Server Room Improvements | 15,200 |  |  | 15,200 | 15,200 |  | 425 |
| CVSEC | Civic Suite - Replace Security system | 11,600 |  |  | 11,600 | 11,600 |  | 0 |
| EENAB | eEnabling Members | 5,000 |  |  | 5,000 | 5,000 |  | 0 |
| EGIIV | E Government Initiative |  | 60,000 |  | 60,000 | 60,000 |  | 0 |
| OFCEI | Council Offices - Fire safety improvements to ceilings | 21,600 | 7,000 |  | 28,600 | 28,600 |  | 10,739 |
| OFTOL | Council Offices - Toilets |  |  |  |  | 1,300 |  | 1,299 |
| OFWIN | Council Offices - Replace windows |  | 39,800 |  | 39,800 | 39,800 |  | 39,867 |
| ROOFL | Council Offices - Lead replacement & repairs to Roof | 21,000 |  |  | 21,000 | 21,000 |  | 15,365 |
| RTELE | Replace Telephone system |  | 16,000 |  | 16,000 | 8,000 |  | 0 |
| UPFIN | Upgrade of Financial Ledger System |  | 44,600 |  | 44,600 | 44,600 |  | 3,128 |
|  | Total Policy and Finance Committee | 129,400 | 177,400 | 0 | 306,800 | 290,700 | 0 | 100,443 |

| RIBBLE VALLEY BOROUGH COUNCIL |  | ANNEX 2 |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | BADDA |
| Name of Scheme | BUILDING ALTERATIONS – DISABILITY DISCRIMINATION ACT |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Disability Discrimination Act compliance work |
| Benefits of Scheme | Comply with legislation and bring in improvements recommended by Ribble Valley Access Group |
| Project Timetable | Start Date | April 2005 |
|  | Completion Date | March 2006 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | The extent of works required under this scheme needs to be considered by the Ribble Valley Access Group. There could be potential savings under this scheme. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | BADDA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: | £10,600 |  |
| Summary | Slippage from 2006/07: | £10,000 |  |
|  | Expected Total Cost of Scheme: | £10,600 |  |
|  | Approved by Committee: | Council |
|  | Date: | 1 March 2005 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 10,600 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 10,600 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| March 2005 | This budget is to cover any items of work that are raised as a result of implementation of the Disability Discrimination Act and any action taken against the Council. Possibility for work to be carried out is reception on level C, which is not compliant with the Act. |
| End June 2005 | Negotiation with Ribble Valley Access Group still to take place. Requirement for automatic doors at main entrance have been identified. Anticipated cost £10,000. |
| End Sept 2005 | As June 2005. Prices received for doors. Work anticipated February 2006. |
| End Dec 2005 | Work anticipated end February 2006. |
| End Sept 2006 | Work to automatic doors complete June 2006 cost £10,565. Potential savings under the scheme due to delayed negotiations with RV access group as the groups structure is currently under review. |
| End Dec 2006 | Scheme complete. Work to construct disabled ramp on Platform Gallery not carried out due to budget constraints, plan to incorporate in 5 year capital programme. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CHIPP |
| Name of Scheme | INTRODUCE CHIP AND PIN TECHNOLOGY |
| Officer Responsible | MARK EDMONDSON |
| Description of Scheme | Banks are moving away from signatures for credit and debit card payments to reduce fraud. They may make the use of this technology compulsory in the future. |
| Benefits of Scheme | To reduce possibility of fraud |
| Project Timetable | Start Date | August 2006 |
|  | Completion Date | August 2006 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Compatibility with Radius cash receipting system |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None. However, may encourage more customers to pay electronically |

|  |  |  |  |  |  | Cost Centre | CHIPP |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: | £0 |  |
| Summary | Approved Budget for Current Year: | £10,000 |  |
|  | Expected Total Cost of Scheme: | £10,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  | 0 |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 0 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | Discussions currently taking place with cash receipting system providers (Radius) about implementation and their charges. |
| End Sept 2006 | Further investigation revealed the cost of implementing chip and pin would be substantially more than £10,000. Quote from Radius of £22,150 up front fee and £680 annual fee. Also the current pc’s do not meet the hardware requirements and therefore up to 5 new pc’s would be required. As a result of the substantial increase in cost, and the fact that there is no legal requirement to use chip and pin no further action has been taken. NB anyone accepting credit/debit card payments now have to use chip and pin or be responsible for any fraud. At RVBC the vast majority of these transactions relate to council tax and if a card is used fraudulently we simply re-bill the liable party. |
| End Dec 2006 | As above scheme cancelled. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CIVHS |
| Name of Scheme | DDA AND HEALTH AND SAFETY WORKS TO CIVIC SUITE |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | To install lift to allow access to first floor meeting rooms. Refurbish works to comply with DDA and remove Legionnaires risk from existing stored water system. Civic Suite – Lift The lift is necessary as no disabled access is available to the meeting rooms on the first floor or the public gallery. Installing monitors within reception that transmit live pictures and sound from the council chamber have catered for access to the gallery. The meeting rooms are however inaccessible for disabled people with walking difficulties attending meetings. This can include members of staff, members of the public, external auditors and members of the Council. Regarding members of the Council the DDA has been amended in that members are now included within the Act and as such councils cannot discriminate against this group. Civic Suite – WCs The WCs are included for inclusion as it was deemed that they are not really up to a sufficient standard (unlike offices) for the building they are held in. The main issue however is that the WCs are served from a large water heater that stores hot water. This is defective at the moment and as such is potentially a Legionella bacteria source. The aim is to remove the heater and incorporate instantaneous water heaters therefore eliminating the Legionella risk. During refurbishment water saving taps would be installed and an anti-slip floor covering. The whole refurbishment would improve health and safety regarding the WCs. The disabled WC does not comply with current best practice, building regulations and DDA regarding the equipment within it. |
| Benefits of Scheme | Health and safety improvements and compliance with current legislation |
| Project Timetable | Start Date | July 2006 |
|  | Completion Date | September 2006 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None at this stage |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | £600 annual maintenance repairs to lift |

|  |  |  |  |  |  | Cost Centre | CIVHS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £45,000 |  |
| Summary | Expected Total Cost of Scheme: | £45,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 40,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  | 2,000 |
|  | Internal Salaries |  |  |  |  | 3,000 |
|  | TOTAL |  |  |  |  | 45,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | Design work to lift to be commenced/revisited. |
| End Sept 2006 | WC work complete beginning October 2006 lift prices received September 2006 final approval on design October 2006. Work to commence January 2007 completion January 2007. |
| End Dec 2006 | Retention and final account outstanding for toilet work. Lift decision still being considered. Plan to commence before end of financial year. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CROOM |
| Name of Scheme | IMPROVEMENTS TO COMPUTER SERVER ROOM |
| Officer Responsible | PETER HOTHERSALL |
| Description of Scheme | Following review of IT service by external auditors a number of recommendations were made regarding the current server room. In addition our insurance company have requested similar improvements to ensure fire prevention methods are in place. |
| Benefits of Scheme | Will enhance and improve the efficiency and quality of services by optimising the application of information technology and continuing to invest in cost effective business solutions. |
| Project Timetable | Start Date | June 2006 |
|  | Completion Date | July 2006 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | External contractors are doing the work |
| What are the revenue implications of the scheme? | £200 per annum service and maintenance of air conditioning unit. £200 per annum fire extinguishing system |

|  |  |  |  |  |  | Cost Centre | CROOM |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £15,200 |  |
| Summary | Expected Total Cost of Scheme: | £15,200 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Fire Structural Precautionary Work |  |  | 1,000 |
|  | Fire Extinguishing System |  |  |  | 4,770 |
|  | Room Integrity Check |  |  |  | 480 |
|  | Air Sampling System |  |  |  | 2,350 |
|  | Ceiling Made Airtight |  |  |  | 600 |
|  | Secondary Air Conditioning Unit |  |  | 6,000 |
|  | TOTAL |  |  |  |  | 15,200 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | End of June completion |
| End Sept 2006 | The fire structural precautionary work completed. Room integrity check scheduled for December. |
| End Dec 2006 | Remainder of work scheduled for Feb 2007, to be completed by end of Feb 2007. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | CVSEC |
| Name of Scheme | CIVIC SUITE – REPLACE SECURITY SYSTEM |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Scheme to be cancelled. Existing system adequate for purpose. Existing life approximately 15 years. |
| Benefits of Scheme |  |
| Project Timetable | Start Date |  |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose |  |
| What are the revenue implications of the scheme? |  |

|  |  |  |  |  |  | Cost Centre | CVSEC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: | £0 |  |
| Summary | Approved Budget for Current Year: | £11,600 |  |
|  | Expected Total Cost of Scheme: | £11,600 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 0 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 0 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | Scheme cancelled. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | EENAB |
| Name of Scheme | E-ENABLING MEMBERS |
| Officer Responsible | MICHELLE SMITH/PETER HOTHERSALL |
| Description of Scheme | Provision of PC access/laptops |
| Benefits of Scheme | Enable email services for member information, eg minutes, agendas, circulars, and improve electronic communication between members and officers |
| Project Timetable | Start Date | April 2006 |
|  | Completion Date | April 2009 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Availability of in-house IT technical support, willingness of members to engage with new technology |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Probably within democratic services but issues regarding IT support. Discussions currently taking place between Michelle Smith, Peter Hothersall and Councillor Sherras to review issues. |
| What are the revenue implications of the scheme? |  |

|  |  |  |  |  |  | Cost Centre | EENAB |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £5,000 |  |
| Summary | Expected Total Cost of Scheme: | £15,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  | Expected Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  | 5,000 | 5,000 | 5,000 | 15,000 |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  | 5,000 | 5,000 | 5,000 | 15,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | Initial report on proposed method of implementation to policy and Finance Committee. |
| End Sept 2006 | Have held 2 meetings of the e-enabling working group. Carried out survey of IT equipment and usage amongst councillors. Moved to electronic distribution of minutes and agendas where possible and reduce paper usage. Explored options to improve email access for members and looking to purchase a Juniper Netscreen product at a cost of £2,659 (includes annual maintenance figure of £400) this will be confirmed when PH returns from holiday. |
| End Dec 2006 | Work commenced on developing Councillor’s portal to access committee papers on line. Brief presentation demonstrating portal and improvements to website, given at Full Council in November 2006. System currently under test after which full training/briefing session will be provided for members. Work ongoing to include appendices and attachments to electronic version of minutes and agendas. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | EGIIV |
| Name of Scheme | E-GOVERNMENT INITIATIVE – IEG4 – PHASE 2 2006/07 |
| Officer Responsible | MARSHAL SCOTT |
| Description of Scheme | To introduce electronic methods of service delivery |
| Benefits of Scheme | Improved access to services |
| Project Timetable | Start Date | April 2005 |
|  | Completion Date | March 2007 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Shortage of staff resources. The number of computer projects to be implemented. |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Will be difficult given the Government’s deadlines for priority outcomes |
| What are the revenue implications of the scheme? | Not yet quantified but the Government believes there will be long-term savings from this initiative |

|  |  |  |  |  |  | Cost Centre | EGIIV |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £60,000 |  |
| Summary | Expected Total Cost of Scheme: | £60,000 |  |
|  | Approved by Committee: | Council |
|  | Date: | 1 March 2005 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 60,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 60,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2005 | The £150,000 IEG4 grant money will be funding both the e-Government office and the East Lancashire e-Partnership (ELEP) initiatives. These initiatives consist of joint service delivery, e-Procurement, web interactions and joint e-Consultation. |
| End Sept 2005 | Continuing progress towards meeting the e-Government priority outcomes. Notified by ODPM funds need to be spent by 31 March 2006. |
| End Dec 2005 | Funds to be spent by 31 March 2006 to meet priority outcomes. Progress currently being reviewed. |
| End Dec 2006 | Evaluation of new projects currently underway. Electronic presentation improvements to Committee Room 1 costing £5,000 are underway. An E-forms package may be purchased at a cost of £7,500. May be some slippage into 2007/08. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | OFCEI |
| Name of Scheme | COUNCIL OFFICES – FIRE SAFETY IMPROVEMENTS TO CEILINGS |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Replacement of existing suspended ceilings |
| Benefits of Scheme | Improved fire and safety energy performance |
| Project Timetable | Start Date | July 2005 |
|  | Completion Date | November 2006 |
|  | Any Other Key Dates | Description of Work |
|  |  | Strip our concealed grid ceiling and replace with exposed grid ceiling |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | OFCEI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Original Budget for year: | £21,600 |  |
| Summary | Slippage from 2005/06 | £7,000 |  |
|  | Total Budget for Current Year: | £28,600 |  |
|  | Expected Total Cost of Scheme: | £64,157 |  |
|  | Approved by Committee: | Council |
|  | Date: | 1 March 2005 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 35,557 | 28,600 | 64,157 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  | 35,557 | 28,600 | 64,157 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2005 | Design works carried out. Delay due to programming on site. Works to start during holiday period to minimise disruption. Anticipate some of the budget may not be needed or may need to be moved to 2006/07, depending on progress. |
| End Sept 2005 | Work complete to several areas, including housing, level C, chief executive. Remaining ceiling due for replacing January 2006. |
| End Dec 2005 | As September 2005 |
| End March 2006 | Work to commence on staircases March 2006. Office area to Level C legal services planned for July 2006. |
| End Sept 2006 | Work delayed since July due to contractor commitments. Work planned October 2006 for Environmental Health Section followed by Legal Services. If funding allows then other items will be identified and work carried out. |
| End Dec 2006 | Work done to Environmental Health Section ceiling. Legal Section to commence February. Hope to carry out other work before end of March. Will be some slippage into 2007/08. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | OFTOL |
| Name of Scheme | COUNCIL OFFICES – REFURBISH TOILETS |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Refurbish council offices toilets and make changes to level C |
| Benefits of Scheme | Improved energy efficiency and efficiency measures |
| Project Timetable | Start Date | 7 March 2005 |
|  | Completion Date |  |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? |  |

|  |  |  |  |  |  | Cost Centre | OFTOL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: | £1,300 |  |
| Summary | Total original Budget for Scheme: | £64,500 |  |
|  | Expected Total Cost of Scheme: | £59,865 |  |
|  | Approved by Committee: | Council |
|  | Date: | 1 March 2005 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  | Actual Expenditure 2004/05 £ | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  | 25,898 | 32,668 | 1,299 | 59,865 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  | 25,898 | 32,668 | 1,299 | 59,865 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2005 | Scheme is complete with exception of minor snagging items. Retention due 8 June 2006. Anticipated outstanding expenditure: £ 8,976 due 2005/06 £ 1,324 due 2006/07 £10,300 Also, approximately £3,000 required for Chief Executive’s WC. |
| End Sept 2005 | Work to chief executive office commenced. Due for completion November 2005. |
| End Dec 2005 | Completion due January 2006. Delay due to manufacture of panels. Will slip retention into 2006/07. |
| End Dec 2006 | Retention now paid £1,299. Scheme complete. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | OFWIN |
| Name of Scheme | COUNCIL OFFICES – REPLACE WINDOWS |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Replace existing aluminium single glazed windows |
| Benefits of Scheme | Improved energy efficiency/thermal comfort |
| Project Timetable | Start Date | September 2005 |
|  | Completion Date | September 2005 |
|  | Any Other Key Dates | Description of Work |
|  | July 2005 | Approval from planning for style |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | OFWIN |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2005/06 | £39,800 |  |
| Summary | Approved Budget for Current Year: | £39,800 |  |
|  | Expected Total Cost of Scheme: | £40,047 |  |
|  | Approved by Committee: | Council |
|  | Date: | 1 March 2005 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  | 247 | 39,800 | 40,047 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  | 247 | 39,800 | 40,047 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2005 | Waiting for response from planning section regarding approval of design for new windows. Intend to replace aluminium windows with new. Anticipate works will be carried out within budget and before end of financial year. |
| End Sept 2005 | Prices received for replacement of aluminium windows. Budget insufficient for replacement in aluminium therefore estimates for replacements in alternative materials being sought. |
| End Dec 2005 | Price for replacement in PVC being sought. |
| End Sept 2006 | Scheme complete April 2006 |
| End Dec 2006 | Scheme complete |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | ROOFL |
| Name of Scheme | COUNCIL OFFICES – ROOF REPAIRS, LEAD REPLACEMENT |
| Officer Responsible | ROD PEARCE |
| Description of Scheme | Urgent repairs required to several areas that are causing health and safety concerns. This constitutes lead replacement and felt renewals to isolated areas. |
| Benefits of Scheme | Health and safety |
| Project Timetable | Start Date | April 2006 |
|  | Completion Date | April 2006 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |
| What are the revenue implications of the scheme? | None |

|  |  |  |  |  |  | Cost Centre | ROOFL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: | £21,000 |  |
| Summary | Expected Total Cost of Scheme: | £21,000 |  |
|  | Approved by Committee: | Full Council |
|  | Date: | 28 February 2006 |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 21,000 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 21,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End March 2006 | Work out to tender with returns due March. Work to commence April 2006. |
| End Sept 2006 | Main roof work complete. Cavity tray work to be complete by March 2007. |
| End Dec 2006 | Cavity tray work currently being carried out at main entrance to offices. Scheme to be complete by end of March. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | RTELE |
| Name of Scheme | REPLACE TELEPHONE SYSTEM |
| Officer Responsible | MICHELLE SMITH |
| Description of Scheme | Replacement of existing system which currently has no capacity for future expansion |
| Benefits of Scheme | Improved telecom service for internal and external customers |
| Project Timetable | Start Date | March 2004 (tender) |
|  | Completion Date | Spring 2005 |
|  | Any Other Key Dates | Description of Work |
|  | 23 March 2004 | Final tender specification to Policy & Finance Committee then invitation to tender will be issued |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Possible IT issues when new system is selected although initial specification would prevent this |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose? | No. Have engaged consultancy services from Improcom to manage tender process and implementation programme |
| What are the revenue implications of the scheme? | None |

| Financial | Revised Estimate: | £8,000 |  |
| --- | --- | --- | --- |
| Summary | Slippage From 2005/06: | £16,000 |  |
|  | Approved Budget for Current Year: | £16,000 |  |
|  | Expected Total Cost of Scheme: | £50,182 |  |
|  | Approved by Committee: | Council |
|  | Date: | 2 March 2004 |
|  | Minute Ref: | 762 |

|  |  |  |  |  | Cost Centre | RTELE |
| --- | --- | --- | --- | --- | --- | --- |
| Expenditure Analysis |  |  | Actual Expenditure 2004/05 £ | Expected Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  | 13,600 | 20,581 | 8,000 | 42,181 |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  | 13,600 | 20,581 | 8,000 | 42,181 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End June 2004 | Tenders processed and preferred supplier chosen (Philips). Initial project plan meeting held in June. Implementation plan agreed. Next meeting 12 July 2004. Hoping to go live by middle September 2004. |
| End Dec 2004 | Payment withheld until new system available. New upgraded system installed 17 January 2005. Will anticipate releasing payment by end of January 2005 when I am happy that it is working properly. |
| End June 2005 | Regular meetings have taken place with Philips Telecommunications over the course of the last 6 months whilst the system continued to be tested. We now have an engineer on site 3 days per week to roll out the PC application to all departments during the next month or so. At the last meeting with Philips we agreed to pay 60% of the original invoice (£24,182.92). This will leave an outstanding balance of £16,121.94 plus a maintenance contract for 12 months at a cost of £2,749.50. |
| End Sept 2005 | Continue to experience problems with the telephone system in respect of stability. Philips has accepted that it is unrealistic for the Council to continue in this manner and have decided to remove the system totally and replace with a new and more stable system. Representatives from Philips will meet with CMT on 9 November to agree a way forward. Full payment for the system is still being withheld. |
| End Dec 2005 | Following meeting with Philips, agreed that current system will be replaced by a new switchboard system in January 2006 at no extra cost. Still withholding final settlement until new system is fully operational and all staff trained. |
| End Sept 2006 | New switchboard product installed but continue to experience problems. Negotiations continue with Philips and they have agreed to reduce final bill to £8k. We are still withholding payment until technical issues have been sorted; especially as new problems have arisen since contact centre online. |
| End Dec 2006 | Still testing the system and particularly the interface with the MacFarlane Call Centre Software. Discussions to resolve technical issues still ongoing. Final payment still withheld. |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |
| --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT | Cost Centre | UPFIN |
| Name of Scheme | UPGRADE OF FINANCIAL LEDGER SYSTEM |
| Officer Responsible | JANE PEARSON |
| Description of Scheme | Upgrade financial system to include e-procurement system |
| Benefits of Scheme | More efficient system of ordering and better, more up-to-date, financial ledger system |
| Project Timetable | Start Date | October 2005 |
|  | Completion Date | June 2006 |
|  | Any Other Key Dates | Description of Work |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Limited staff resources and competing workloads |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Hopefully but may impact on other aspects of financial services work |
| What are the revenue implications of the scheme? | Can be met within existing revenue budget |

|  |  |  |  |  |  | Cost Centre | UPFIN |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: | £44,600 |  |
| Summary | Approved Budget for Current Year: | £44,600 |  |
|  | Expected Total Cost of Scheme: | £91,079 |  |
|  | Approved by Committee: |  |
|  | Date: |  |
|  | Minute Ref: |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2005/06 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |
|  | Other Costs |  |  | 46,479 | 44,600 | 91,079 |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |
|  | TOTAL |  |  | 46,479 | 44,600 | 91,079 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |
| End Sept 2005 | Hardware purchased and installed. Software arrived and loaded, implementation begun. |
| End Dec 2005 | Conversion of existing data underway. Software consultant on site on a regular basis. Plan to go live April 2006. |
| End March 06 | Conversion plans finalised. Plan to go live April/May 2006. Training of users underway. |
| End Sept 06 | New financials system fully working live date May 2006. all data successfully migrated from Powersolve and balanced to Financials. All interfaces written and correctly working. |
| End Dec 06 | The final figures need to be agreed with Civica however, members will recall that significant savings were likely to be made due to the joint procurement with neighbouring East Lancashire Authorities. It appears that we will save around £40k. |

ANNEX 3

# POLICY & FINANCE COMMITTEE

DRAFT FIVE YEAR CAPITAL PROGRAMME 2007/12

|  | Officer | Scheme | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | £ | £ | £ | £ | £ | £ | Notes |
|  |  | Policy & Finance Committee |  |  |  |  |  |  |  |
|  | MSm | Replace Risograph Printer | 6,200 |  |  |  |  | 6,200 |  |
|  | MSm | eEnabling Members | 5,000 | 5,000 |  |  |  | 10,000 |  |
|  | ME | Replacement for Mobile Office |  | 50,000 |  |  |  | 50,000 |  |
| NEW | ME | eBenefits System | 35,000 |  |  |  |  | 35,000 |  |
|  |  | Council Offices: |  |  |  |  |  |  |  |
|  | RP | Fire safety improvements to ceilings | 21,600 |  |  |  |  | 21,600 |  |
|  | RP | Full Reroof of council offices |  |  |  | 0 |  | 0 | Deleted £221,500 in 2010/11 |
|  | RP | Refurbish common staircases |  | 8,800 |  |  |  | 8,800 |  |
|  |  | Civic Suite: |  |  |  |  |  |  |  |
|  | RP | Replace Furniture |  | 11,600 |  |  |  | 11,600 |  |
|  | RP | Replace Light Fittings | 10,300 |  |  |  |  | 10,300 |  |
| NEW | RP | Replace Gas fired boilers at Civic Suite | 98,800 |  |  |  |  | 98,800 |  |
|  |  | Total Policy & Finance Committee | 176,900 | 75,400 | 0 | 0 | 0 | 252,300 |  |

ANNEX 4

| NEW CAPITAL SCHEME PROFORMA |
| --- |
| Name of Officer Responsible | Mark Edmondson |
| Committee | Policy and Finance |
| Brief Description of Scheme | Purchase Northgate E-Benefits System to allow mobile working in Benefits Section |
| Full Details of Scheme | As above |
| Links to Corporate Objectives | To be a well managed Council |
| Cost of Scheme: | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor |  |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | 35,000 | Estimated cost |
|  |  | 35,000 |  |

| Revenue Implications of the Scheme per year | £ | Details |
| --- | --- | --- |
| Timescale (incl any key dates) |  |  |
|  | eg start on site |  |  |
|  | scheme completion |  |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |
| if the scheme will cover more than one year please breakdown the cost for each year |
|  | Year eg | £ |  |
|  | 2007/08 | 35,000 |  |
| Capital Funding & Sources |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |

| NEW CAPITAL SCHEME PROFORMA |
| --- |
| Name of Officer Responsible | Rod Pearce |
| Committee | Policy and Finance |
| Brief Description of Scheme | Replacement of gas fired boilers to Civic Suite. |
| Full Details of Scheme | Existing boilers are 17 years old. Reliability is an issue with several instances of boiler failure for minor periods (approx 1-2 days at a time). Excessive maintenance costs and call outs are also being experienced. Replacement boilers will be high efficiency units resulting in lower fuel usage resulting in lower C02 emissions and lower maintenance costs. |
| Links to Corporate Objectives | To make people’s lives safer and healthier. To protect and enhance existing environmental quality of our area. |
| Cost of Scheme: | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 80,000 |  |
|  | Fees | 8,000 |  |
|  | Internal Staff Salaries | 2,000 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | 8,800 | Contingency |
|  |  | 98,800 |  |

| Revenue Implications of the Scheme per year | £ | Details |
| --- | --- | --- |
|  |  | 700 | Annual servicing of boilers and BMs. |
| Timescale (incl any key dates) |  |  |
|  | eg start on site | June 2007 |  |
|  | scheme completion | August 2007 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |
| if the scheme will cover more than one year please breakdown the cost for each year |
|  | Year eg | £ |  |
| Capital Funding & Sources |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |

# Text boxes

DECISION