RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO SPECIAL POLICY & FINANCE COMMITTEE

Agenda Item No

meeting date: 	13 FEBRUARY 2007

title:	OVERALL REVISED CAPITAL PROGRAMME 2006/07

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

1	PURPOSE

1.1	To approve the overall revised capital programme.

2	LATEST POSITION BY COMMITTEE

2.1	Annex 1 (PINK) shows the position by scheme, as presented to committees in the current cycle.  Summarised by committee the situation is as follows:

|  | Budget Analysis |  | Expenditure |
| --- | --- | --- | --- |
|  | Original Estimate 2006/07 £ | Slippage £ | Additional Approvals £ | Total Approved Budget £ | Revised Estimate £ | Budget Moved to 2007/08 £ |  | Actual to Date £ |
| Community | 1,049,510 | 153,200 | 10,000 | 1,212,710 | 1,077,870 | 494,310 |  | 711,813 |
| Planning & Development | 58,200 | 29,100 | 0 | 87,300 | 65,300 | 22,000 |  | 7,811 |
| Policy & Finance | 129,400 | 177,400 | 0 | 306,800 | 290,700 | 0 |  | 100,443 |
| Housing: |  |  |  |  |  |  |  |  |
| General Fund | 420,000 | 146,600 | 0 | 566,600 | 566,600 | 0 |  | 351,778 |
| Revenue | 937,400 | -43,300 | 0 | 894,100 | 880,700 | 0 |  | 682,316 |
|  | 2,594,510 | 463,000 | 10,000 | 3,067,510 | 2,881,170 | 516,310 |  | 1,854,161 |

As you can see we have, to date, spent 64% of the revised estimate.

3	RESOURCES

3.1	The amount of capital resources available for 2006/07 has also been revised and consists of:

Spare resources carried forward from 2005/06

Slippage, ie resources promised for the previous year but not yet received

Current year's borrowing approvals

Government grants, eg DEFRA

Contributions towards specific schemes

Estimated usable capital receipts from sales of land, council houses etc

Repair and renewals fund contributions

Transfers from revenue

The revised estimate of the total resources for 2006/07 is set out in detail in Annex 2 (CREAM).

3.2	This now leaves estimated spare resources at 31 March 2007 of:

|  | £000 |
| --- | --- |
| Total Resources | 4,383 |
| Revised Capital Spending Plans | 2,881 |
| Spare Resources | 1,502 |

4	COMMENTS ON OVERALL POSITION

4.1	At this time last year we forecast we would have spare resources of £1,481,000 by the end of March 2007.  A comparison between the actual position and the expected position is as follows:

|  | Position Expected at Jan 2006 £000 | Position Expected at Jan 2007 £000 | Difference £000 |
| --- | --- | --- | --- |
| Resources B/Fwd From 2005/06 | 1,492 | 2,045 | 553 |
| Resources Expected in 2006/07 | 1,892 | 2,338 | 446 |
|  | 3,384 | 4,383 | 999 |
| Expenditure on Schemes 2006/07 | 2,595 | 2,881 | 286 |
| Expected Resources at 31.03.07 | 789 | 1,502 | 713 |

The biggest variations in resources, which were not expected at January 2006, are:

|  | £000 | £000 |
| --- | --- | --- |
| Resources B/Fwd From 2005/06 |  |  |
| Increase in Resources Received: |  |  |
| Actual available in 2005/06 | 5,413 |  |
| Expected at Revised Estimate Time | 5,113 | 300 |
| Less Used in 2005/06 Due to Slippage of Schemes |  | 252 |
|  |  | 552 |
|  |  | 552 |
| Resources Expected in 2006/07 |  |  |
| Increase in Expected External Grant Funding |  | 274 |
| Increase in Expected Usable Capital Receipts |  | 172 |
|  |  | 446 |
|  |  | 1,209 |

|  | £000 |
| --- | --- |
| Expenditure on Schemes between January 2006 and January 2007 |  |
| Slippage From 2005/06 | 463 |
| New Additional Schemes Added to 2006/07 Programme |  |
| Castle Lottery Bid | 213 |
| Edisford Consultancy Costs | 9 |
| Castle Keep Repairs | 80 |
| Schemes Moved to 2007/08 | -516 |
| Schemes Increased at Revised Estimate Time: |  |
| Brungerley Park Improvement Scheme | 10 |
| Children’s Play Areas | 5 |
| Council Offices Toilets | 1 |
| Tennants Suggested Housing Improvements Scheme | 1 |
| Cemetery Wall | 9 |
| Clitheroe Castle Rose Garden | 56 |
| Schemes Reduced at Revised Estimate Time: |  |
| Football Pitches Drainage | -2 |
| Suzuki Pest Control Van | -1 |
| Mowers/Trailer | -3 |
| Grounds Maintenance Vehicles | -7 |
| Chip and Pin Scheme – Deleted from programme | -10 |
| Telephone System | -8 |
| Disabled Facilities Grant at Vale House | -1 |
| Showley Court Improvements | -13 |
| Net Total Change on Scheme Expenditure | 286 |

5	CONCLUSION

5.1	There have been a number of variations affecting both expenditure and resources.  Overall, resources brought forward from 2005/06 have increased by £552,000 however this is mostly offset by the slippage carried forward into the current year.  We expect to receive significantly higher resources in the current year due to increases in expected grants and capital receipts (mostly the sale of Beacon Villas).

5.2	Overall Expenditure is up by £286,000. However this comprises:

|  | £000 |
| --- | --- |
| Slippage from 05/06 | 463 |
| New Schemes added | 302 |
| Schemes moved to next year (07/08) | -516 |
| Schemes increased in the current year. | 82 |
| Schemes reduced in the current year. | -45 |
|  | 286 |

5.3	With only two months of the financial year remaining there is some progress to be made if we are to achieve the revised programme in full.

6	RECOMMENDED THAT COMMITTEE

6.1	Approve the overall revised capital programme 2006/07.

FINANCIAL SERVICES MANAGER

PF9-07/JP/AC

06 FEBRUARY 2007

ANNEX 1

SPECIAL POLICY & FINANCE COMMITTEE

OVERALL REVISED CAPITAL PROGRAMME 2006/07

|  |  | Budget Analysis |  |
| --- | --- | --- | --- |
| Cost | Schemes | Original | Slippage | Additional | Total | Revised | Budget | Total |
| Centre |  | Estimate |  | Approvals | Approved | Estimate | moved to | Expenditure |
|  |  | 2006/07 |  |  | Budget |  | 2007/08 | To Date |
|  |  | £ | £ | £ | £ | £ | £ | £ |
|  | Community Committee |  |  |  |  |  |  |  |
| BPIMP | Brungerley Park Improvement scheme |  | 1,900 | 10,000 | 11,900 | 11,900 |  | 4,475 |
| BPSCT | Replacement of Brungerley sculpture trail | 5,400 | 15,300 |  | 20,700 | 20,700 |  | 7,586 |
| CASED | Castle/Museum/Heritage Improvement Scheme |  | 20,800 | -13,250 | 7,550 | 20,800 |  | 22,746 |
| CLPAT | Cemetery - Resurface paths and roadways |  | 1,600 |  | 1,600 | 1,600 |  | 0 |
| CLWAL | Cemetery - Rebuild wall |  | 11,600 |  | 11,600 | 20,000 |  | 19,435 |
| CSLOT | Castle Lottery Bid |  |  |  |  | 213,000 |  | 168,539 |
| CYCIN | Cycling Initiatives | 5,500 |  |  | 5,500 | 5,500 |  | 13,137 |
| EDICR | Edisford Consultantancy Costs |  |  |  |  | 9,200 |  | 9,200 |
| FENCW | Fencing Improvements at Edisford All Weather Pitch | 15,000 |  |  | 15,000 | 15,000 |  | 13,548 |
| FOODR | Football pitches drainage | 16,900 |  |  | 16,900 | 15,100 |  | 15,030 |
| KEEPR | Castle Keep Repairs - Phase 1 |  |  | 13,250 | 13,250 | 79,400 |  | 0 |
| LFIRD | Provision of Fire Escape at Longridge Depot | 6,300 |  |  | 6,300 | 0 | 6,300 | 0 |
| LOADS | Loading Shovel Waste Transfer Station |  | 60,000 |  | 60,000 | 60,200 |  | 60,184 |
| LOCHG | Grant Aid to Longridge Action Group re Civic Hall |  | 10,000 |  | 10,000 | 10,000 |  | 0 |
| LSREC | Longridge Sports Centre Reception (moved from 05/06) | 54,410 |  |  | 54,410 | 0 | 54,410 | 0 |
| PBOIL | Pool - Replace boiler and calorifier | 96,300 |  |  | 96,300 | 0 | 96,300 | 0 |
| PCRPE | Replace Slaidburn Toilets (moved from 05/06) | 113,040 | -4,300 |  | 108,740 | 108,740 |  | 107,232 |
| PESTS | Replace Pest Control Suzuki Van - Y378 XHG | 10,000 |  |  | 10,000 | 9,100 |  | 9,065 |
| PLAYF | Improvements to children's play areas |  | 29,600 |  | 29,600 | 34,200 |  | 34,195 |
| PLAYG | Improvements to children's play areas | 35,300 |  |  | 35,300 | 35,300 |  | 33,159 |
| POSEC | Pool - Security & Fire alarm | 13,200 |  |  | 13,200 | 13,200 |  | 6,040 |
| RALSH | Replace Grounds Maintenance Allet Shaver with Dennis cylinder mower | 2,245 |  |  | 2,245 | 2,250 |  | 2,245 |
| RCOLT | Replace N313 SWK Dennis Refuse Collection Vehicle | 180,000 |  |  | 180,000 | 180,000 |  | 0 |
| REBIN | Recycling and Residual Waste Containers | 172,500 |  |  | 172,500 | 0 | 172,500 | 0 |
| RGBUF | Replace Grounds Maintenance 4 Allett Buffalo mowers with 1 Dennis | 6,985 |  |  | 6,985 | 6,980 |  | 6,985 |
| RGDCW | Replace Grounds Maintenance Hayter ride-on N383 DCW | 20,800 |  |  | 20,800 | 20,700 |  | 20,700 |
| RGMOW | Purchase of 4 mowing machines & Trailer | 7,700 |  |  | 7,700 | 5,200 |  | 5,159 |
| RGOFR | Replace Grounds Maintenance G190 OFR mini tractor | 9,000 |  |  | 9,000 | 9,000 |  | 9,000 |
| RIBCA | Refurbishment of Ribchester Public Conveniences | 37,200 |  |  | 37,200 | 37,200 |  | 17,887 |
| RLIFT | Bin Lifts (x2) for existing Refuse Vehicles | 30,900 |  |  | 30,900 |  | 30,900 | 0 |
| ROSEG | Rose Garden Castle Grounds |  |  |  | 0 | 56,000 |  | 48,802 |
| RPCHA | Ribblesdale Pool - Refurbish Staff changing rooms & external store |  | 6,700 |  | 6,700 | 7,100 |  | 7,104 |
| RVERG | Replace Grounds Maintenance 3 Blade Verge Cutter Haytor Condor | 4,500 |  |  | 4,500 | 4,500 |  | 4,497 |
| RWFBU | Replace Grounds Maintenance Vehicle R485 FBU Iveco 7.5tonne | 37,000 |  |  | 37,000 | 35,100 |  | 35,090 |
| RWKEG | Replace P715 KEG Ford General Works Vehicle | 15,400 |  |  | 15,400 | 12,100 |  | 12,041 |
| RWXCK | Replace Grounds Maintenance Vehicle P996 XCK with Transit van | 13,500 |  |  | 13,500 | 11,800 |  | 11,726 |
| SDIMP | Improvements to Salthill Depot budget moved from 05/06 | 6,530 |  |  | 6,530 | 7,000 |  | 7,004 |
| SYNCA | Longridge Sports Centre Replace carpet on synthetic pitch | 133,900 |  |  | 133,900 | 0 | 133,900 | 0 |
|  | Total Community Committee | 1,049,510 | 153,200 | 10,000 | 1,212,710 | 1,077,870 | 494,310 | 711,811 |
|  | Planning & Development Committee |  |  |  |  |  |  |  |
| CARPH | Car Parks Rolling Programme |  | 29,100 |  | 29,100 | 7,100 | 22,000 | 6,331 |
| CARPI | Car Parks Rolling Programme | 41,200 |  |  | 41,200 | 41,200 |  | 1,480 |
| ERGTV | Replace screens and ergonomices CCTV system | 17,000 |  |  | 17,000 | 17,000 |  | 0 |
|  | Total Planning & Development Committee | 58,200 | 29,100 | 0 | 87,300 | 65,300 | 22,000 | 7,811 |
|  | Policy & Finance Committee |  |  |  |  |  |  |  |
| BADDA | Building alterations - Disability Discrimination Act |  | 10,000 |  | 10,000 | 10,600 |  | 10,565 |
| CHIPP | Chip and Pin Implementation | 10,000 |  |  | 10,000 | 0 |  | 0 |
| CIVHS | Civic Suite - DDA & Impts to stored water system | 45,000 |  |  | 45,000 | 45,000 |  | 19,055 |
| CROOM | Computer Server Room Improvements | 15,200 |  |  | 15,200 | 15,200 |  | 425 |
| CVSEC | Civic Suite - Replace Security system | 11,600 |  |  | 11,600 | 11,600 |  | 0 |
| EENAB | eEnabling Members | 5,000 |  |  | 5,000 | 5,000 |  | 0 |
| EGIIV | E Government Initiative |  | 60,000 |  | 60,000 | 60,000 |  | 0 |
| OFCEI | Council Offices - Fire safety improvements to ceilings | 21,600 | 7,000 |  | 28,600 | 28,600 |  | 10,739 |
| OFTOL | Council Offices - Toilets |  |  |  |  | 1,300 |  | 1,299 |
| OFWIN | Council Offices - Replace windows |  | 39,800 |  | 39,800 | 39,800 |  | 39,867 |
| ROOFL | Council Offices - Lead replacement & repairs to Roof | 21,000 |  |  | 21,000 | 21,000 |  | 15,365 |
| RTELE | Replace Telephone system |  | 16,000 |  | 16,000 | 8,000 |  | 0 |
| UPFIN | Upgrade of Financial Ledger System |  | 44,600 |  | 44,600 | 44,600 |  | 3,128 |
|  | Total Policy and Finance Committee | 129,400 | 177,400 | 0 | 306,800 | 290,700 | 0 | 100,443 |
|  | Housing |  |  |  |  |  |  |  |
|  | Housing General Fund |  |  |  |  |  |  |  |
| AFORD | Affordable Housing (commissioning rounds) Supported Borrowing |  | 80,000 |  | 80,000 | 80,000 |  | 80,000 |
| EMPTY | Empty Properties |  | 46,000 |  | 46,000 | 0 |  | 0 |
| LHOME | Improvements to Longridge Homeless Facility | 50,000 |  |  | 50,000 | 50,000 |  | 0 |
| Grants |  |  |  |  |  |  |  | 0 |
| DISCP | Disabled Facilities Grants | 120,000 | 20,600 |  | 140,600 | 140,600 |  | 130,622 |
| IMPFN | Private Sector Renewal | 180,000 |  |  | 180,000 | 226,000 |  | 83,423 |
| MINWK | Minor Works | 70,000 |  |  | 70,000 | 70,000 |  | 57,733 |
|  | Total Housing General Fund | 420,000 | 146,600 | 0 | 566,600 | 566,600 | 0 | 351,778 |
|  | Housing Revenue |  |  |  |  |  |  |  |
| HRDFG | HR DFG 9 Vale House Close |  | 4,900 |  | 4,900 | 3,900 |  | 3,876 |
| IMPCM | Council House Improvements - 2006/07 | 937,400 | -70,100 |  | 867,300 | 867,300 |  | 668,953 |
| TENSH | Tenants suggested improvement schemes |  | 5,000 |  | 5,000 | 6,000 |  | 6,011 |
| THIMP | Showley Court improvements |  | 16,900 |  | 16,900 | 3,500 |  | 3,475 |
|  | Total Housing Revenue | 937,400 | -43,300 | 0 | 894,100 | 880,700 | 0 | 682,315 |
|  | Total Housing Committee | 1,357,400 | 103,300 | 0 | 1,460,700 | 1,447,300 | 0 | 1,034,093 |
|  | TOTALS | 2,594,510 | 463,000 | 10,000 | 3,067,510 | 2,881,170 | 516,310 | 1,854,158 |

ANNEX 2

SPECIAL POLICY & FINANCE COMMITTEE

REVISED CAPITAL RESOURCES 2006/07

|  | Actual |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Resources | Brought | Slippage | Original | Additional | Total |
|  | Forward | from 2005/06 | 2006/07 |  | Resources |
|  | £ | £ | £ | £ | £ |
| Government Grants |  |  |  |  |  |
| Disabled Grants | 8,100 |  | 72,000 |  | 80,109 |
| DEFRA - Capital element of Waste Performance & Efficiency Grant |  |  | 23,350 |  | 23,350 |
| DEFRA - Capital element of Waste Performance & Efficiency Grant 05/06 (to use for loading shovel) | 9,886 |  |  |  | 9,886 |
| Other Grants |  |  |  |  | 0 |
| Improvement Grant Repaid |  |  | 0 |  | 0 |
| LCC - Brungerly Park |  |  |  | 10,000 | 10,000 |
| Brungerly Park Improvements Grant from Market Towns Initiative |  |  |  | 10,000 | 10,000 |
| Rose Garden Grant from Market Towns Initiative |  |  |  | 28,000 | 28,000 |
| Lancashire Environmental Fund - Towards Castle Keep Repairs Scheme |  |  |  | 25,000 | 25,000 |
| Regional Park - Grant Request Towards Castle Keep Repairs Scheme |  |  |  | 39,400 | 39,400 |
| HLF Grant towards Castle Lottery Bid Scheme |  |  |  | 160,000 | 160,000 |
| Contributions |  |  |  |  | 0 |
| Longridge High School to provide 40% funding for synthetic pitch |  |  | 53,560 |  | 53,560 |
| Clitheroe Rotary Club - Towards Castle Keep Repairs Scheme |  |  |  | 1,800 | 1,800 |
| Major Repairs Allowance | 230,136 |  | 704,441 |  | 934,577 |
| Housing Capital Grant |  |  | 301,000 |  | 301,000 |
| Borrowing |  |  |  |  | 0 |
| SCE® - HRA |  |  | 33,000 |  | 33,000 |
| Unsupported |  |  | 250,000 |  | 250,000 |
| Unsupported - Three Stream Waste Bins |  |  | 229,650 |  | 229,650 |
| Useable Capital Receipts | 39,604 |  | 396,500 |  | 436,104 |
| Revenue |  |  |  |  | 0 |
| Egovt expenditure capitalised & reimbursed | 50,000 |  |  |  | 50,000 |
| Recreation grant towards Longridge Skate Park | 3,644 |  |  |  | 3,644 |
| HRA where mortgage repayment less than 10k | 4,062 |  |  |  | 4,062 |
| Housing Revenue | 19,788 |  | 0 |  | 19,788 |
| Capital Fund | 683,963 |  |  |  | 683,963 |
| Repair & Renewals Fund | 995,984 |  |  |  | 995,984 |
| Total resources | 2,045,176 | 0.00 | 2,063,501 | 274,200 | 4,382,877 |
| Revised Capital Spending Plans |  |  |  |  | 2,881,170 |
| Spare Resources to carry forward |  |  |  |  | 1,501,707 |

# Text boxes

DECISION