PROGRAMME OF KEY TASKS FOR 3 STREAM WASTE COLLECTION SERVICE

| DATE | DAY | ACTION |
| --- | --- | --- |
| 29 October | Monday | Start of collections on Phase I and trial round and change of collection days for properties on Phase II. |
| 19 October | Friday | Last day for delivery of wheeled bins and information leaflets to properties on Phase I. Last day for delivery of leaflets/calendar to properties on trial round. Last day for delivery of letters to properties on Phase II re change of collection day, etc. |
| 12 October | Monday | Finalise press release for CA&T on 18/25 October, Longridge News on 19/26 October, Lancs Telegraph week commencing 22 October. |
| 1 October | Monday | Delivery of wheeled bins to properties on Phase I to start today (including information leaflets) – allows 3 week delivery period. Delivery of additional wheeled bins to some properties on trial round to start today. |
| 28 September | Friday | Last day by which letters to properties on Phase I are to be received advising of new arrangements and delivery of bins. Last day by which new information leaflets are to be supplied to RVBC from printers. |
| 17 September | Monday | Start distribution of letters to properties in Phase I advising of new arrangements and delivery of wheeled bins (+ properties on trial scheme) – allows 2 week delivery period. Start production of leaflets (12315) |
| 14 September | Friday | Last day by which details of revisions to information leaflets shall be with the printers. Sign off new leaflets. |
| 13 September | Thursday | Second/final amendments and send to printer. |
| 12 September | Wednesday | Return of second proofs from printer. |
| 11 September | Tuesday | Meeting of Community Committee where members are to get report updating on progress. |
| 7 September | Friday | Last day by which Titan require full address list for chipping and delivery of wheeled bins. Complete first amendments and send to printer. |
| DATE | DAY | ACTION |
| 3 September | Monday | Last date for start of revision of information leaflets. Report to Community Committee to be completed by today. |
| 31 August | Friday | Return of first proofs for leaflet from printer. |
| 24 August | Friday | Last date for receipt of revised rounds schedules from ENTEC. Copy deadline for updated leaflets to send to printer. |
| 20 August | Monday | Start drafting of letters and production of delivery point plans. |
| 13 August | Monday | Start sorting data for plans for collection prints. |
| 10 August | Friday | Last day by which data is to be sent to ENTEC for production of final rounds design and schedules. |